## 90 Day Outlook
Site | Description | Metrics (WO/Building) | Upgrades Needed? | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM Scheduled Start Date | MCM Scheduled End Date | MCM/TT | Vendor Start Date | Vendor End Date | Site Confirmation | MCM Gap Status
PDX111 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-05-04 | 2026-03-10 | 2026-06-28 |  | 2026-06-07 13:00 | 2026-07-08 06:59 | MCM-134903284 |  |  |  | MCM Scheduled
PDX112 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-05-10 | 2026-03-16 | 2026-07-04 |  | 2026-06-08 13:00 | 2026-07-09 06:59 | MCM-145242196 |  |  |  | MCM Scheduled
PDX112 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-04 | 2026-04-10 | 2026-07-29 |  | 2026-06-08 07:00 | 2026-07-09 06:59 | MCM-144338241 |  |  |  | MCM Scheduled
PDX111 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-11 | 2026-04-17 | 2026-08-05 |  | 2026-06-07 13:00 | 2026-07-08 06:59 | MCM-136066518 |  |  |  | MCM Scheduled
PDX69 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-07-25 | 2026-05-31 | 2026-09-18 |  | 2026-07-01 07:00 | 2026-07-31 06:55 | MCM-151521619 |  |  |  | MCM Scheduled
PDX57 | [GLOBAL] AMCOP 36M PM V1.0 | 13 | Yes | 2026-07-26 | 2026-06-01 | 2026-09-19 | [7 empty] | MCM Needed (<60d)
PDX99 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | Yes | 2026-08-01 | 2026-06-07 | 2026-09-25 | [7 empty] | MCM Needed (<60d)
PDX132 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 | [7 empty] | MCM Needed (<90d)
PDX96 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | No | 2026-08-15 | 2026-06-21 | 2026-10-09 | [7 empty] | MCM Needed (<90d)
PDX132 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 |  | 2026-07-27 13:00 | 2026-08-26 06:55 | MCM-147982640 |  |  |  | MCM in Draft
PDX54 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 2 | No | 2026-08-15 | 2026-06-21 | 2026-10-09 |  | 2026-07-01 07:00 | 2026-07-31 06:55 | MCM-151535397 |  |  |  | MCM in Draft
PDX57 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 12 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 |  | 2026-06-15 13:00 | 2026-07-16 01:00 | MCM-150275221 |  |  |  | MCM Scheduled
PDX60 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 11 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 |  | 2026-06-15 13:00 | 2026-07-16 01:00 | MCM-150274397 |  |  |  | MCM Scheduled