## 90 Day Outlook
Site | Description | Metrics (WO/Building) | Upgrades Needed? | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM Scheduled Start Date | MCM Scheduled End Date | MCM/TT | Vendor Start Date | Vendor End Date | Site Confirmation | MCM Gap Status
PDX80 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 16 | Yes | 2026-03-13 | 2026-01-17 | 2026-05-07 |  | 2026-04-27 07:00 | 2026-05-28 06:55 | MCM-143631288 |  |  |  | MCM Complete
PDX81 | [GLOBAL] AMCOP 36M PM V1.0 | 6 | Yes | 2026-05-15 | 2026-03-21 | 2026-07-09 |  | 2026-06-18 07:00 | 2026-08-12 06:55 | MCM-150801576 |  |  |  | MCM Pending Approval
PDX82 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-05-24 | 2026-03-30 | 2026-07-18 |  | 2026-05-18 07:00 | 2026-06-18 06:59 | MCM-136370733 |  |  |  | MCM Scheduled
PDX81 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-10 | 2026-04-16 | 2026-08-04 |  | 2026-05-04 07:00 | 2026-06-04 06:59 | MCM-138742066 |  |  |  | MCM Scheduled
PDX83 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-07-01 | 2026-05-07 | 2026-08-25 |  | 2026-05-25 13:00 | 2026-06-25 06:59 | MCM-141405665 |  |  |  | MCM Scheduled
PDX80 | [GLOBAL] AMCOP 36M PM V1.0 | 20 | Yes | 2026-07-30 | 2026-06-05 | 2026-09-23 |  | 2026-06-17 07:00 | 2026-07-18 06:55 | MCM-151427924 |  |  |  | MCM Pending Approval
PDX98 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | No | 2026-08-01 | 2026-06-07 | 2026-09-25 |  | 2026-06-17 07:00 | 2026-07-18 06:55 | MCM-151429971 |  |  |  | MCM Pending Approval
PDX83 | [GLOBAL] AMCOP 36M PM V1.0 | 9 | Yes | 2026-08-07 | 2026-06-13 | 2026-10-01 | [7 empty] | MCM Needed (<90d)
PDX83 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | Yes | 2026-09-18 | 2026-07-25 | 2026-11-12 | [7 empty] | MCM Needed (<90d)