## AMCOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
May | PDXE | PDX63 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 20 |  | 2022-05-30 | 2022-04-05 | 2022-07-24 | Completed |  | 2022-05-30 | 2022-05-30 | [8 empty] | 3 | PM |  | Past Compliance | -1467
October | PDXW | PDX64 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 16 |  | 2022-10-15 | 2022-08-21 | 2022-12-09 | Completed |  | 2022-10-15 | 2022-10-15 | [8 empty] | 3 | PM |  | Past Compliance | -1329
February | PDXE | PDX65 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2023-02-01 | 2022-12-08 | 2023-03-28 | Completed |  | 2023-02-01 | 2023-02-01 | [8 empty] | 3 | PM |  | Past Compliance | -1220
April | PDXW | PDX56 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 13 |  | 2023-04-01 | 2023-02-05 | 2023-05-26 | Completed |  | 2023-04-01 | 2023-04-01 | [8 empty] | 3 | PM |  | Past Compliance | -1161
April | PDXE | PDX54 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 14 |  | 2023-04-02 | 2023-02-06 | 2023-05-27 | Completed |  | 2023-04-02 | 2023-04-02 | [8 empty] | 3 | PM |  | Past Compliance | -1160
June | PDXE | PDX57 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 13 |  | 2023-06-26 | 2023-05-02 | 2023-08-20 | Completed |  | 2023-06-26 | 2023-06-26 | [8 empty] | 3 | PM |  | Past Compliance | -1075
August | PDXE | PDX96 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2023-08-01 | 2023-06-07 | 2023-09-25 | Completed |  | 2023-08-01 | 2023-08-01 | [8 empty] | 3 | PM |  | Past Compliance | -1039
August | PDXW | PDX99 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2023-08-01 | 2023-06-07 | 2023-09-25 | Completed |  | 2023-08-01 | 2023-08-01 | [8 empty] | 3 | PM |  | Past Compliance | -1039
November | PDXW | PDX59 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 5 |  | 2023-11-02 | 2023-09-08 | 2023-12-27 | Cancelled |  | 2023-11-02 | 2023-11-02 | [8 empty] | 3 | PM |  | Past Compliance | -946
January | PDXE | PDX69 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2024-01-06 | 2023-11-12 | 2024-03-01 | Completed |  | 2024-01-06 | 2024-01-06 | [8 empty] | 3 | PM |  | Past Compliance | -881
January | PDXW | PDX59 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 6 |  | 2024-01-30 | 2023-12-06 | 2024-03-25 | Cancelled |  | 2024-01-30 | 2024-01-30 | [8 empty] | 3 | PM |  | Past Compliance | -857
February | PDXW | PDX68 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2024-02-01 | 2023-12-08 | 2024-03-27 | Completed |  | 2024-02-01 | 2024-02-01 | [8 empty] | 3 | PM |  | Past Compliance | -855
March | PDXW | PDX59 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2024-03-31 | 2024-02-05 | 2024-05-25 | Completed |  | 2024-03-31 | 2024-03-31 | [8 empty] | 3 | PM |  | Past Compliance | -796
April | PDXW | PDX66 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2024-04-01 | 2024-02-06 | 2024-05-26 | Completed |  | 2024-04-01 | 2024-04-01 | [8 empty] | 3 | PM |  | Past Compliance | -795
May | PDXE | PDX67 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2024-05-01 | 2024-03-07 | 2024-06-25 | Completed |  | 2024-05-01 | 2024-05-01 | [8 empty] | 3 | PM |  | Past Compliance | -765
May | PDXE | PDX60 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 10 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | PM |  | Past Compliance | -750
June | PDXW | PDX59 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 11 |  | 2024-06-15 | 2024-04-21 | 2024-08-09 | Completed |  | 2024-06-15 | 2024-06-15 | [8 empty] | 3 | PM |  | Past Compliance | -720
July | PDXE | PDX60 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2024-07-14 | 2024-05-20 | 2024-09-07 | Completed |  | 2024-07-14 | 2024-07-14 | [8 empty] | 3 | PM |  | Past Compliance | -691
September | PDXW | PDX62 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 19 |  | 2024-09-11 | 2024-07-18 | 2024-11-05 | Completed |  | 2024-09-11 | 2024-09-11 | [8 empty] | 3 | PM |  | Past Compliance | -632
November | PDXE | PDX51 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2024-11-18 | 2024-09-24 | 2025-01-12 | Completed |  | 2024-11-18 | 2024-11-18 | [8 empty] | 3 | PM |  | Past Compliance | -564
December | PDXW | PDX109 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2024-12-03 | 2024-10-09 | 2025-01-27 | Completed |  | 2024-12-03 | 2024-12-03 | [8 empty] | 3 | PM |  | Past Compliance | -549
February | PDXE | PDX130 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2025-02-01 | 2024-12-08 | 2025-03-28 | Completed |  | 2025-02-01 | 2025-02-01 | [8 empty] | 3 | PM |  | Past Compliance | -489
April | PDXW | PDX1 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 14 |  | 2025-04-26 | 2025-03-02 | 2025-06-20 | Cancelled |  | 2025-04-26 | 2025-04-26 | [8 empty] | 3 | PM |  | Past Compliance | -405
May | PDXE | PDX63 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2025-05-30 | 2025-04-05 | 2025-07-24 | Completed |  | 2025-05-30 | 2025-05-30 | [8 empty] | 3 | PM |  | Past Compliance | -371
August | PDXE | PDX131 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2025-08-15 | 2025-06-21 | 2025-10-09 | Cancelled |  | 2025-08-15 | 2025-08-15 | [8 empty] | 3 | PM |  | Past Compliance | -294
August | PDXE | PDX2 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2025-08-15 | 2025-06-21 | 2025-10-09 | Completed |  | 2025-08-15 | 2025-08-15 | [8 empty] | 3 | PM |  | Past Compliance | -294
August | PDXE | PDX51 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2025-08-15 | 2025-06-21 | 2025-10-09 | Completed |  | 2025-08-15 | 2025-08-15 | [8 empty] | 3 | PM |  | Past Compliance | -294
August | PDXE | PDX54 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 14 |  | 2025-08-15 | 2025-06-21 | 2025-10-09 | Completed |  | 2025-08-15 | 2025-08-15 | [8 empty] | 3 | PM |  | Past Compliance | -294
September | PDXW | PDX50 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2025-09-15 | 2025-07-22 | 2025-11-09 | Completed |  | 2025-09-15 | 2025-09-15 | [8 empty] | 3 | PM |  | Past Compliance | -263
September | PDXW | PDX1 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 14 |  | 2025-09-30 | 2025-08-06 | 2025-11-24 | Completed | MCM-130521782 | 2025-09-30 | 2025-09-30 |  |  | Complete | Tier 2 | xabrahar | 2025-12-08 14:00 | 2026-01-07 08:00 | Successful | 3 | PM |  | Past Compliance | -248 | MCM Complete
September | PDXW | PDX53 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2025-09-30 | 2025-08-06 | 2025-11-24 | Completed |  | 2025-09-30 | 2025-09-30 | [8 empty] | 3 | PM |  | Past Compliance | -248
September | PDXW | PDX59 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 13 |  | 2025-09-30 | 2025-08-06 | 2025-11-24 | Completed |  | 2025-09-30 | 2025-09-30 | [8 empty] | 3 | PM |  | Past Compliance | -248
October | PDXW | PDX64 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2025-10-15 | 2025-08-21 | 2025-12-09 | Completed | MCM-138180676 | 2025-10-15 | 2025-10-15 |  |  | Complete | Tier 2 | bwolsen | 2025-12-08 08:00 | 2026-01-08 07:59 | Successful | 3 | PM |  | Past Compliance | -233 | MCM Complete
November | PDXW | PDX110 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2025-11-21 | 2025-09-27 | 2026-01-15 | Completed | MCM-143356203 | 2025-11-21 | 2025-11-21 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 3 | PM |  | Past Compliance | -196 | MCM Complete
November | PDXE | PDX131 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2025-11-23 | 2025-09-29 | 2026-01-17 | Completed | MCM-132785774 | 2025-11-23 | 2025-11-23 |  |  | Complete | Tier 3 | baehpetd | 2025-12-08 14:00 | 2025-12-20 02:00 | Successful | 3 | PM |  | Past Compliance | -194 | MCM Complete
January | PDXW | PDX68 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 6 |  | 2026-01-30 | 2025-12-06 | 2026-03-26 | Completed | MCM-138981780 | 2026-01-30 | 2026-01-30 |  |  | Complete | Tier 2 | ryantcol | 2026-01-05 14:00 | 2026-02-04 02:00 | Successful | 3 | PM |  | Past Compliance | -126 | MCM Complete
February | PDXE | PDX65 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2026-02-01 | 2025-12-08 | 2026-03-28 | Completed | MCM-141713975 | 2026-02-01 | 2026-02-01 |  |  | Complete | Tier 2 | cabless | 2026-01-26 08:00 | 2026-02-26 07:59 | Successful | 3 | PM |  | Past Compliance | -124 | MCM Complete
April | PDXW | PDX56 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 13 |  | 2026-04-01 | 2026-02-05 | 2026-05-26 | Completed | MCM-136172170 | 2026-04-01 | 2026-04-01 |  |  | Complete | Tier 2 | baltgarz | 2026-03-26 19:00 | 2026-04-26 01:00 | Successful | 3 | PM |  | Past Compliance | -65 | MCM Complete
May | PDXW | PDX111 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2026-05-04 | 2026-03-10 | 2026-06-28 | Open | MCM-134903284 | 2026-05-04 | 2026-05-04 |  |  | Scheduled | Tier 2 | juavvill | 2026-06-07 13:00 | 2026-07-08 06:59 |  | 3 | PM |  | Within Compliance | -32 | MCM Scheduled
May | PDXW | PDX112 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2026-05-10 | 2026-03-16 | 2026-07-04 | Open | MCM-145242196 | 2026-05-10 | 2026-05-10 |  |  | Scheduled | Tier 2 | smjonah | 2026-06-08 13:00 | 2026-07-09 06:59 |  | 3 | PM |  | Within Compliance | -26 | MCM Scheduled
July | PDXE | PDX57 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 13 |  | 2026-07-26 | 2026-06-01 | 2026-09-19 | Open |  | 2026-07-26 | 2026-07-26 | [8 empty] | 3 | PM |  | Within Compliance | 51 | MCM Needed (<60d)
August | PDXW | PDX99 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-08-01 | 2026-06-07 | 2026-09-25 | Open |  | 2026-08-01 | 2026-08-01 | [8 empty] | 3 | PM |  | Outside Compliance | 57 | MCM Needed (<60d)
August | PDXE | PDX132 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open |  | 2026-08-15 | 2026-08-15 | [8 empty] | 3 | PM |  | Outside Compliance | 71 | MCM Needed (<90d)
August | PDXE | PDX96 | Hanley Energy | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open |  | 2026-08-15 | 2026-08-15 | [8 empty] | 3 | PM |  | Outside Compliance | 71 | MCM Needed (<90d)

## AMCOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXE | PDX2 | Hanley Energy | AMCOP Timer Correction Post Re-Audit | CM |  |  | 2 |  | 2024-04-03 | 2024-02-08 | 2024-05-28 | Completed |  | 2024-04-03 | 2024-04-03 | [8 empty] | 5 | CM |  | Past Compliance | -793
April | PDXE | PDX132 | Hanley Energy | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 25 |  | 2024-04-08 | 2024-02-13 | 2024-06-02 | Completed |  | 2024-04-08 | 2024-04-08 | [8 empty] | 3 | FSB |  | Past Compliance | -788
April | PDXE | PDX130 | Hanley Energy | AMCOP 1.6A troubleshoot | CM |  |  | 1 |  | 2024-04-09 | 2024-02-14 | 2024-06-03 | Completed |  | 2024-04-09 | 2024-04-09 | [8 empty] | 5 | CM |  | Past Compliance | -787
April | PDXW | PDX56 | Hanley Energy | EOT Basic Training Session (Rack Down & AMCOP) | CM |  |  | 1 |  | 2024-04-12 | 2024-02-17 | 2024-06-06 | Completed |  | 2024-04-12 | 2024-04-12 | [8 empty] | 5 | CM |  | Past Compliance | -784
April | PDXW | PDX1 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 14 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX109 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:22 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:22 | 2024-04-26 19:22 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXW | PDX110 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:23 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:23 | 2024-04-26 19:23 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXW | PDX111 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX112 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 21 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX130 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:24 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:24 | 2024-04-26 19:24 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX131 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX2 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX50 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 19:26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:26 | 2024-04-26 19:26 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX51 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX53 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 19:27 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:27 | 2024-04-26 19:27 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX54 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 14 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX56 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 13 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX57 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 13 |  | 2024-04-26 19:28 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:28 | 2024-04-26 19:28 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXW | PDX59 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 13 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX60 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 12 |  | 2024-04-26 19:28 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:28 | 2024-04-26 19:28 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXW | PDX62 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 19 |  | 2024-04-26 19:29 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:29 | 2024-04-26 19:29 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX63 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX64 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX65 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX66 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 19:30 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:30 | 2024-04-26 19:30 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX67 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX68 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXE | PDX69 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 20:19 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 20:19 | 2024-04-26 20:19 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXE | PDX96 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXW | PDX99 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
May | PDXE | PDX131 | Hanley Energy | AMCOP Settings Change - Q4 2023 (rev. 3) | REG-FOLL |  |  | 2 |  | 2024-05-01 | 2024-03-07 | 2024-06-25 | Completed |  | 2024-05-01 | 2024-05-01 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -765
May | PDXE | PDX132 | Hanley Energy | FRB: Update AMCOP to V4.0 | FRB |  |  | 30 |  | 2024-05-05 | 2024-03-11 | 2024-06-29 | Completed |  | 2024-05-05 | 2024-05-05 | [8 empty] | 5 | FRB |  | Past Compliance | -761
May | PDXW | PDX66 | Hanley Energy | AMCOP Settings Change - Q4 2023 AMCOP 6A | CM |  |  | 26 |  | 2024-05-10 | 2024-03-16 | 2024-07-04 | Completed |  | 2024-05-10 | 2024-05-10 | [8 empty] | 5 | CM |  | Past Compliance | -756
May | PDXW | PDX1 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 14 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX109 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 06:31 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:31 | 2024-05-16 06:31 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX110 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 06:31 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:31 | 2024-05-16 06:31 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX111 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 06:32 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:32 | 2024-05-16 06:32 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX112 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 21 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX130 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 06:53 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:53 | 2024-05-16 06:53 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX131 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX2 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX50 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX51 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX53 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX54 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 14 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX56 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 13 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX57 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 13 |  | 2024-05-16 06:55 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:55 | 2024-05-16 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX59 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 13 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX60 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 12 |  | 2024-05-16 06:56 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:56 | 2024-05-16 06:56 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX62 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 19 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX63 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX64 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX65 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX66 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 06:58 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:58 | 2024-05-16 06:58 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX67 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX68 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 06:59 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:59 | 2024-05-16 06:59 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXE | PDX96 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX99 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXW | PDX111 | Hanley Energy | AMCOP 2.6B PSU Replacement | CM |  |  | 1 |  | 2024-05-20 | 2024-03-26 | 2024-07-14 | Completed |  | 2024-05-20 | 2024-05-20 | [8 empty] | 4 | CM |  | Past Compliance | -746
May | PDXE | PDX130 | Hanley Energy | Rework AMCOP Setting Changes MCM | PR |  |  | 1 |  | 2024-05-25 | 2024-03-31 | 2024-07-19 | Completed |  | 2024-05-25 | 2024-05-25 | [8 empty] | 5 | PR |  | Past Compliance | -741
June | PDXW | PDX64 | Hanley Energy | AMCOP 3B Battery Replacment | CM |  |  | 1 |  | 2024-06-05 | 2024-04-11 | 2024-07-30 | Completed |  | 2024-06-05 | 2024-06-05 | [8 empty] | 5 | CM |  | Past Compliance | -730
June | PDXW | PDX111 | Hanley Energy | AMCOP Settings Change - Q4 2023 (rev.3) FSB 1176 | CM |  |  | 1 |  | 2024-06-07 | 2024-04-13 | 2024-08-01 | Completed |  | 2024-06-07 | 2024-06-07 | [8 empty] | 5 | CM |  | Past Compliance | -728
June | PDXW | PDX50 | Hanley Energy | FSB: Basler-AMCOP Wiring Standardization | CM |  |  | 18 |  | 2024-06-10 | 2024-04-16 | 2024-08-04 | Completed |  | 2024-06-10 | 2024-06-10 | [8 empty] | 5 | CM |  | Past Compliance | -725
June | PDXW | PDX112 | Hanley Energy | PDX112 AMCOP Settings Change - Q4 2023 (rev.3) FSB 1176 | PR |  |  | 3 |  | 2024-06-14 | 2024-04-20 | 2024-08-08 | Completed |  | 2024-06-14 | 2024-06-14 | [8 empty] | 5 | PR |  | Past Compliance | -721
July | PDXW | PDX110 | Hanley Energy | AMCOP_DC_UPS_Batt_Not_Healthy AMCOP DC-UPS Battery Needs to Be Replaced | CM |  |  | 3 |  | 2024-07-05 | 2024-05-11 | 2024-08-29 | Completed |  | 2024-07-05 | 2024-07-05 | [8 empty] | 5 | CM |  | Past Compliance | -700
July | PDXW | PDX1 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 14 |  | 2024-07-23 16:54 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:54 | 2024-07-23 16:54 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX109 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 15:59 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 15:59 | 2024-07-23 15:59 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX110 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:00 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:00 | 2024-07-23 16:00 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX111 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:01 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:01 | 2024-07-23 16:01 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX112 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 21 |  | 2024-07-23 16:01 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:01 | 2024-07-23 16:01 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX130 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:55 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:55 | 2024-07-23 16:55 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX131 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:02 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:02 | 2024-07-23 16:02 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX132 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:02 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:02 | 2024-07-23 16:02 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX194 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXE | PDX2 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXW | PDX50 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 16:05 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:05 | 2024-07-23 16:05 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX51 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 16:05 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:05 | 2024-07-23 16:05 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX53 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 16:06 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:06 | 2024-07-23 16:06 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX54 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 14 |  | 2024-07-23 16:06 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:06 | 2024-07-23 16:06 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX56 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 13 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXE | PDX57 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 13 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXW | PDX59 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 13 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXE | PDX60 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 12 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXW | PDX62 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 19 |  | 2024-07-23 16:08 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:08 | 2024-07-23 16:08 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX63 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXW | PDX64 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:09 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:09 | 2024-07-23 16:09 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX65 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:09 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:09 | 2024-07-23 16:09 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX66 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:59 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:59 | 2024-07-23 16:59 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX67 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:10 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:10 | 2024-07-23 16:10 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX68 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:11 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:11 | 2024-07-23 16:11 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX69 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:11 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:11 | 2024-07-23 16:11 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXE | PDX96 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXW | PDX99 | Hanley Energy | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 16:16 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:16 | 2024-07-23 16:16 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXW | PDX50 | Hanley Energy | AMCOP Conduit Sealant | CM |  |  | 18 |  | 2024-07-29 | 2024-06-04 | 2024-09-22 | Completed |  | 2024-07-29 | 2024-07-29 | [8 empty] | 5 | CM |  | Past Compliance | -676
July | PDXW | PDX53 | Hanley Energy | AMCOP Conduit Sealant | CM |  |  | 1 |  | 2024-07-29 | 2024-06-04 | 2024-09-22 | Completed |  | 2024-07-29 | 2024-07-29 | [8 empty] | 5 | CM |  | Past Compliance | -676
August | PDXW | PDX112 | Hanley Energy | FRB: Update AMCOP to V4.0 | FRB |  |  | 13 |  | 2024-08-03 02:42 | 2024-06-09 | 2024-09-27 | Completed |  | 2024-08-03 02:42 | 2024-08-03 02:42 | [8 empty] | 5 | FRB |  | Past Compliance | -671
August | PDXE | PDX194 | Hanley Energy | FRB: Update AMCOP to V4.0 | FRB |  |  | 20 |  | 2024-08-03 | 2024-06-09 | 2024-09-27 | Completed |  | 2024-08-03 | 2024-08-03 | [8 empty] | 5 | FRB |  | Past Compliance | -671
August | PDXW | PDX64 | Hanley Energy | PDX64 FSB AMCOP Sealant MCM/ Procedure/ Test | CM |  |  | 1 |  | 2024-08-05 | 2024-06-11 | 2024-09-29 | Completed |  | 2024-08-05 | 2024-08-05 | [8 empty] | 5 | CM |  | Past Compliance | -669
August | PDXW | PDX66 | Hanley Energy | Amcop 6B SER Troubleshoot and Repair | CM |  |  | 2 |  | 2024-08-07 | 2024-06-13 | 2024-10-01 | Completed |  | 2024-08-07 | 2024-08-07 | [8 empty] | 4 | CM |  | Past Compliance | -667
September | PDXW | PDX112 | Hanley Energy | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 26 |  | 2024-09-01 | 2024-07-08 | 2024-10-26 | Completed |  | 2024-09-01 | 2024-09-01 | [8 empty] | 3 | SRVY |  | Past Compliance | -642
September | PDXE | PDX194 | Hanley Energy | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 23 |  | 2024-09-01 | 2024-07-08 | 2024-10-26 | Completed |  | 2024-09-01 | 2024-09-01 | [8 empty] | 3 | SRVY |  | Past Compliance | -642
September | PDXE | PDX65 | Hanley Energy | AMCOP 3A Battery Replacement | CM |  |  | 1 |  | 2024-09-06 | 2024-07-13 | 2024-10-31 | Completed |  | 2024-09-06 | 2024-09-06 | [8 empty] | 5 | CM |  | Past Compliance | -637
September | PDXE | PDX130 | Hanley Energy | PDX130 AMCOP 2.6A Battery Replacement | CM |  |  | 2 |  | 2024-09-17 | 2024-07-24 | 2024-11-11 | Completed |  | 2024-09-17 | 2024-09-17 | [8 empty] | 5 | CM |  | Past Compliance | -626
September | PDXW | PDX111 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 15 |  | 2024-09-18 | 2024-07-25 | 2024-11-12 | Completed |  | 2024-09-18 | 2024-09-18 | [8 empty] | 3 | FSB |  | Past Compliance | -625
September | PDXE | PDX130 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 20 |  | 2024-09-18 | 2024-07-25 | 2024-11-12 | Completed |  | 2024-09-18 | 2024-09-18 | [8 empty] | 3 | FSB |  | Past Compliance | -625
September | PDXE | PDX132 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 17 |  | 2024-09-18 12:13 | 2024-07-25 | 2024-11-12 | Completed |  | 2024-09-18 12:13 | 2024-09-18 12:13 | [8 empty] | 3 | FSB |  | Past Compliance | -624
September | PDXE | PDX69 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 24 |  | 2024-09-18 12:14 | 2024-07-25 | 2024-11-12 | Completed |  | 2024-09-18 12:14 | 2024-09-18 12:14 | [8 empty] | 3 | FSB |  | Past Compliance | -624
October | PDXW | PDX111 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 8 |  | 2024-10-01 06:55 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 06:55 | 2024-10-01 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXW | PDX112 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 2 |  | 2024-10-01 06:55 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 06:55 | 2024-10-01 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXE | PDX130 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 8 |  | 2024-10-01 06:55 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 06:55 | 2024-10-01 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXE | PDX132 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 10 |  | 2024-10-01 06:55 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 06:55 | 2024-10-01 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXE | PDX57 | Hanley Energy | PDX57 AMCOP 4C TROUBLESHOOT - REPAIR | CM |  |  | 2 |  | 2024-10-01 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 | 2024-10-01 | [8 empty] | 5 | CM |  | Past Compliance | -612
October | PDXE | PDX69 | Hanley Energy | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 8 |  | 2024-10-01 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 | 2024-10-01 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXE | PDX195 | Hanley Energy | FRB: Update AMCOP to V4.0 | FRB |  |  | 16 |  | 2024-10-16 | 2024-08-22 | 2024-12-10 | Completed |  | 2024-10-16 | 2024-10-16 | [8 empty] | 5 | FRB |  | Past Compliance | -597
November | PDXW | PDX56 | Hanley Energy | Assist FE with Lab AMCOP update and receive training. | PR |  |  | 1 |  | 2024-11-01 | 2024-09-07 | 2024-12-26 | Completed |  | 2024-11-01 | 2024-11-01 | [8 empty] | 5 | PR |  | Past Compliance | -581
November | PDXE | PDX195 | Hanley Energy | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 80 |  | 2024-11-03 08:10 | 2024-09-09 | 2024-12-28 | Completed |  | 2024-11-03 08:10 | 2024-11-03 08:10 | [8 empty] | 3 | FSB |  | Past Compliance | -578
November | PDXE | PDX130 | Hanley Energy | 36M AMCOP PM SOP/MCM creation | PR |  |  | 2 |  | 2024-11-06 | 2024-09-12 | 2024-12-31 | Completed |  | 2024-11-06 | 2024-11-06 | [8 empty] | 5 | PR |  | Past Compliance | -576
November | PDXE | PDX2 | Hanley Energy | 18A AMCOP Batt repair | CM |  |  | 1 |  | 2024-11-07 | 2024-09-13 | 2025-01-01 | Completed |  | 2024-11-07 | 2024-11-07 | [8 empty] | 5 | CM |  | Past Compliance | -575
November | PDXE | PDX194 | Hanley Energy | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 115 |  | 2024-11-13 | 2024-09-19 | 2025-01-07 | Completed |  | 2024-11-13 | 2024-11-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -569
November | PDXE | PDX130 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 127 |  | 2024-11-15 11:17 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 11:17 | 2024-11-15 11:17 | [8 empty] | 3 | FSB |  | Past Compliance | -566
November | PDXE | PDX132 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 126 |  | 2024-11-15 15:23 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 15:23 | 2024-11-15 15:23 | [8 empty] | 3 | FSB |  | Past Compliance | -566
November | PDXE | PDX54 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 128 |  | 2024-11-15 15:23 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 15:23 | 2024-11-15 15:23 | [8 empty] | 3 | FSB |  | Past Compliance | -566
November | PDXE | PDX57 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 63 |  | 2024-11-15 15:25 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 15:25 | 2024-11-15 15:25 | [8 empty] | 3 | FSB |  | Past Compliance | -566
November | PDXE | PDX69 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 125 |  | 2024-11-15 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 | 2024-11-15 | [8 empty] | 3 | FSB |  | Past Compliance | -567
November | PDXW | PDX111 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 123 |  | 2024-11-22 15:50 | 2024-09-28 | 2025-01-16 | Completed |  | 2024-11-22 15:50 | 2024-11-22 15:50 | [8 empty] | 3 | FSB |  | Past Compliance | -559
November | PDXW | PDX112 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 121 |  | 2024-11-22 | 2024-09-28 | 2025-01-16 | Completed |  | 2024-11-22 | 2024-11-22 | [8 empty] | 3 | FSB |  | Past Compliance | -560
November | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 30 |  | 2024-11-22 | 2024-09-28 | 2025-01-16 | Completed |  | 2024-11-22 | 2024-11-22 | [8 empty] | 3 | FSB |  | Past Compliance | -560
December | PDXE | PDX195 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 23 |  | 2024-12-04 08:45 | 2024-10-10 | 2025-01-28 | Completed |  | 2024-12-04 08:45 | 2024-12-04 08:45 | [8 empty] | 3 | FSB |  | Past Compliance | -547
December | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 14 |  | 2024-12-12 | 2024-10-18 | 2025-02-05 | Completed |  | 2024-12-12 | 2024-12-12 | [8 empty] | 3 | FSB |  | Past Compliance | -540
December | PDXE | PDX63 | Hanley Energy | AMCOP 2B PLC Fault | CM |  |  | 2 |  | 2024-12-14 | 2024-10-20 | 2025-02-07 | Completed |  | 2024-12-14 | 2024-12-14 | [8 empty] | 5 | CM |  | Past Compliance | -538
December | PDXE | PDX194 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 25 |  | 2024-12-17 19:35 | 2024-10-23 | 2025-02-10 | Completed |  | 2024-12-17 19:35 | 2024-12-17 19:35 | [8 empty] | 3 | FSB |  | Past Compliance | -534
December | PDXE | PDX57 | Hanley Energy | PDX57 AMCOP puttying | PR |  |  | 1 |  | 2024-12-27 | 2024-11-02 | 2025-02-20 | Completed |  | 2024-12-27 | 2024-12-27 | [8 empty] | 5 | PR |  | Past Compliance | -525
January | PDXE | PDX63 | Hanley Energy | ISSUE FOUND DURING LLT - AMCOP date/time wrong | CM |  |  | 3 |  | 2025-01-03 | 2024-11-09 | 2025-02-27 | Completed |  | 2025-01-03 | 2025-01-03 | [8 empty] | 3 | CM |  | Past Compliance | -518
January | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 12 |  | 2025-01-06 | 2024-11-12 | 2025-03-02 | Completed |  | 2025-01-06 | 2025-01-06 | [8 empty] | 3 | FSB |  | Past Compliance | -515
January | PDXE | PDX195 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 62 |  | 2025-01-06 18:41 | 2024-11-12 | 2025-03-02 | Completed |  | 2025-01-06 18:41 | 2025-01-06 18:41 | [8 empty] | 3 | FSB |  | Past Compliance | -514
January | PDXE | PDX2 | Hanley Energy | ISSUE FOUND DURING LLT - AMCOP indicating lineup in deadbus when the lineup was | CM |  |  | 1 |  | 2025-01-07 | 2024-11-13 | 2025-03-03 | Completed |  | 2025-01-07 | 2025-01-07 | [8 empty] | 3 | CM |  | Past Compliance | -514
January | PDXW | PDX1 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 14 |  | 2025-01-22 12:16 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:16 | 2025-01-22 12:16 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX109 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 | 2025-01-22 | [8 empty] | 5 | FRB |  | Past Compliance | -499
January | PDXW | PDX110 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:17 | 2024-11-28 | 2025-03-18 | Completed |  | 2025-01-22 12:17 | 2025-01-22 12:17 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX112 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:19 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:19 | 2025-01-22 12:19 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX130 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:19 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:19 | 2025-01-22 12:19 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX131 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:20 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:20 | 2025-01-22 12:20 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX132 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:21 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:21 | 2025-01-22 12:21 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX194 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:24 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:24 | 2025-01-22 12:24 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX2 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 | 2025-01-22 | [8 empty] | 5 | FRB |  | Past Compliance | -499
January | PDXW | PDX50 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 12:26 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:26 | 2025-01-22 12:26 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX51 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 12:26 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:26 | 2025-01-22 12:26 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX53 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 12:27 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:27 | 2025-01-22 12:27 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX54 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 14 |  | 2025-01-22 12:28 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:28 | 2025-01-22 12:28 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX56 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 13 |  | 2025-01-22 12:28 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:28 | 2025-01-22 12:28 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX57 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 13 |  | 2025-01-22 12:29 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:29 | 2025-01-22 12:29 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX59 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 13 |  | 2025-01-22 12:29 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:29 | 2025-01-22 12:29 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX60 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 12 |  | 2025-01-22 12:30 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:30 | 2025-01-22 12:30 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX62 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 19 |  | 2025-01-22 12:31 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:31 | 2025-01-22 12:31 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX63 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 22 |  | 2025-01-22 12:31 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:31 | 2025-01-22 12:31 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX68 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:34 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:34 | 2025-01-22 12:34 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX69 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:34 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:34 | 2025-01-22 12:34 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX96 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:40 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:40 | 2025-01-22 12:40 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXW | PDX99 | Hanley Energy | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:40 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:40 | 2025-01-22 12:40 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXE | PDX132 | Hanley Energy | AMCOP 1.5B Utility Breaker Racked out. Transfer to Utility Inhibited. | CM |  |  | 1 |  | 2025-01-29 | 2024-12-05 | 2025-03-25 | Completed |  | 2025-01-29 | 2025-01-29 | [8 empty] | 5 | CM |  | Past Compliance | -492
January | PDXW | PDX111 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 28 |  | 2025-01-30 | 2024-12-06 | 2025-03-26 | Completed |  | 2025-01-30 | 2025-01-30 | [8 empty] | 3 | FSB |  | Past Compliance | -491
February | PDXW | PDX111 | Hanley Energy | AMCOP V5 Upgrades | REG-FOLL |  |  | 27 |  | 2025-02-02 | 2024-12-09 | 2025-03-29 | Completed |  | 2025-02-02 | 2025-02-02 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -488
February | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 24 |  | 2025-02-04 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 | 2025-02-04 | [8 empty] | 3 | FSB |  | Past Compliance | -486
February | PDXW | PDX112 | Hanley Energy | AMCOP C2 R4 Relay Base | CM |  |  | 2 |  | 2025-02-05 | 2024-12-12 | 2025-04-01 | Completed |  | 2025-02-05 | 2025-02-05 | [8 empty] | 5 | CM |  | Past Compliance | -485
February | PDXE | PDX131 | Hanley Energy | PDX131 AMCOP V5.0 Upgrade | PR |  |  | 1 |  | 2025-02-06 | 2024-12-13 | 2025-04-02 | Completed |  | 2025-02-06 | 2025-02-06 | [8 empty] | 5 | PR |  | Past Compliance | -484
February | PDXE | PDX131 | Hanley Energy | [PDX131][Planned]AMCOP 1.1B Troubleshoot/Repair | CM |  |  | 1 |  | 2025-02-06 | 2024-12-13 | 2025-04-02 | Completed |  | 2025-02-06 | 2025-02-06 | [8 empty] | 5 | CM |  | Past Compliance | -484
February | PDXE | PDX69 | Hanley Energy | LLT AMCOP follow up | CM |  |  | 6 |  | 2025-02-07 | 2024-12-14 | 2025-04-03 | Completed |  | 2025-02-07 | 2025-02-07 | [8 empty] | 5 | CM |  | Past Compliance | -483
February | PDXE | PDX51 | Hanley Energy | LLT Corrective-Amcop M-selector switch loose wire causing not to switch to auto. | CM |  |  | 2 |  | 2025-02-11 | 2024-12-18 | 2025-04-07 | Completed |  | 2025-02-11 | 2025-02-11 | [8 empty] | 3 | CM |  | Past Compliance | -479
February | PDXE | PDX2 | Hanley Energy | PDX2 amcop timer labels | PR |  |  | 1 |  | 2025-02-12 | 2024-12-19 | 2025-04-08 | Completed |  | 2025-02-12 | 2025-02-12 | [8 empty] | 5 | PR |  | Past Compliance | -478
February | PDXW | PDX109 | Hanley Energy | AMCOP Firmware V5.0 upgrade | REG-FOLL |  |  | 1 |  | 2025-02-14 | 2024-12-21 | 2025-04-10 | Completed |  | 2025-02-14 | 2025-02-14 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -476
February | PDXE | PDX67 | Hanley Energy | PDX67_Writing MCM for AMCOP_Update 5.0 | PR |  |  | 1 |  | 2025-02-18 | 2024-12-25 | 2025-04-14 | Completed |  | 2025-02-18 | 2025-02-18 | [8 empty] | 5 | PR |  | Past Compliance | -472
February | PDXE | PDX132 | Hanley Energy | PDX132 FRB: AMCOP V5 Upgrade | CM |  |  | 1 |  | 2025-02-19 | 2024-12-26 | 2025-04-15 | Completed |  | 2025-02-19 | 2025-02-19 | [8 empty] | 5 | CM |  | Past Compliance | -471
February | PDXW | PDX170 | Hanley Energy | AMCOP 2.3A/Door Latch Correction | CM |  |  | 1 |  | 2025-02-24 | 2024-12-31 | 2025-04-20 | Completed |  | 2025-02-24 | 2025-02-24 | [8 empty] | 5 | CM |  | Past Compliance | -466
March | PDXW | PDX64 | Hanley Energy | AMCOP 6C PLC Watchdog Active: Logic Failed | CM |  |  | 4 |  | 2025-03-04 | 2025-01-08 | 2025-04-28 | Completed |  | 2025-03-04 | 2025-03-04 | [8 empty] | 5 | CM |  | Past Compliance | -458
March | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 12 |  | 2025-03-05 14:51 | 2025-01-09 | 2025-04-29 | Completed |  | 2025-03-05 14:51 | 2025-03-05 14:51 | [8 empty] | 3 | FSB |  | Past Compliance | -456
March | PDXE | PDX130 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 1 |  | 2025-03-06 | 2025-01-10 | 2025-04-30 | Completed |  | 2025-03-06 | 2025-03-06 | [8 empty] | 3 | FSB |  | Past Compliance | -456
March | PDXE | PDX63 | Hanley Energy | firmware and hardware changes to AMCOP | CM |  |  | 1 |  | 2025-03-06 | 2025-01-10 | 2025-04-30 | Completed |  | 2025-03-06 | 2025-03-06 | [8 empty] | 5 | CM |  | Past Compliance | -456
March | PDXE | PDX65 | Hanley Energy | firmware and hardware changes to AMCOP | CM |  |  | 1 |  | 2025-03-06 | 2025-01-10 | 2025-04-30 | Cancelled |  | 2025-03-06 | 2025-03-06 | [8 empty] | 5 | CM |  | Past Compliance | -456
March | PDXW | PDX170 | Hanley Energy | AMCOP 1.1A/1.1B Log download | CM |  |  | 1 |  | 2025-03-07 | 2025-01-11 | 2025-05-01 | Completed |  | 2025-03-07 | 2025-03-07 | [8 empty] | 5 | CM |  | Past Compliance | -455
March | PDXE | PDX133 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 9 |  | 2025-03-11 | 2025-01-15 | 2025-05-05 | Completed |  | 2025-03-11 | 2025-03-11 | [8 empty] | 3 | FSB |  | Past Compliance | -451
March | PDXE | PDX196 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 8 |  | 2025-03-21 | 2025-01-25 | 2025-05-15 | Completed |  | 2025-03-21 | 2025-03-21 | [8 empty] | 3 | FSB |  | Past Compliance | -441
March | PDXE | PDX63 | Hanley Energy | AMCOP 3B Autofail | CM |  |  | 1 |  | 2025-03-24 | 2025-01-28 | 2025-05-18 | Completed |  | 2025-03-24 | 2025-03-24 | [8 empty] | 5 | CM |  | Past Compliance | -438
March | PDXW | PDX50 | Hanley Energy | AMCOP 5B Utility Transfer to Generator | CM |  |  | 1 |  | 2025-03-26 | 2025-01-30 | 2025-05-20 | Completed |  | 2025-03-26 | 2025-03-26 | [8 empty] | 5 | CM |  | Past Compliance | -436
April | PDXE | PDX133 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 13 |  | 2025-04-01 | 2025-02-05 | 2025-05-26 | Completed |  | 2025-04-01 | 2025-04-01 | [8 empty] | 3 | FSB |  | Past Compliance | -430
April | PDXE | PDX194 | Hanley Energy | PDX194 AMCOP Setting Update Racks with no BBU | PR |  |  | 1 |  | 2025-04-01 | 2025-02-05 | 2025-05-26 | Completed |  | 2025-04-01 | 2025-04-01 | [8 empty] | 5 | PR |  | Past Compliance | -430
April | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 33 |  | 2025-04-02 | 2025-02-06 | 2025-05-27 | Completed |  | 2025-04-02 | 2025-04-02 | [8 empty] | 3 | FSB |  | Past Compliance | -429
April | PDXE | PDX196 | Hanley Energy | FSB: Update AMCOP v4.1 HMI network port setting R1 | FSB |  |  | 13 |  | 2025-04-03 10:05 | 2025-02-07 | 2025-05-28 | Completed |  | 2025-04-03 10:05 | 2025-04-03 10:05 | [8 empty] | 3 | FSB |  | Past Compliance | -427
April | PDXW | PDX68 | Hanley Energy | AMCOP DC-UPS Battery Needs to Be Replaced Condition | CM |  |  | 1 |  | 2025-04-10 | 2025-02-14 | 2025-06-04 | Completed |  | 2025-04-10 | 2025-04-10 | [8 empty] | 3 | CM |  | Past Compliance | -421
April | PDXW | PDX110 | Hanley Energy | AMCOP 2.4B Troubleshooting | CM |  |  | 1 |  | 2025-04-13 | 2025-02-17 | 2025-06-07 | Completed |  | 2025-04-13 | 2025-04-13 | [8 empty] | 3 | CM |  | Past Compliance | -418
April | PDXW | PDX171 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 54 |  | 2025-04-14 | 2025-02-18 | 2025-06-08 | Completed |  | 2025-04-14 | 2025-04-14 | [8 empty] | 3 | FSB |  | Past Compliance | -417
April | PDXW | PDX112 | Hanley Energy | AMCOP 2.4A Battery Replacement | CM |  |  | 1 |  | 2025-04-21 | 2025-02-25 | 2025-06-15 | Completed |  | 2025-04-21 | 2025-04-21 | [8 empty] | 5 | CM |  | Past Compliance | -410
April | PDXE | PDX54 | Hanley Energy | AMCOP SER Rewiring | PR |  |  | 1 |  | 2025-04-23 | 2025-02-27 | 2025-06-17 | Completed |  | 2025-04-23 | 2025-04-23 | [8 empty] | 5 | PR |  | Past Compliance | -408
April | PDXE | PDX130 | Hanley Energy | AMCOP C1 Troubleshoot & Repair | CM |  |  | 1 |  | 2025-04-25 | 2025-03-01 | 2025-06-19 | Completed |  | 2025-04-25 | 2025-04-25 | [8 empty] | 5 | CM |  | Past Compliance | -406
May | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 10 |  | 2025-05-01 10:53 | 2025-03-07 | 2025-06-25 | Completed |  | 2025-05-01 10:53 | 2025-05-01 10:53 | [8 empty] | 3 | FSB |  | Past Compliance | -399
May | PDXE | PDX196 | Hanley Energy | FSB: Identify AMCOPs running software V4.1 for network setting update R1 | SRVY |  |  | 9 |  | 2025-05-05 | 2025-03-11 | 2025-06-29 | Completed |  | 2025-05-05 | 2025-05-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -396
May | PDXW | PDX53 | Hanley Energy | AMCOP 4C Battery Replacement | CM |  |  | 1 |  | 2025-05-05 | 2025-03-11 | 2025-06-29 | Completed |  | 2025-05-05 | 2025-05-05 | [8 empty] | 5 | CM |  | Past Compliance | -396
May | PDXE | PDX2 | Hanley Energy | AMCOP 20B Battery Exchange | CM |  |  | 2 |  | 2025-05-07 | 2025-03-13 | 2025-07-01 | Completed |  | 2025-05-07 | 2025-05-07 | [8 empty] | 5 | CM |  | Past Compliance | -394
May | PDXE | PDX195 | Hanley Energy | AMCOP 2.6B DC UPS battery replacement | CM |  |  | 1 |  | 2025-05-09 | 2025-03-15 | 2025-07-03 | Completed |  | 2025-05-09 | 2025-05-09 | [8 empty] | 5 | CM |  | Past Compliance | -392
May | PDXE | PDX194 | Hanley Energy | FSB: Update AMCOP Settings for BBU-Less OPTDC Lineups | FSB |  |  | 27 |  | 2025-05-12 09:07 | 2025-03-18 | 2025-07-06 | Completed |  | 2025-05-12 09:07 | 2025-05-12 09:07 | [8 empty] | 2 | FSB |  | Past Compliance | -388
May | PDXW | PDX171 | Hanley Energy | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 33 |  | 2025-05-15 | 2025-03-21 | 2025-07-09 | Completed |  | 2025-05-15 | 2025-05-15 | [8 empty] | 3 | FSB |  | Past Compliance | -386
May | PDXE | PDX133 | Hanley Energy | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 5 |  | 2025-05-19 | 2025-03-25 | 2025-07-13 | Completed |  | 2025-05-19 | 2025-05-19 | [8 empty] | 3 | SRVY |  | Past Compliance | -382
May | PDXE | PDX69 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 5 |  | 2025-05-19 | 2025-03-25 | 2025-07-13 | Completed |  | 2025-05-19 | 2025-05-19 | [8 empty] | 3 | FSB |  | Past Compliance | -382
May | PDXE | PDX605 | Hanley Energy | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 2 |  | 2025-05-21 | 2025-03-27 | 2025-07-15 | Completed |  | 2025-05-21 | 2025-05-21 | [8 empty] | 3 | FSB |  | Past Compliance | -380
May | PDXE | PDX194 | Hanley Energy | AMCOP 1.5B DC UPS Battery Replacement | CM |  |  | 1 |  | 2025-05-23 | 2025-03-29 | 2025-07-17 | Completed |  | 2025-05-23 | 2025-05-23 | [8 empty] | 5 | CM |  | Past Compliance | -378
June | PDXW | PDX110 | Hanley Energy | AMCOP 1.4A PSU2 RDY Wire Repair | CM |  |  | 2 |  | 2025-06-02 | 2025-04-08 | 2025-07-27 | Completed |  | 2025-06-02 | 2025-06-02 | [8 empty] | 5 | CM |  | Past Compliance | -368
June | PDXE | PDX63 | Hanley Energy | AMCOP 8A 36M | CM |  |  | 22 |  | 2025-06-03 | 2025-04-09 | 2025-07-28 | Completed |  | 2025-06-03 | 2025-06-03 | [8 empty] | 5 | CM |  | Past Compliance | -367
June | PDXE | PDX196 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 25 |  | 2025-06-04 13:50 | 2025-04-10 | 2025-07-29 | Completed |  | 2025-06-04 13:50 | 2025-06-04 13:50 | [8 empty] | 3 | FSB |  | Past Compliance | -365
June | PDXW | PDX170 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 36 |  | 2025-06-05 14:55 | 2025-04-11 | 2025-07-30 | Completed |  | 2025-06-05 14:55 | 2025-06-05 14:55 | [8 empty] | 3 | FSB |  | Past Compliance | -364
June | PDXW | PDX1 | Hanley Energy | AMCOP 4A Battery Replacement | CM |  |  | 1 |  | 2025-06-09 | 2025-04-15 | 2025-08-03 | Completed |  | 2025-06-09 | 2025-06-09 | [8 empty] | 5 | CM |  | Past Compliance | -361
June | PDXE | PDX133 | Hanley Energy | FSB: Identify AMCOPs running software V4.1 for network setting update R1 | SRVY |  |  | 19 |  | 2025-06-10 | 2025-04-16 | 2025-08-04 | Completed |  | 2025-06-10 | 2025-06-10 | [8 empty] | 3 | SRVY |  | Past Compliance | -360
June | PDXE | PDX131 | Hanley Energy | PDX131 AMCOP 1.1B Battery Replacement | CM |  |  | 1 |  | 2025-06-23 | 2025-04-29 | 2025-08-17 | Completed |  | 2025-06-23 | 2025-06-23 | [8 empty] | 5 | CM |  | Past Compliance | -347
July | PDXE | PDX133 | Hanley Energy | PDX133 2.5A AMCOP Update | CM |  |  | 9 |  | 2025-07-01 | 2025-05-07 | 2025-08-25 | Completed |  | 2025-07-01 | 2025-07-01 | [8 empty] | 5 | CM |  | Past Compliance | -339
July | PDXE | PDX195 | Hanley Energy | HS AMCOP Start Up | CM |  |  | 1 |  | 2025-07-02 | 2025-05-08 | 2025-08-26 | Completed |  | 2025-07-02 | 2025-07-02 | [8 empty] | 5 | CM |  | Past Compliance | -338
July | PDXW | PDX171 | Hanley Energy | AMCOP 2C PLC Replacement | CM |  |  | 6 |  | 2025-07-03 | 2025-05-09 | 2025-08-27 | Completed |  | 2025-07-03 | 2025-07-03 | [8 empty] | 5 | CM |  | Past Compliance | -337
July | PDXW | PDX171 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 44 |  | 2025-07-03 17:24 | 2025-05-09 | 2025-08-27 | Completed |  | 2025-07-03 17:24 | 2025-07-03 17:24 | [8 empty] | 3 | FSB |  | Past Compliance | -336
July | PDXW | PDX170 | Hanley Energy | PDX170/AMCOP MK2 Software Update | CM |  |  | 1 |  | 2025-07-07 | 2025-05-13 | 2025-08-31 | Completed |  | 2025-07-07 | 2025-07-07 | [8 empty] | 5 | CM |  | Past Compliance | -333
July | PDXW | PDX1 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 14 |  | 2025-07-11 07:55 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 07:55 | 2025-07-11 07:55 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXW | PDX109 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX110 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX111 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 07:56 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 07:56 | 2025-07-11 07:56 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX130 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 07:58 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 07:58 | 2025-07-11 07:58 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX131 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 07:59 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 07:59 | 2025-07-11 07:59 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX132 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 08:00 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:00 | 2025-07-11 08:00 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX196 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 15 |  | 2025-07-11 08:06 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:06 | 2025-07-11 08:06 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX2 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX50 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX51 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX53 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX54 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 14 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX56 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 13 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX57 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 13 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX59 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 13 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX60 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 12 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX605 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX62 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 19 |  | 2025-07-11 08:13 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:13 | 2025-07-11 08:13 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX63 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 32 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX64 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX65 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 08:15 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:15 | 2025-07-11 08:15 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXW | PDX66 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 08:15 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:15 | 2025-07-11 08:15 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXE | PDX67 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX68 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX69 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXE | PDX96 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXW | PDX99 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 08:24 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:24 | 2025-07-11 08:24 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXW | PDX604 | Hanley Energy | FSB: Identify AMCOPs running software V4.1 for network setting update R1 | SRVY |  |  | 2 |  | 2025-07-16 | 2025-05-22 | 2025-09-09 | Completed |  | 2025-07-16 | 2025-07-16 | [8 empty] | 3 | SRVY |  | Past Compliance | -324
July | PDXW | PDX112 | Hanley Energy | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 28 |  | 2025-07-21 | 2025-05-27 | 2025-09-14 | Open |  | 2025-07-21 | 2025-07-21 | [8 empty] | 5 | FRB |  | Past Compliance | -319 | MCM OVERDUE
July | PDXW | PDX170 | Hanley Energy | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 10 |  | 2025-07-21 | 2025-05-27 | 2025-09-14 | Completed |  | 2025-07-21 | 2025-07-21 | [8 empty] | 5 | FRB |  | Past Compliance | -319
July | PDXE | PDX194 | Hanley Energy | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 28 |  | 2025-07-21 11:17 | 2025-05-27 | 2025-09-14 | Open |  | 2025-07-21 11:17 | 2025-07-21 11:17 | [8 empty] | 5 | FRB |  | Past Compliance | -318 | MCM OVERDUE
July | PDXE | PDX195 | Hanley Energy | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 35 |  | 2025-07-21 10:21 | 2025-05-27 | 2025-09-14 | Open |  | 2025-07-21 10:21 | 2025-07-21 10:21 | [8 empty] | 5 | FRB |  | Past Compliance | -318 | MCM OVERDUE
July | PDXE | PDX63 | Hanley Energy | AMCOP 6A Battery Replacement | CM |  |  | 12 |  | 2025-07-23 | 2025-05-29 | 2025-09-16 | Completed |  | 2025-07-23 | 2025-07-23 | [8 empty] | 5 | CM |  | Past Compliance | -317
August | PDXE | PDX131 | Hanley Energy | FSB AMCOP V6 Upgrade | CM |  |  | 14 |  | 2025-08-10 | 2025-06-16 | 2025-10-04 | Completed |  | 2025-08-10 | 2025-08-10 | [8 empty] | 5 | CM |  | Past Compliance | -299
August | PDXW | PDX1 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 14 |  | 2025-08-14 18:44 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 18:44 | 2025-08-14 18:44 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXW | PDX170 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 27 |  | 2025-08-14 18:48 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 18:48 | 2025-08-14 18:48 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXE | PDX2 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 18 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXW | PDX50 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 20 |  | 2025-08-14 18:54 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 18:54 | 2025-08-14 18:54 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXE | PDX51 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 18 |  | 2025-08-14 18:55 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 18:55 | 2025-08-14 18:55 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXW | PDX53 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 18 |  | 2025-08-14 18:56 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 18:56 | 2025-08-14 18:56 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXW | PDX604 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXE | PDX605 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXW | PDX99 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXE | PDX96 | Hanley Energy | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-15 | 2025-06-21 | 2025-10-09 | Completed |  | 2025-08-15 | 2025-08-15 | [8 empty] | 4 | FSB |  | Past Compliance | -294
August | PDXW | PDX171 | Hanley Energy | PDX171 2.1C AMCOP HMI Replacement | CM |  |  | 1 |  | 2025-08-18 | 2025-06-24 | 2025-10-12 | Completed |  | 2025-08-18 | 2025-08-18 | [8 empty] | 5 | CM |  | Past Compliance | -291
August | PDXE | PDX2 | Hanley Energy | PDX 67 amcop procedure | PR |  |  | 1 |  | 2025-08-20 | 2025-06-26 | 2025-10-14 | Completed |  | 2025-08-20 | 2025-08-20 | [8 empty] | 5 | PR |  | Past Compliance | -289
August | PDXE | PDX131 | Hanley Energy | AMCOP SER (PLC) BCD Wiring and IP Validation | CM |  |  | 4 |  | 2025-08-28 16:32 | 2025-07-04 | 2025-10-22 | Open |  | 2025-08-28 16:32 | 2025-08-28 16:32 | [8 empty] | 5 | CM |  | Past Compliance | -280 | MCM OVERDUE
September | PDXE | PDX133 | Hanley Energy | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 5 |  | 2025-09-02 | 2025-07-09 | 2025-10-27 | Completed |  | 2025-09-02 | 2025-09-02 | [8 empty] | 3 | FSB |  | Past Compliance | -276
September | PDXE | PDX69 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 2 |  | 2025-09-07 | 2025-07-14 | 2025-11-01 | Completed |  | 2025-09-07 | 2025-09-07 | [8 empty] | 5 | CM |  | Past Compliance | -271
September | PDXE | PDX131 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-09-08 | 2025-07-15 | 2025-11-02 | Completed |  | 2025-09-08 | 2025-09-08 | [8 empty] | 5 | CM |  | Past Compliance | -270
September | PDXE | PDX196 | Hanley Energy | PDX196 House Generator AMCOP in Auto Fail | CM |  |  | 1 |  | 2025-09-10 | 2025-07-17 | 2025-11-04 | Completed |  | 2025-09-10 | 2025-09-10 | [8 empty] | 5 | CM |  | Past Compliance | -268
September | PDXE | PDX67 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 6 |  | 2025-09-10 | 2025-07-17 | 2025-11-04 | Completed |  | 2025-09-10 | 2025-09-10 | [8 empty] | 5 | CM |  | Past Compliance | -268
September | PDXE | PDX54 | Hanley Energy | UPS 6A/ AMCOP discrepancy | CM |  |  | 1 |  | 2025-09-15 | 2025-07-22 | 2025-11-09 | Completed |  | 2025-09-15 | 2025-09-15 | [8 empty] | 5 | CM |  | Past Compliance | -263
September | PDXW | PDX170 | Hanley Energy | FSB: Increase settings on AMCOP Mk2 systems | FSB |  |  | 27 |  | 2025-09-16 11:18 | 2025-07-23 | 2025-11-10 | Completed |  | 2025-09-16 11:18 | 2025-09-16 11:18 | [8 empty] | 3 | FSB |  | Past Compliance | -261
September | PDXW | PDX53 | Hanley Energy | AMCOP 6B Battery Replacement | CM |  |  | 1 |  | 2025-09-16 | 2025-07-23 | 2025-11-10 | Completed |  | 2025-09-16 | 2025-09-16 | [8 empty] | 5 | CM |  | Past Compliance | -262
September | PDXE | PDX132 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-09-17 | 2025-07-24 | 2025-11-11 | Completed |  | 2025-09-17 | 2025-09-17 | [8 empty] | 5 | CM |  | Past Compliance | -261
September | PDXE | PDX605 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-09-17 | 2025-07-24 | 2025-11-11 | Completed |  | 2025-09-17 | 2025-09-17 | [8 empty] | 5 | CM |  | Past Compliance | -261
September | PDXW | PDX64 | Hanley Energy | PDX64 AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 23 |  | 2025-09-17 | 2025-07-24 | 2025-11-11 | Completed | MCM-138180676 | 2025-09-17 | 2025-09-17 |  |  | Complete | Tier 2 | bwolsen | 2025-12-08 08:00 | 2026-01-08 07:59 | Successful | 5 | CM |  | Past Compliance | -261 | MCM Complete
September | PDXW | PDX112 | Hanley Energy | AMCOP SER (PLC) BCD Wiring and IP Validation | PR |  |  | 1 |  | 2025-09-21 | 2025-07-28 | 2025-11-15 | Completed |  | 2025-09-21 | 2025-09-21 | [8 empty] | 5 | PR |  | Past Compliance | -257
October | PDXE | PDX63 | Hanley Energy | Global Action Item[PDX63][AMCOP SER (PLC) BCD Wiring and IP Validation] | CM |  |  | 1 |  | 2025-10-01 | 2025-08-07 | 2025-11-25 | Completed |  | 2025-10-01 | 2025-10-01 | [8 empty] | 5 | CM |  | Past Compliance | -247
October | PDXW | PDX1 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 2 |  | 2025-10-02 | 2025-08-08 | 2025-11-26 | Completed | MCM-130521782 | 2025-10-02 | 2025-10-02 |  |  | Complete | Tier 2 | xabrahar | 2025-12-08 14:00 | 2026-01-07 08:00 | Successful | 3 | FSB |  | Past Compliance | -246 | MCM Complete
October | PDXW | PDX110 | Hanley Energy | AMCOP Battery replacement | CM |  |  | 1 |  | 2025-10-05 | 2025-08-11 | 2025-11-29 | Completed |  | 2025-10-05 | 2025-10-05 | [8 empty] | 5 | CM |  | Past Compliance | -243
October | PDXE | PDX133 | Hanley Energy | PDX133 AMCOP Troubleshoot and Repair | CM |  |  | 1 |  | 2025-10-11 | 2025-08-17 | 2025-12-05 | Completed | MCM-140805548 | 2025-10-11 | 2025-10-11 |  |  | Complete | Tier 3 | chrenr | 2025-12-29 14:00 | 2026-01-20 02:00 | Successful | 5 | CM |  | Past Compliance | -237 | MCM Complete
October | PDXE | PDX51 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 1 |  | 2025-10-13 | 2025-08-19 | 2025-12-07 | Completed |  | 2025-10-13 | 2025-10-13 | [8 empty] | 5 | PR |  | Past Compliance | -235
October | PDXE | PDX54 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 1 |  | 2025-10-13 | 2025-08-19 | 2025-12-07 | Completed |  | 2025-10-13 | 2025-10-13 | [8 empty] | 5 | PR |  | Past Compliance | -235
October | PDXE | PDX69 | Hanley Energy | 1.4-1.6 AMCOP 36M PM | CM |  |  | 3 |  | 2025-10-13 04:24 | 2025-08-19 | 2025-12-07 | Open | MCM-140214255 | 2025-10-13 04:24 | 2025-10-13 04:24 |  |  | Cancelled | Tier 2 | jmiveson | 2026-01-05 08:00 | 2026-02-04 08:00 |  | 5 | CM |  | Past Compliance | -235 | MCM Cancelled — Resubmit
October | PDXE | PDX2 | Hanley Energy | AMCOP logs | PR |  |  | 1 |  | 2025-10-28 | 2025-09-03 | 2025-12-22 | Completed | MCM-142049976 | 2025-10-28 | 2025-10-28 |  |  | Complete | Tier 2 | bzucker | 2026-01-12 12:30 | 2026-02-09 10:00 | Successful | 5 | PR |  | Past Compliance | -220 | MCM Complete
November | PDXE | PDX131 | Hanley Energy | AMCOP 1.1B UPS Battery Replacement | CM |  |  | 1 |  | 2025-11-06 | 2025-09-12 | 2025-12-31 | Completed | MCM-132785774 | 2025-11-06 | 2025-11-06 |  |  | Complete | Tier 3 | baehpetd | 2025-12-08 14:00 | 2025-12-20 02:00 | Successful | 5 | CM |  | Past Compliance | -211 | MCM Complete
November | PDXE | PDX2 | Hanley Energy | Amcop file translation. | PR |  |  | 1 |  | 2025-11-07 | 2025-09-13 | 2026-01-01 | Completed | MCM-142049976 | 2025-11-07 | 2025-11-07 |  |  | Complete | Tier 2 | bzucker | 2026-01-12 12:30 | 2026-02-09 10:00 | Successful | 5 | PR |  | Past Compliance | -210 | MCM Complete
November | PDXW | PDX59 | Hanley Energy | PDX59 AMCOP SER PLC/IP WIRING VALIDATION | CM |  |  | 1 |  | 2025-11-10 | 2025-09-16 | 2026-01-04 | Completed |  | 2025-11-10 | 2025-11-10 | [8 empty] | 4 | CM |  | Past Compliance | -207
November | PDXW | PDX171 | Hanley Energy | PDX171 2.6A AMCOP HMI/PLC Replacement | CM |  |  | 1 |  | 2025-11-11 | 2025-09-17 | 2026-01-05 | Completed |  | 2025-11-11 | 2025-11-11 | [8 empty] | 5 | CM |  | Past Compliance | -206
November | PDXW | PDX62 | Hanley Energy | AMCOP 6A Stack Light Replacement | CM |  |  | 1 |  | 2025-11-12 | 2025-09-18 | 2026-01-06 | Completed |  | 2025-11-12 | 2025-11-12 | [8 empty] | 5 | CM |  | Past Compliance | -205
November | PDXW | PDX172 | Hanley Energy | FSB: Increase settings on AMCOP Mk2 systems | FSB |  |  | 39 |  | 2025-11-14 | 2025-09-20 | 2026-01-08 | Completed |  | 2025-11-14 | 2025-11-14 | [8 empty] | 3 | FSB |  | Past Compliance | -203
November | PDXW | PDX59 | Hanley Energy | AMCOP V6.0 Upgrades 2A MCM Creation | PR |  |  | 1 |  | 2025-11-14 | 2025-09-20 | 2026-01-08 | Completed |  | 2025-11-14 | 2025-11-14 | [8 empty] | 5 | PR |  | Past Compliance | -203
November | PDXW | PDX56 | Hanley Energy | AMCOP V6.0 Upgrades 6A MCM Creation | PR |  |  | 1 |  | 2025-11-27 | 2025-10-03 | 2026-01-21 | Completed |  | 2025-11-27 | 2025-11-27 | [8 empty] | 5 | PR |  | Past Compliance | -190
December | PDXW | PDX172 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 39 |  | 2025-12-01 15:14 | 2025-10-07 | 2026-01-25 | Completed |  | 2025-12-01 15:14 | 2025-12-01 15:14 | [8 empty] | 3 | FSB |  | Past Compliance | -185
December | PDXW | PDX56 | Hanley Energy | AMCOP V6.0 Upgrades 6B MCM Creation | PR |  |  | 15 |  | 2025-12-05 | 2025-10-11 | 2026-01-29 | Completed |  | 2025-12-05 | 2025-12-05 | [8 empty] | 5 | PR |  | Past Compliance | -182
December | PDXW | PDX59 | Hanley Energy | AMCOP V6.0 Upgrades 7A MCM Creation | PR |  |  | 15 |  | 2025-12-05 | 2025-10-11 | 2026-01-29 | Completed |  | 2025-12-05 | 2025-12-05 | [8 empty] | 5 | PR |  | Past Compliance | -182
December | PDXW | PDX111 | Hanley Energy | PDX111 AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-12-09 | 2025-10-15 | 2026-02-02 | Completed | MCM-140110919 | 2025-12-09 | 2025-12-09 |  |  | Complete | Tier 2 | joelloza | 2025-12-30 08:00 | 2026-01-30 07:59 | Successful | 5 | CM |  | Past Compliance | -178 | MCM Complete
December | PDXW | PDX68 | Hanley Energy | PDX68 AMCOP 36M PM | CM |  |  | 2 |  | 2025-12-11 | 2025-10-17 | 2026-02-04 | Completed | MCM-138981780 | 2025-12-11 | 2025-12-11 |  |  | Complete | Tier 2 | ryantcol | 2026-01-05 14:00 | 2026-02-04 02:00 | Successful | 5 | CM |  | Past Compliance | -176 | MCM Complete
December | PDXE | PDX2 | Hanley Energy | Perform firmware and hardware upgrades to AMCOP 20A | CM |  |  | 20 |  | 2025-12-12 | 2025-10-18 | 2026-02-05 | Completed | MCM-142049976 | 2025-12-12 | 2025-12-12 |  |  | Complete | Tier 2 | bzucker | 2026-01-12 12:30 | 2026-02-09 10:00 | Successful | 5 | CM |  | Past Compliance | -175 | MCM Complete
December | PDXE | PDX131 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-12-15 | 2025-10-21 | 2026-02-08 | Completed | MCM-137899544 | 2025-12-15 | 2025-12-15 |  |  | Complete | Tier 3 | manuebmi | 2025-12-17 08:00 | 2026-01-15 07:55 | Successful | 5 | CM |  | Past Compliance | -172 | MCM Complete
December | PDXE | PDX2 | Hanley Energy | 13A AMCOP SER (PLC) BCD Wiring and IP Validation | PR |  |  | 3 |  | 2025-12-16 | 2025-10-22 | 2026-02-09 | Completed | MCM-142049976 | 2025-12-16 | 2025-12-16 |  |  | Complete | Tier 2 | bzucker | 2026-01-12 12:30 | 2026-02-09 10:00 | Successful | 5 | PR |  | Past Compliance | -171 | MCM Complete
December | PDXE | PDX130 | Hanley Energy | FSB: Perform firmware and hardware upgrades to AMCOP | PR |  |  | 29 |  | 2025-12-20 | 2025-10-26 | 2026-02-13 | Completed | MCM-144843493 | 2025-12-20 | 2025-12-20 |  |  | Pending Approval | Tier 2 | jimelver | 2026-03-09 13:00 | 2026-04-09 01:00 |  | 5 | PR |  | Past Compliance | -167
December | PDXE | PDX194 | Hanley Energy | AMCOP SER PLC Wiring | PR |  |  | 1 |  | 2025-12-22 | 2025-10-28 | 2026-02-15 | Completed | MCM-132551901 | 2025-12-22 | 2025-12-22 |  |  | Complete | Tier 2 | kbencomo | 2026-02-09 16:00 | 2026-03-10 06:55 | Successful | 5 | PR |  | Past Compliance | -165 | MCM Complete
December | PDXW | PDX1 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 15 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Open | MCM-130521782 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | xabrahar | 2025-12-08 14:00 | 2026-01-07 08:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX109 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-143356540 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX110 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 14:32 | 2025-10-29 | 2026-02-16 | Completed | MCM-143356203 | 2025-12-23 14:32 | 2025-12-23 14:32 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXW | PDX111 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 14:33 | 2025-10-29 | 2026-02-16 | Open | MCM-140110919 | 2025-12-23 14:33 | 2025-12-23 14:33 |  |  | Complete | Tier 2 | joelloza | 2025-12-30 08:00 | 2026-01-30 07:59 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXW | PDX112 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-131235586 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | smjonah | 2026-01-26 14:00 | 2026-02-17 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX131 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-137899544 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 3 | manuebmi | 2025-12-17 08:00 | 2026-01-15 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX132 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-135261884 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | colldtim | 2026-01-29 14:00 | 2026-03-01 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX133 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-140805548 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 3 | chrenr | 2025-12-29 14:00 | 2026-01-20 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX171 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Open | MCM-137918488 | 2025-12-23 | 2025-12-23 |  |  | Scheduled | Tier 2 | tarjosh | 2026-03-16 13:00 | 2026-04-01 01:00 |  | 5 | FSB |  | Past Compliance | -164 | MCM Scheduled
December | PDXE | PDX194 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 14:39 | 2025-10-29 | 2026-02-16 | Completed | MCM-132551901 | 2025-12-23 14:39 | 2025-12-23 14:39 |  |  | Complete | Tier 2 | kbencomo | 2026-02-09 16:00 | 2026-03-10 06:55 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXE | PDX195 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-135111500 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | esgap | 2026-02-24 14:00 | 2026-03-27 06:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX196 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 14:40 | 2025-10-29 | 2026-02-16 | Open | MCM-142880100 | 2025-12-23 14:40 | 2025-12-23 14:40 |  |  | Complete | Tier 3 | dilgates | 2026-01-26 14:00 | 2026-01-31 02:00 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXW | PDX50 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 19 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed |  | 2025-12-23 | 2025-12-23 | [8 empty] | 5 | FSB |  | Past Compliance | -164
December | PDXE | PDX51 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 19 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Open | MCM-136321219 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | zferanto | 2026-02-11 14:00 | 2026-03-11 13:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX53 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 19 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Open |  | 2025-12-23 | 2025-12-23 | [8 empty] | 5 | FSB |  | Past Compliance | -164 | MCM OVERDUE
December | PDXE | PDX54 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 15 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-136321701 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | zferanto | 2026-02-10 14:00 | 2026-03-10 13:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX57 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 14 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-142538477 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX60 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 13 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-142537766 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX604 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-143357244 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX605 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-135325228 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | colldtim | 2026-02-23 14:00 | 2026-03-19 01:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX62 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 20 |  | 2025-12-23 14:45 | 2025-10-29 | 2026-02-16 | Open | MCM-143732068 | 2025-12-23 14:45 | 2025-12-23 14:45 |  |  | Complete | Tier 2 | crrjesu | 2026-02-16 08:00 | 2026-03-14 06:55 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXE | PDX63 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-135642351 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | jvanorsh | 2026-02-05 08:00 | 2026-03-08 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX64 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-138180676 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | bwolsen | 2025-12-08 08:00 | 2026-01-08 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX65 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-141713975 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | cabless | 2026-01-26 08:00 | 2026-02-26 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX67 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed |  | 2025-12-23 | 2025-12-23 | [8 empty] | 5 | FSB |  | Past Compliance | -164
December | PDXW | PDX68 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-138981780 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | ryantcol | 2026-01-05 14:00 | 2026-02-04 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX69 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-142310462 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | batrocki | 2026-01-27 08:00 | 2026-02-26 08:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX96 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-142538611 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXW | PDX99 | Hanley Energy | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Open | MCM-143742247 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | crrjesu | 2026-02-16 08:00 | 2026-03-14 06:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXE | PDX67 | Hanley Energy | PDX67/Troubleshoot-Repair AMCOP | CM |  |  | 1 |  | 2025-12-26 | 2025-11-01 | 2026-02-19 | Completed |  | 2025-12-26 | 2025-12-26 | [8 empty] | 5 | CM |  | Past Compliance | -161
December | PDXE | PDX69 | Hanley Energy | PDX69 AMCOP v6 DLB Timer Update | CM |  |  | 1 |  | 2025-12-27 | 2025-11-02 | 2026-02-20 | Completed | MCM-142310462 | 2025-12-27 | 2025-12-27 |  |  | Complete | Tier 2 | batrocki | 2026-01-27 08:00 | 2026-02-26 08:00 | Successful | 5 | CM |  | Past Compliance | -160 | MCM Complete
December | PDXE | PDX63 | Hanley Energy | Global Action Item[PDX63][AMCOP SER (PLC) BCD Wiring and IP Validation] | CM |  |  | 1 |  | 2025-12-29 | 2025-11-04 | 2026-02-22 | Completed | MCM-135642351 | 2025-12-29 | 2025-12-29 |  |  | Complete | Tier 2 | jvanorsh | 2026-02-05 08:00 | 2026-03-08 07:59 | Successful | 5 | CM |  | Past Compliance | -158 | MCM Complete
January | PDXE | PDX65 | Hanley Energy | PDX65 AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 1 |  | 2026-01-03 | 2025-11-09 | 2026-02-27 | Completed | MCM-141713975 | 2026-01-03 | 2026-01-03 |  |  | Complete | Tier 2 | cabless | 2026-01-26 08:00 | 2026-02-26 07:59 | Successful | 5 | PR |  | Past Compliance | -153 | MCM Complete
January | PDXW | PDX172 | Hanley Energy | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 17 |  | 2026-01-05 10:14 | 2025-11-11 | 2026-03-01 | Completed |  | 2026-01-05 10:14 | 2026-01-05 10:14 | [8 empty] | 3 | FSB |  | Past Compliance | -150
January | PDXW | PDX68 | Hanley Energy | AMCOP SER(BCD) PLC/IP Wiring Validation | REG-FOLL |  |  | 1 |  | 2026-01-06 | 2025-11-12 | 2026-03-02 | Completed | MCM-138981780 | 2026-01-06 | 2026-01-06 |  |  | Complete | Tier 2 | ryantcol | 2026-01-05 14:00 | 2026-02-04 02:00 | Successful | 5 | REG-FOLL |  | Past Compliance | -150 | MCM Complete
January | PDXW | PDX111 | Hanley Energy | AMCOP V6 Upgrade | CM |  |  | 2 |  | 2026-01-09 | 2025-11-15 | 2026-03-05 | Open | MCM-140110919 | 2026-01-09 | 2026-01-09 |  |  | Complete | Tier 2 | joelloza | 2025-12-30 08:00 | 2026-01-30 07:59 | Successful | 5 | CM |  | Past Compliance | -147 | MCM Complete
January | PDXE | PDX2 | Hanley Energy | 15B AMCOP V6 UPGRADE | CM |  |  | 5 |  | 2026-01-12 | 2025-11-18 | 2026-03-08 | Completed | MCM-142049976 | 2026-01-12 | 2026-01-12 |  |  | Complete | Tier 2 | bzucker | 2026-01-12 12:30 | 2026-02-09 10:00 | Successful | 5 | CM |  | Past Compliance | -144 | MCM Complete
January | PDXE | PDX51 | Hanley Energy | ISSUE FOUND DURING LLT - AMCOP 6B Failed to Open MCBU | CM |  |  | 1 |  | 2026-01-14 | 2025-11-20 | 2026-03-10 | Completed | MCM-136321219 | 2026-01-14 | 2026-01-14 |  |  | Complete | Tier 2 | zferanto | 2026-02-11 14:00 | 2026-03-11 13:00 | Successful | 1 | CM |  | Past Compliance | -142 | MCM Complete
January | PDXE | PDX57 | Hanley Energy | AMCOP Wiring Validation | CM |  |  | 1 |  | 2026-01-17 | 2025-11-23 | 2026-03-13 | Completed | MCM-142538477 | 2026-01-17 | 2026-01-17 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | CM |  | Past Compliance | -139 | MCM Complete
January | PDXE | PDX60 | Hanley Energy | AMCOP Wiring Validation | CM |  |  | 1 |  | 2026-01-17 | 2025-11-23 | 2026-03-13 | Completed | MCM-142537766 | 2026-01-17 | 2026-01-17 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | CM |  | Past Compliance | -139 | MCM Complete
January | PDXE | PDX96 | Hanley Energy | AMCOP Wiring Validation | CM |  |  | 1 |  | 2026-01-17 | 2025-11-23 | 2026-03-13 | Completed | MCM-142538611 | 2026-01-17 | 2026-01-17 |  |  | Complete | Tier 2 | livintra | 2026-02-18 14:00 | 2026-03-07 02:00 | Successful | 5 | CM |  | Past Compliance | -139 | MCM Complete
January | PDXW | PDX110 | Hanley Energy | PDX110 AMCOP SER PLC-IP and Wiring Validation | CM |  |  | 1 |  | 2026-01-21 | 2025-11-27 | 2026-03-17 | Completed | MCM-143356203 | 2026-01-21 | 2026-01-21 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | CM |  | Past Compliance | -135 | MCM Complete
January | PDXE | PDX196 | Hanley Energy | PDX196 AMCOP 2.3A communications loss | CM |  |  | 2 |  | 2026-01-21 | 2025-11-27 | 2026-03-17 | Completed | MCM-135582695 | 2026-01-21 | 2026-01-21 |  |  | Scheduled | Tier 2 | wildhare | 2026-03-23 15:00 | 2026-06-22 06:55 |  | 5 | CM |  | Past Compliance | -135
January | PDXW | PDX604 | Hanley Energy | PDX604 AMCOP V6 Upgrade | CM |  |  | 1 |  | 2026-01-21 | 2025-11-27 | 2026-03-17 | Completed | MCM-143357244 | 2026-01-21 | 2026-01-21 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | CM |  | Past Compliance | -135 | MCM Complete
January | PDXW | PDX170 | Hanley Energy | FSB: Upgrade AMCOP Mk2 HMI from v10 to v11 | FSB |  |  | 27 |  | 2026-01-23 06:22 | 2025-11-29 | 2026-03-19 | Completed | MCM-148368893 | 2026-01-23 06:22 | 2026-01-23 06:22 |  |  | Cancelled | Tier 2 | cgiesen | 2026-04-22 07:00 | 2026-05-01 06:55 |  | 4 | FSB |  | Past Compliance | -133 | MCM Cancelled — Resubmit
January | PDXW | PDX59 | Hanley Energy | 6A AMCOP SER PLC/IP WIRING VALIDATION | CM |  |  | 10 |  | 2026-01-26 | 2025-12-02 | 2026-03-22 | Completed | MCM-136161140 | 2026-01-26 | 2026-01-26 |  |  | Scheduled | Tier 2 | baltgarz | 2026-04-14 13:00 | 2026-05-14 01:00 |  | 4 | CM |  | Past Compliance | -130
January | PDXW | PDX109 | Hanley Energy | PDX109 D1A1-D1A6 AMCOP SER PLC-IP and Wiring Validation | PR |  |  | 1 |  | 2026-01-28 | 2025-12-04 | 2026-03-24 | Completed | MCM-143356540 | 2026-01-28 | 2026-01-28 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | PR |  | Past Compliance | -128 | MCM Complete
January | PDXE | PDX2 | Hanley Energy | ER 17 AMCOP SER (PLC) BCD Wiring | CM |  |  | 2 |  | 2026-01-28 | 2025-12-04 | 2026-03-24 | Completed | MCM-138291887 | 2026-01-28 | 2026-01-28 |  |  | Complete | Tier 2 | geocotto | 2026-01-12 14:00 | 2026-02-12 02:00 | Successful | 5 | CM |  | Past Compliance | -128 | MCM Complete
January | PDXW | PDX604 | Hanley Energy | ER1 AMCOP SER PLC-IP and Wiring Validation | PR |  |  | 1 |  | 2026-01-28 | 2025-12-04 | 2026-03-24 | Completed | MCM-143357244 | 2026-01-28 | 2026-01-28 |  |  | Complete | Tier 2 | msmmons | 2026-02-12 08:00 | 2026-03-15 06:59 | Successful | 5 | PR |  | Past Compliance | -128 | MCM Complete
February | PDXE | PDX69 | Hanley Energy | AMCOP Control Power Alarm Verification | CM |  |  | 1 |  | 2026-02-04 | 2025-12-11 | 2026-03-31 | Completed | MCM-142310462 | 2026-02-04 | 2026-02-04 |  |  | Complete | Tier 2 | batrocki | 2026-01-27 08:00 | 2026-02-26 08:00 | Successful | 5 | CM |  | Past Compliance | -121 | MCM Complete

## BACOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
July | PDXW | PDX66 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 01M PM V1.0 | PPM | G.CNTRL.BACOP.01M | 1M | 14 |  | 2021-07-01 | 2021-06-28 | 2021-07-04 | Completed |  | 2021-07-01 | 2021-07-01 | [8 empty] | 4 | SC |  | Past Compliance | -1800
July | PDXW | PDX68 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 01M PM V1.0 | PPM | G.CNTRL.BACOP.01M | 1M | 6 |  | 2021-07-01 | 2021-06-28 | 2021-07-04 | Completed |  | 2021-07-01 | 2021-07-01 | [8 empty] | 4 | SC |  | Past Compliance | -1800
August | PDXW | PDX66 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 01M PM V1.0 | PPM | G.CNTRL.BACOP.01M | 1M | 13 |  | 2021-08-01 | 2021-07-29 | 2021-08-04 | Completed |  | 2021-08-01 | 2021-08-01 | [8 empty] | 4 | SC |  | Past Compliance | -1769
August | PDXW | PDX68 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 01M PM V1.0 | PPM | G.CNTRL.BACOP.01M | 1M | 1 |  | 2021-08-01 | 2021-07-29 | 2021-08-04 | Completed |  | 2021-08-01 | 2021-08-01 | [8 empty] | 4 | SC |  | Past Compliance | -1769
January | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 25 |  | 2023-01-01 | 2022-11-07 | 2023-02-25 | Cancelled |  | 2023-01-01 | 2023-01-01 | [8 empty] | 4 | PM |  | Past Compliance | -1251
April | PDXE | PDX54 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-04-27 | 2023-03-03 | 2023-06-21 | Completed |  | 2023-04-27 | 2023-04-27 | [8 empty] | 4 | PM |  | Past Compliance | -1135
May | PDXW | PDX109 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2023-05-01 | 2023-03-07 | 2023-06-25 | Cancelled |  | 2023-05-01 | 2023-05-01 | [8 empty] | 4 | PM |  | Past Compliance | -1131
May | PDXE | PDX54 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-05-29 | 2023-04-04 | 2023-07-23 | Cancelled |  | 2023-05-29 | 2023-05-29 | [8 empty] | 4 | PM |  | Past Compliance | -1103
September | PDXE | PDX57 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2023-09-01 | 2023-07-08 | 2023-10-26 | Completed |  | 2023-09-01 | 2023-09-01 | [8 empty] | 4 | PM |  | Past Compliance | -1008
September | PDXE | PDX131 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-09-15 | 2023-07-22 | 2023-11-09 | Cancelled |  | 2023-09-15 | 2023-09-15 | [8 empty] | 4 | PM |  | Past Compliance | -994
October | PDXW | PDX110 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-10-03 | 2023-08-09 | 2023-11-27 | Cancelled |  | 2023-10-03 | 2023-10-03 | [8 empty] | 4 | PM |  | Past Compliance | -976
November | PDXW | PDX53 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-11-03 | 2023-09-09 | 2023-12-28 | Completed |  | 2023-11-03 | 2023-11-03 | [8 empty] | 4 | PM |  | Past Compliance | -945
November | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-11-24 | 2023-09-30 | 2024-01-18 | Completed |  | 2023-11-24 | 2023-11-24 | [8 empty] | 4 | PM |  | Past Compliance | -924
December | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2023-12-07 | 2023-10-13 | 2024-01-31 | Completed |  | 2023-12-07 | 2023-12-07 | [8 empty] | 4 | PM |  | Past Compliance | -911
February | PDXE | PDX69 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2024-02-06 | 2023-12-13 | 2024-04-01 | Completed |  | 2024-02-06 | 2024-02-06 | [8 empty] | 4 | PM |  | Past Compliance | -850
April | PDXW | PDX66 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 14 |  | 2024-04-01 | 2024-02-06 | 2024-05-26 | Completed |  | 2024-04-01 | 2024-04-01 | [8 empty] | 4 | PM |  | Past Compliance | -795
April | PDXW | PDX68 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2024-04-01 | 2024-02-06 | 2024-05-26 | Completed |  | 2024-04-01 | 2024-04-01 | [8 empty] | 4 | PM |  | Past Compliance | -795
April | PDXE | PDX54 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2024-04-27 | 2024-03-03 | 2024-06-21 | Completed |  | 2024-04-27 | 2024-04-27 | [8 empty] | 4 | PM |  | Past Compliance | -769
May | PDXW | PDX50 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2024-05-01 | 2024-03-07 | 2024-06-25 | Completed |  | 2024-05-01 | 2024-05-01 | [8 empty] | 4 | PM |  | Past Compliance | -765
May | PDXE | PDX67 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 16 |  | 2024-05-01 | 2024-03-07 | 2024-06-25 | Completed |  | 2024-05-01 | 2024-05-01 | [8 empty] | 4 | PM |  | Past Compliance | -765
June | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 3 |  | 2024-06-01 | 2024-04-07 | 2024-07-26 | Completed |  | 2024-06-01 | 2024-06-01 | [8 empty] | 4 | PM |  | Past Compliance | -734
June | PDXE | PDX63 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 11 |  | 2024-06-12 | 2024-04-18 | 2024-08-06 | Completed |  | 2024-06-12 | 2024-06-12 | [8 empty] | 4 | PM |  | Past Compliance | -723
October | PDXW | PDX64 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 18 |  | 2024-10-04 | 2024-08-10 | 2024-11-28 | Completed |  | 2024-10-04 | 2024-10-04 | [8 empty] | 4 | PM |  | Past Compliance | -609
November | PDXW | PDX62 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 14 |  | 2024-11-28 | 2024-10-04 | 2025-01-22 | Completed |  | 2024-11-28 | 2024-11-28 | [8 empty] | 4 | PM |  | Past Compliance | -554
March | PDXW | PDX59 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2025-03-10 | 2025-01-14 | 2025-05-04 | Cancelled |  | 2025-03-10 | 2025-03-10 | [8 empty] | 4 | PM |  | Past Compliance | -452
May | PDXW | PDX109 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2025-05-01 | 2025-03-07 | 2025-06-25 | Completed |  | 2025-05-01 | 2025-05-01 | [8 empty] | 4 | PM |  | Past Compliance | -400
May | PDXW | PDX59 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 3 |  | 2025-05-05 | 2025-03-11 | 2025-06-29 | Cancelled |  | 2025-05-05 | 2025-05-05 | [8 empty] | 4 | PM |  | Past Compliance | -396
July | PDXE | PDX130 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2025-07-25 | 2025-05-31 | 2025-09-18 | Completed |  | 2025-07-25 | 2025-07-25 | [8 empty] | 4 | PM |  | Past Compliance | -315
July | PDXE | PDX65 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 20 |  | 2025-07-25 | 2025-05-31 | 2025-09-18 | Completed |  | 2025-07-25 | 2025-07-25 | [8 empty] | 4 | PM |  | Past Compliance | -315
August | PDXE | PDX131 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2025-08-01 | 2025-06-07 | 2025-09-25 | Completed |  | 2025-08-01 | 2025-08-01 | [8 empty] | 4 | PM |  | Past Compliance | -308
September | PDXW | PDX56 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 4 |  | 2025-09-25 | 2025-08-01 | 2025-11-19 | Completed |  | 2025-09-25 | 2025-09-25 | [8 empty] | 4 | PM |  | Past Compliance | -253
September | PDXW | PDX59 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 6 |  | 2025-09-25 | 2025-08-01 | 2025-11-19 | Completed |  | 2025-09-25 | 2025-09-25 | [8 empty] | 4 | PM |  | Past Compliance | -253
November | PDXW | PDX110 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2025-11-21 | 2025-09-27 | 2026-01-15 | Completed |  | 2025-11-21 | 2025-11-21 | [8 empty] | 4 | PM |  | Past Compliance | -196
January | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 5 |  | 2026-01-01 | 2025-11-07 | 2026-02-25 | Cancelled |  | 2026-01-01 | 2026-01-01 | [8 empty] | 4 | PM |  | Past Compliance | -155
January | PDXW | PDX66 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 6 |  | 2026-01-05 | 2025-11-11 | 2026-03-01 | Cancelled | MCM-136563989 | 2026-01-05 | 2026-01-05 |  |  | Complete | Tier 2 | camrenk | 2026-01-20 14:00 | 2026-02-07 07:30 | Successful | 4 | PM |  | Past Compliance | -151 | MCM Complete
June | PDXW | PDX112 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-06-04 | 2026-04-10 | 2026-07-29 | Open | MCM-144338241 | 2026-06-04 | 2026-06-04 |  |  | Scheduled | Tier 3 | aminpe | 2026-06-08 07:00 | 2026-07-09 06:59 |  | 4 | PM |  | Within Compliance | -1 | MCM Scheduled
June | PDXW | PDX111 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-06-11 | 2026-04-17 | 2026-08-05 | Open | MCM-136066518 | 2026-06-11 | 2026-06-11 |  |  | Scheduled | Tier 2 | aminpe | 2026-06-07 13:00 | 2026-07-08 06:59 |  | 4 | PM |  | Within Compliance | 6 | MCM Scheduled
July | PDXE | PDX69 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-07-25 | 2026-05-31 | 2026-09-18 | Open | MCM-151521619 | 2026-07-25 | 2026-07-25 |  |  | Scheduled | Tier 3 | lkgray | 2026-07-01 07:00 | 2026-07-31 06:55 |  | 4 | PM |  | Within Compliance | 50 | MCM Scheduled
August | PDXE | PDX132 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open | MCM-147982640 | 2026-08-15 | 2026-08-15 |  |  | Draft | Tier 3 | gabeher | 2026-07-27 13:00 | 2026-08-26 06:55 |  | 4 | PM |  | Outside Compliance | 71 | MCM in Draft
August | PDXE | PDX54 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open | MCM-151535397 | 2026-08-15 | 2026-08-15 |  |  | Draft | Tier 3 | zferanto | 2026-07-01 07:00 | 2026-07-31 06:55 |  | 4 | PM |  | Outside Compliance | 71 | MCM in Draft
August | PDXE | PDX57 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 12 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open | MCM-150275221 | 2026-08-15 | 2026-08-15 |  |  | Scheduled | Tier 2 | livintra | 2026-06-15 13:00 | 2026-07-16 01:00 |  | 4 | PM |  | Outside Compliance | 71 | MCM Scheduled
August | PDXE | PDX60 | Hanley Energy | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 11 |  | 2026-08-15 | 2026-06-21 | 2026-10-09 | Open | MCM-150274397 | 2026-08-15 | 2026-08-15 |  |  | Scheduled | Tier 2 | livintra | 2026-06-15 13:00 | 2026-07-16 01:00 |  | 4 | PM |  | Outside Compliance | 71 | MCM Scheduled

## BACOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXW | PDX112 | Hanley Energy | MCM Creation: MCM-99996464 : PDX112 BACOP 12M PM Pending Approval | FPM |  |  | 19 |  | 2024-04-04 | 2024-02-09 | 2024-05-29 | Completed |  | 2024-04-04 | 2024-04-04 | [8 empty] | 5 | FPM |  | Past Compliance | -792
April | PDXE | PDX65 | Hanley Energy | BACOP 4B troubleshooting | CM |  |  | 1 |  | 2024-04-10 | 2024-02-15 | 2024-06-04 | Completed |  | 2024-04-10 | 2024-04-10 | [8 empty] | 5 | CM |  | Past Compliance | -786
April | PDXW | PDX110 | Hanley Energy | BACOP 12M MCM Update | MEC |  |  | 6 |  | 2024-04-16 12:43 | 2024-02-21 | 2024-06-10 | Completed |  | 2024-04-16 12:43 | 2024-04-16 12:43 | [8 empty] | 5 | MEC |  | Past Compliance | -779
April | PDXE | PDX69 | Hanley Energy | BACOP 2.5A Stratix Switch Configuration Fault | PR |  |  | 1 |  | 2024-04-22 | 2024-02-27 | 2024-06-16 | Completed |  | 2024-04-22 | 2024-04-22 | [8 empty] | 5 | PR |  | Past Compliance | -774
May | PDXE | PDX132 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2024-05-07 | 2024-03-13 | 2024-07-01 | Completed |  | 2024-05-07 | 2024-05-07 | [8 empty] | 3 | SRVY |  | Past Compliance | -759
May | PDXE | PDX69 | Hanley Energy | FRB: Upgrade FUJI SMBE BACOP to v4.1 | FRB |  |  | 28 |  | 2024-05-15 | 2024-03-21 | 2024-07-09 | Completed |  | 2024-05-15 | 2024-05-15 | [8 empty] | 5 | FRB |  | Past Compliance | -751
May | PDXW | PDX109 | Hanley Energy | BACOP 1.1A DC UPS Issue | REG-FOLL |  |  | 1 |  | 2024-05-23 | 2024-03-29 | 2024-07-17 | Completed |  | 2024-05-23 | 2024-05-23 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -743
June | PDXE | PDX69 | Hanley Energy | BACOP 2.5A Power Cycle | CM |  |  | 1 |  | 2024-06-01 | 2024-04-07 | 2024-07-26 | Completed |  | 2024-06-01 | 2024-06-01 | [8 empty] | 5 | CM |  | Past Compliance | -734
June | PDXW | PDX110 | Hanley Energy | BACOP 12M MCM rework. | MEC |  |  | 5 |  | 2024-06-03 11:03 | 2024-04-09 | 2024-07-28 | Completed |  | 2024-06-03 11:03 | 2024-06-03 11:03 | [8 empty] | 5 | MEC |  | Past Compliance | -731
June | PDXE | PDX132 | Hanley Energy | BACOP 2.3A Power Cycle | CM |  |  | 2 |  | 2024-06-04 | 2024-04-10 | 2024-07-29 | Completed |  | 2024-06-04 | 2024-06-04 | [8 empty] | 5 | CM |  | Past Compliance | -731
June | PDXE | PDX131 | Hanley Energy | PDX131 Bacop troubleshooting and repair. | CM |  |  | 1 |  | 2024-06-11 | 2024-04-17 | 2024-08-05 | Completed |  | 2024-06-11 | 2024-06-11 | [8 empty] | 5 | CM |  | Past Compliance | -724
June | PDXE | PDX60 | Hanley Energy | PDX060 BACOP HUPP 4C, 5C/HPP 1A, 2A, 5A, 7A Circuit Terminations | PR |  |  | 1 |  | 2024-06-17 | 2024-04-23 | 2024-08-11 | Completed |  | 2024-06-17 | 2024-06-17 | [8 empty] | 4 | PR |  | Past Compliance | -718
June | PDXE | PDX67 | Hanley Energy | PDX 67 / BACOP: 30A Tap Box Removal & Shunt Trip Install | PR |  |  | 1 |  | 2024-06-17 | 2024-04-23 | 2024-08-11 | Completed |  | 2024-06-17 | 2024-06-17 | [8 empty] | 5 | PR |  | Past Compliance | -718
July | PDXE | PDX69 | Hanley Energy | BACOP Power Cycle | CM |  |  | 4 |  | 2024-07-02 | 2024-05-08 | 2024-08-26 | Completed |  | 2024-07-02 | 2024-07-02 | [8 empty] | 5 | CM |  | Past Compliance | -703
July | PDXE | PDX131 | Hanley Energy | BACOP Power Cycle August | CM |  |  | 2 |  | 2024-07-03 | 2024-05-09 | 2024-08-27 | Completed |  | 2024-07-03 | 2024-07-03 | [8 empty] | 5 | CM |  | Past Compliance | -702
July | PDXW | PDX62 | Hanley Energy | BACOP 36M maintenance | FPM |  |  | 1 |  | 2024-07-17 | 2024-05-23 | 2024-09-10 | Completed |  | 2024-07-17 | 2024-07-17 | [8 empty] | 5 | FPM |  | Past Compliance | -688
July | PDXW | PDX64 | Hanley Energy | BACOP 5B 3YR PM | FPM |  |  | 1 |  | 2024-07-22 | 2024-05-28 | 2024-09-15 | Completed |  | 2024-07-22 | 2024-07-22 | [8 empty] | 5 | FPM |  | Past Compliance | -683
July | PDXW | PDX56 | Hanley Energy | BACOP 7A PDP Main Meter Replacement | CM |  |  | 1 |  | 2024-07-31 | 2024-06-06 | 2024-09-24 | Completed |  | 2024-07-31 | 2024-07-31 | [8 empty] | 5 | CM |  | Past Compliance | -674
August | PDXE | PDX131 | Hanley Energy | BACOP Power Cycle Sepember | CM |  |  | 2 |  | 2024-08-08 | 2024-06-14 | 2024-10-02 | Completed |  | 2024-08-08 | 2024-08-08 | [8 empty] | 5 | CM |  | Past Compliance | -666
August | PDXE | PDX69 | Hanley Energy | BACOP 2.5A | PR |  |  | 1 |  | 2024-08-08 | 2024-06-14 | 2024-10-02 | Completed |  | 2024-08-08 | 2024-08-08 | [8 empty] | 5 | PR |  | Past Compliance | -666
August | PDXW | PDX112 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | MEC |  |  | 7 |  | 2024-08-09 18:14 | 2024-06-15 | 2024-10-03 | Completed |  | 2024-08-09 18:14 | 2024-08-09 18:14 | [8 empty] | 5 | MEC |  | Past Compliance | -664
August | PDXE | PDX194 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 9 |  | 2024-08-10 | 2024-06-16 | 2024-10-04 | Completed |  | 2024-08-10 | 2024-08-10 | [8 empty] | 3 | SRVY |  | Past Compliance | -664
August | PDXE | PDX130 | Hanley Energy | BACOP 12M SOP Updates | PR |  |  | 25 |  | 2024-08-15 | 2024-06-21 | 2024-10-09 | Completed |  | 2024-08-15 | 2024-08-15 | [8 empty] | 5 | PR |  | Past Compliance | -659
August | PDXW | PDX111 | Hanley Energy | BACOP 2.2A troubleshooting | CM |  |  | 1 |  | 2024-08-20 | 2024-06-26 | 2024-10-14 | Completed |  | 2024-08-20 | 2024-08-20 | [8 empty] | 5 | CM |  | Past Compliance | -654
August | PDXE | PDX54 | Hanley Energy | 3B BACOP Integration RRPR Audit | PR |  |  | 3 |  | 2024-08-22 | 2024-06-28 | 2024-10-16 | Completed |  | 2024-08-22 | 2024-08-22 | [8 empty] | 5 | PR |  | Past Compliance | -652
September | PDXE | PDX131 | Hanley Energy | Bacop Power Cycle October | REG-FOLL |  |  | 1 |  | 2024-09-01 | 2024-07-08 | 2024-10-26 | Completed |  | 2024-09-01 | 2024-09-01 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -642
September | PDXW | PDX62 | Hanley Energy | BACOP 5A Manual Inhibit EPMS Fault | CM |  |  | 1 |  | 2024-09-02 | 2024-07-09 | 2024-10-27 | Completed |  | 2024-09-02 | 2024-09-02 | [8 empty] | 5 | CM |  | Past Compliance | -641
September | PDXW | PDX110 | Hanley Energy | PDX110 BACOP/PDC Troubleshooting and Repair | REG-FOLL |  |  | 6 |  | 2024-09-05 | 2024-07-12 | 2024-10-30 | Completed |  | 2024-09-05 | 2024-09-05 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -638
September | PDXE | PDX194 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-09-05 | 2024-07-12 | 2024-10-30 | Completed |  | 2024-09-05 | 2024-09-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -638
September | PDXE | PDX63 | Hanley Energy | BACOP 9B Alarm | CM |  |  | 2 |  | 2024-09-06 | 2024-07-13 | 2024-10-31 | Completed |  | 2024-09-06 | 2024-09-06 | [8 empty] | 5 | CM |  | Past Compliance | -637
September | PDXW | PDX111 | Hanley Energy | BACOP 2.6B PLC Troubleshooting | CM |  |  | 2 |  | 2024-09-08 | 2024-07-15 | 2024-11-02 | Completed |  | 2024-09-08 | 2024-09-08 | [8 empty] | 5 | CM |  | Past Compliance | -635
September | PDXW | PDX64 | Hanley Energy | BACOP 7A Alarm | CM |  |  | 2 |  | 2024-09-10 | 2024-07-17 | 2024-11-04 | Completed |  | 2024-09-10 | 2024-09-10 | [8 empty] | 5 | CM |  | Past Compliance | -633
September | PDXE | PDX69 | Hanley Energy | BACOP 1.2B - Baud Rate Setting Update | CM |  |  | 15 |  | 2024-09-16 | 2024-07-23 | 2024-11-10 | Completed |  | 2024-09-16 | 2024-09-16 | [8 empty] | 5 | CM |  | Past Compliance | -627
October | PDXE | PDX194 | Hanley Energy | FRB: Identify BACOPs with Janitza UMG 604-PRO meters not separately in EAM | SRVY |  |  | 13 |  | 2024-10-01 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 | 2024-10-01 | [8 empty] | 3 | SRVY |  | Past Compliance | -612
October | PDXE | PDX194 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2024-10-01 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 | 2024-10-01 | [8 empty] | 3 | SRVY |  | Past Compliance | -612
October | PDXE | PDX131 | Hanley Energy | BACOP Powercycle December | CM |  |  | 1 |  | 2024-10-16 | 2024-08-22 | 2024-12-10 | Completed |  | 2024-10-16 | 2024-10-16 | [8 empty] | 5 | CM |  | Past Compliance | -597
October | PDXE | PDX195 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2024-10-16 | 2024-08-22 | 2024-12-10 | Completed |  | 2024-10-16 | 2024-10-16 | [8 empty] | 3 | SRVY |  | Past Compliance | -597
October | PDXE | PDX60 | Hanley Energy | BACOP 4B Conrol Power Supply 2 Lost | CM |  |  | 3 |  | 2024-10-23 | 2024-08-29 | 2024-12-17 | Completed |  | 2024-10-23 | 2024-10-23 | [8 empty] | 4 | CM |  | Past Compliance | -590
October | PDXE | PDX130 | Hanley Energy | PDX130 BACOP 2.5A HMI Connection to PLC Fault | CM |  |  | 1 |  | 2024-10-26 | 2024-09-01 | 2024-12-20 | Completed |  | 2024-10-26 | 2024-10-26 | [8 empty] | 5 | CM |  | Past Compliance | -587
October | PDXW | PDX62 | Hanley Energy | BACOP 36M PM | FPM |  |  | 5 |  | 2024-10-28 | 2024-09-03 | 2024-12-22 | Completed |  | 2024-10-28 | 2024-10-28 | [8 empty] | 5 | FPM |  | Past Compliance | -585
November | PDXW | PDX62 | Hanley Energy | FRB: Identify Hanley BACOPs with Cyber Sciences SER-3200 SERs | SRVY |  |  | 2 |  | 2024-11-05 | 2024-09-11 | 2024-12-30 | Completed |  | 2024-11-05 | 2024-11-05 | [8 empty] | 5 | SRVY |  | Past Compliance | -577
November | PDXW | PDX62 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 2 |  | 2024-11-05 | 2024-09-11 | 2024-12-30 | Completed |  | 2024-11-05 | 2024-11-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -577
November | PDXE | PDX195 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-11-09 | 2024-09-15 | 2025-01-03 | Completed |  | 2024-11-09 | 2024-11-09 | [8 empty] | 3 | SRVY |  | Past Compliance | -573
November | PDXE | PDX67 | Hanley Energy | PDX67 BACOP & Tapbox Programming/EPMS Integration ABB | CM |  |  | 8 |  | 2024-11-09 | 2024-09-15 | 2025-01-03 | Completed |  | 2024-11-09 | 2024-11-09 | [8 empty] | 5 | CM |  | Past Compliance | -573
November | PDXE | PDX194 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-11-13 | 2024-09-19 | 2025-01-07 | Completed |  | 2024-11-13 | 2024-11-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -569
November | PDXW | PDX64 | Hanley Energy | Follow up required for the [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | FPM |  |  | 1 |  | 2024-11-13 | 2024-09-19 | 2025-01-07 | Completed |  | 2024-11-13 | 2024-11-13 | [8 empty] | 4 | FPM |  | Past Compliance | -569
November | PDXE | PDX69 | Hanley Energy | BACOP 2.2A SER Fault | MEC |  |  | 1 |  | 2024-11-23 23:44 | 2024-09-29 | 2025-01-17 | Completed |  | 2024-11-23 23:44 | 2024-11-23 23:44 | [8 empty] | 5 | MEC |  | Past Compliance | -558
December | PDXE | PDX195 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-12-20 | 2024-10-26 | 2025-02-13 | Completed |  | 2024-12-20 | 2024-12-20 | [8 empty] | 3 | SRVY |  | Past Compliance | -532
December | PDXE | PDX131 | Hanley Energy | PDX131 BACOP Power Cycle March | CM |  |  | 1 |  | 2024-12-25 | 2024-10-31 | 2025-02-18 | Completed |  | 2024-12-25 | 2024-12-25 | [8 empty] | 5 | CM |  | Past Compliance | -527
December | PDXE | PDX194 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2024-12-30 09:13 | 2024-11-05 | 2025-02-23 | Completed |  | 2024-12-30 09:13 | 2024-12-30 09:13 | [8 empty] | 3 | SRVY |  | Past Compliance | -521
January | PDXW | PDX170 | Hanley Energy | Investigate BACOP alarm | PR |  |  | 2 |  | 2025-01-01 | 2024-11-07 | 2025-02-25 | Completed |  | 2025-01-01 | 2025-01-01 | [8 empty] | 5 | PR |  | Past Compliance | -520
January | PDXW | PDX64 | Hanley Energy | BACOPs in ER 3 & 4 in alarm | CM |  |  | 4 |  | 2025-01-01 | 2024-11-07 | 2025-02-25 | Completed |  | 2025-01-01 | 2025-01-01 | [8 empty] | 5 | CM |  | Past Compliance | -520
January | PDXW | PDX109 | Hanley Energy | BACOP 36M SOP Creation | REG-FOLL |  |  | 1 |  | 2025-01-06 | 2024-11-12 | 2025-03-02 | Completed |  | 2025-01-06 | 2025-01-06 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -515
January | PDXW | PDX62 | Hanley Energy | Troubleshoot BACOP 5A Manual Inhibit Switch | CM |  |  | 1 |  | 2025-01-09 | 2024-11-15 | 2025-03-05 | Completed |  | 2025-01-09 | 2025-01-09 | [8 empty] | 5 | CM |  | Past Compliance | -512
January | PDXE | PDX195 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-01-17 | 2024-11-23 | 2025-03-13 | Completed |  | 2025-01-17 | 2025-01-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -504
January | PDXW | PDX64 | Hanley Energy | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 40 |  | 2025-01-23 12:06 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 12:06 | 2025-01-23 12:06 | [8 empty] | 5 | FSB |  | Past Compliance | -497
January | PDXE | PDX65 | Hanley Energy | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 42 |  | 2025-01-23 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 | 2025-01-23 | [8 empty] | 5 | FSB |  | Past Compliance | -498
January | PDXW | PDX66 | Hanley Energy | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 36 |  | 2025-01-23 12:07 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 12:07 | 2025-01-23 12:07 | [8 empty] | 5 | FSB |  | Past Compliance | -497
January | PDXE | PDX67 | Hanley Energy | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 38 |  | 2025-01-23 12:08 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 12:08 | 2025-01-23 12:08 | [8 empty] | 5 | FSB |  | Past Compliance | -497
January | PDXE | PDX131 | Hanley Energy | BACOP Health Alarm Troubleshooting | PR |  |  | 1 |  | 2025-01-25 | 2024-12-01 | 2025-03-21 | Completed |  | 2025-01-25 | 2025-01-25 | [8 empty] | 5 | PR |  | Past Compliance | -496
January | PDXE | PDX69 | Hanley Energy | D1E6_BACOP1-6B_SER | CM |  |  | 1 |  | 2025-01-25 | 2024-12-01 | 2025-03-21 | Completed |  | 2025-01-25 | 2025-01-25 | [8 empty] | 5 | CM |  | Past Compliance | -496
January | PDXE | PDX130 | Hanley Energy | PDX130/BACOP 1.5B / Troubleshoot Repair | CM |  |  | 1 |  | 2025-01-31 | 2024-12-07 | 2025-03-27 | Completed |  | 2025-01-31 | 2025-01-31 | [8 empty] | 5 | CM |  | Past Compliance | -490
February | PDXE | PDX132 | Hanley Energy | BACOP 1.5B Stratix Switch Troubleshooting | CM |  |  | 2 |  | 2025-02-05 | 2024-12-12 | 2025-04-01 | Completed |  | 2025-02-05 | 2025-02-05 | [8 empty] | 5 | CM |  | Past Compliance | -485
February | PDXE | PDX195 | Hanley Energy | FRB: Identify Hanley BACOPs with Cyber Sciences SER-3200 SERs | SRVY |  |  | 43 |  | 2025-02-24 | 2024-12-31 | 2025-04-20 | Completed |  | 2025-02-24 | 2025-02-24 | [8 empty] | 5 | SRVY |  | Past Compliance | -466
February | PDXE | PDX195 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2025-02-24 | 2024-12-31 | 2025-04-20 | Completed |  | 2025-02-24 | 2025-02-24 | [8 empty] | 3 | SRVY |  | Past Compliance | -466
March | PDXE | PDX195 | Hanley Energy | FRB: Upgrade all BACOP Janitza UMG 604-PRO meters to firmware v5.026 | FRB |  |  | 9 |  | 2025-03-06 14:25 | 2025-01-10 | 2025-04-30 | Completed |  | 2025-03-06 14:25 | 2025-03-06 14:25 | [8 empty] | 3 | FRB |  | Past Compliance | -455
March | PDXW | PDX62 | Hanley Energy | Troubleshoot and Remediate BACOP 2B | CM |  |  | 2 |  | 2025-03-06 | 2025-01-10 | 2025-04-30 | Completed |  | 2025-03-06 | 2025-03-06 | [8 empty] | 5 | CM |  | Past Compliance | -456
March | PDXE | PDX54 | Hanley Energy | BACOP Multiple LUs | PR |  |  | 1 |  | 2025-03-08 | 2025-01-12 | 2025-05-02 | Completed |  | 2025-03-08 | 2025-03-08 | [8 empty] | 5 | PR |  | Past Compliance | -454
March | PDXE | PDX67 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 2 |  | 2025-03-11 | 2025-01-15 | 2025-05-05 | Completed |  | 2025-03-11 | 2025-03-11 | [8 empty] | 3 | SRVY |  | Past Compliance | -451
March | PDXE | PDX67 | Hanley Energy | FRB: Upgrade Hanley BACOP to v4.1 | FRB |  |  | 3 |  | 2025-03-11 | 2025-01-15 | 2025-05-05 | Completed |  | 2025-03-11 | 2025-03-11 | [8 empty] | 5 | FRB |  | Past Compliance | -451
March | PDXE | PDX133 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2025-03-12 | 2025-01-16 | 2025-05-06 | Completed |  | 2025-03-12 | 2025-03-12 | [8 empty] | 3 | SRVY |  | Past Compliance | -450
March | PDXE | PDX196 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 3 |  | 2025-03-21 | 2025-01-25 | 2025-05-15 | Completed |  | 2025-03-21 | 2025-03-21 | [8 empty] | 5 | SRVY |  | Past Compliance | -441
March | PDXW | PDX56 | Hanley Energy | PDX56 BACOP 36M Preventative Maintenance | PR |  |  | 4 |  | 2025-03-24 | 2025-01-28 | 2025-05-18 | Completed |  | 2025-03-24 | 2025-03-24 | [8 empty] | 3 | PR |  | Past Compliance | -438
March | PDXW | PDX64 | Hanley Energy | FRB: Upgrade Hanley BACOP to v4.1 | FRB |  |  | 3 |  | 2025-03-25 | 2025-01-29 | 2025-05-19 | Completed |  | 2025-03-25 | 2025-03-25 | [8 empty] | 5 | FRB |  | Past Compliance | -437
March | PDXE | PDX69 | Hanley Energy | BACOP 2.4A Power Cycle | CM |  |  | 1 |  | 2025-03-25 | 2025-01-29 | 2025-05-19 | Completed |  | 2025-03-25 | 2025-03-25 | [8 empty] | 5 | CM |  | Past Compliance | -437
March | PDXW | PDX111 | Hanley Energy | PDX111 - Multiple BACOP Health Alarms | CM |  |  | 1 |  | 2025-03-30 | 2025-02-03 | 2025-05-24 | Completed |  | 2025-03-30 | 2025-03-30 | [8 empty] | 5 | CM |  | Past Compliance | -432
March | PDXE | PDX60 | Hanley Energy | PDX60 BACOP Shunt Trip/CT Install | PR |  |  | 1 |  | 2025-03-31 | 2025-02-04 | 2025-05-25 | Completed |  | 2025-03-31 | 2025-03-31 | [8 empty] | 5 | PR |  | Past Compliance | -431
April | PDXE | PDX133 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2025-04-01 | 2025-02-05 | 2025-05-26 | Completed |  | 2025-04-01 | 2025-04-01 | [8 empty] | 3 | SRVY |  | Past Compliance | -430
April | PDXE | PDX63 | Hanley Energy | BACOP 9A Health in alarm | CM |  |  | 1 |  | 2025-04-05 | 2025-02-09 | 2025-05-30 | Completed |  | 2025-04-05 | 2025-04-05 | [8 empty] | 5 | CM |  | Past Compliance | -426
April | PDXE | PDX69 | Hanley Energy | PDX69 BACOP 1.6B STRATIX SWITCH CONFIG FAULT | CM |  |  | 1 |  | 2025-04-05 | 2025-02-09 | 2025-05-30 | Completed |  | 2025-04-05 | 2025-04-05 | [8 empty] | 5 | CM |  | Past Compliance | -426
April | PDXE | PDX196 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2025-04-08 | 2025-02-12 | 2025-06-02 | Completed |  | 2025-04-08 | 2025-04-08 | [8 empty] | 5 | SRVY |  | Past Compliance | -423
April | PDXE | PDX60 | Hanley Energy | PDX60 BACOP Shunt Trip/CT Install | PR |  |  | 1 |  | 2025-04-09 | 2025-02-13 | 2025-06-03 | Completed |  | 2025-04-09 | 2025-04-09 | [8 empty] | 5 | PR |  | Past Compliance | -422
April | PDXW | PDX171 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-04-14 | 2025-02-18 | 2025-06-08 | Completed |  | 2025-04-14 | 2025-04-14 | [8 empty] | 3 | SRVY |  | Past Compliance | -417
April | PDXE | PDX132 | Hanley Energy | BACOP 1.5B Stratix Config Error | BRKD |  |  | 1 |  | 2025-04-28 | 2025-03-04 | 2025-06-22 | Completed |  | 2025-04-28 | 2025-04-28 | [8 empty] | 5 | BRKD |  | Past Compliance | -403
April | PDXW | PDX66 | Hanley Energy | PDX66 BACOP 3A Caution Alarm | CM |  |  | 1 |  | 2025-04-29 | 2025-03-05 | 2025-06-23 | Completed |  | 2025-04-29 | 2025-04-29 | [8 empty] | 5 | CM |  | Past Compliance | -402
May | PDXE | PDX196 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2025-05-05 | 2025-03-11 | 2025-06-29 | Completed |  | 2025-05-05 | 2025-05-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -396
May | PDXE | PDX63 | Hanley Energy | Bacop 10A Stratix Switch Errors | CM |  |  | 1 |  | 2025-05-07 | 2025-03-13 | 2025-07-01 | Completed |  | 2025-05-07 | 2025-05-07 | [8 empty] | 5 | CM |  | Past Compliance | -394
May | PDXE | PDX131 | Hanley Energy | BACOP Power Cycle July | CM |  |  | 3 |  | 2025-05-08 | 2025-03-14 | 2025-07-02 | Completed |  | 2025-05-08 | 2025-05-08 | [8 empty] | 5 | CM |  | Past Compliance | -393
May | PDXW | PDX110 | Hanley Energy | PDX110 BACOP 1.2B and 2.6A Battery Charger Repair | PR |  |  | 1 |  | 2025-05-12 | 2025-03-18 | 2025-07-06 | Completed |  | 2025-05-12 | 2025-05-12 | [8 empty] | 5 | PR |  | Past Compliance | -389
May | PDXW | PDX111 | Hanley Energy | BACOP Shunt Trip Response | PR |  |  | 1 |  | 2025-05-15 | 2025-03-21 | 2025-07-09 | Completed |  | 2025-05-15 | 2025-05-15 | [8 empty] | 5 | PR |  | Past Compliance | -386
May | PDXW | PDX171 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2025-05-15 | 2025-03-21 | 2025-07-09 | Completed |  | 2025-05-15 | 2025-05-15 | [8 empty] | 5 | SRVY |  | Past Compliance | -386
May | PDXE | PDX133 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 4 |  | 2025-05-19 | 2025-03-25 | 2025-07-13 | Completed |  | 2025-05-19 | 2025-05-19 | [8 empty] | 3 | SRVY |  | Past Compliance | -382
June | PDXE | PDX132 | Hanley Energy | BACOP 1.5B Stratix Switch Error | CM |  |  | 1 |  | 2025-06-02 | 2025-04-08 | 2025-07-27 | Completed |  | 2025-06-02 | 2025-06-02 | [8 empty] | 5 | CM |  | Past Compliance | -368
June | PDXW | PDX109 | Hanley Energy | BACOP 1.3B Investigation. | REG-FOLL |  |  | 1 |  | 2025-06-05 | 2025-04-11 | 2025-07-30 | Completed |  | 2025-06-05 | 2025-06-05 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -365
June | PDXW | PDX68 | Hanley Energy | BACOP Communication Alarms | CM |  |  | 5 |  | 2025-06-05 | 2025-04-11 | 2025-07-30 | Completed |  | 2025-06-05 | 2025-06-05 | [8 empty] | 5 | CM |  | Past Compliance | -365
June | PDXE | PDX196 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2025-06-09 | 2025-04-15 | 2025-08-03 | Completed |  | 2025-06-09 | 2025-06-09 | [8 empty] | 5 | SRVY |  | Past Compliance | -361
June | PDXE | PDX133 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-06-10 | 2025-04-16 | 2025-08-04 | Completed |  | 2025-06-10 | 2025-06-10 | [8 empty] | 3 | SRVY |  | Past Compliance | -360
June | PDXW | PDX109 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX110 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX111 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | MEC |  |  | 25 |  | 2025-06-13 10:16 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 10:16 | 2025-06-13 10:16 | [8 empty] | 3 | MEC |  | Past Compliance | -356
June | PDXW | PDX112 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX130 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX131 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 10:20 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 10:20 | 2025-06-13 10:20 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXE | PDX132 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX171 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 27 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX194 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 11:10 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:10 | 2025-06-13 11:10 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXE | PDX195 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX50 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 3 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX53 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 2 |  | 2025-06-13 11:18 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:18 | 2025-06-13 11:18 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXE | PDX54 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 3 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX56 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 5 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX57 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 3 |  | 2025-06-13 11:21 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:21 | 2025-06-13 11:21 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXW | PDX59 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 7 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX60 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 6 |  | 2025-06-13 11:30 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:30 | 2025-06-13 11:30 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXW | PDX62 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 15 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX63 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 12 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX64 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 21 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX65 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 21 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX66 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 15 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX67 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 18 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX68 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXE | PDX69 | Hanley Energy | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 26 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXW | PDX171 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2025-06-17 11:29 | 2025-04-23 | 2025-08-11 | Completed |  | 2025-06-17 11:29 | 2025-06-17 11:29 | [8 empty] | 3 | SRVY |  | Past Compliance | -352
June | PDXW | PDX62 | Hanley Energy | Troubleshoot and Remediate BACOP's Date/Time | CM |  |  | 2 |  | 2025-06-19 | 2025-04-25 | 2025-08-13 | Completed |  | 2025-06-19 | 2025-06-19 | [8 empty] | 5 | CM |  | Past Compliance | -351
July | PDXE | PDX130 | Hanley Energy | BACOP2_1B_SER - S_BACOP CAUTION ALARM | CM |  |  | 1 |  | 2025-07-03 | 2025-05-09 | 2025-08-27 | Completed |  | 2025-07-03 | 2025-07-03 | [8 empty] | 5 | CM |  | Past Compliance | -337
July | PDXE | PDX133 | Hanley Energy | FRB: Upgrade Cyber Sciences SER-3200 in IEM BACOP to v2.23 | FRB |  |  | 32 |  | 2025-07-06 06:10 | 2025-05-12 | 2025-08-30 | Completed |  | 2025-07-06 06:10 | 2025-07-06 06:10 | [8 empty] | 5 | FRB |  | Past Compliance | -334
July | PDXW | PDX64 | Hanley Energy | BACOP 12M PM | CM |  |  | 1 |  | 2025-07-10 | 2025-05-16 | 2025-09-03 | Completed |  | 2025-07-10 | 2025-07-10 | [8 empty] | 5 | CM |  | Past Compliance | -330
July | PDXE | PDX69 | Hanley Energy | Power Cycle BACOP 1.6B | CM |  |  | 1 |  | 2025-07-18 | 2025-05-24 | 2025-09-11 | Completed |  | 2025-07-18 | 2025-07-18 | [8 empty] | 5 | CM |  | Past Compliance | -322
July | PDXE | PDX54 | Hanley Energy | BACOP RRPR Audits | PR |  |  | 1 |  | 2025-07-31 | 2025-06-06 | 2025-09-24 | Completed |  | 2025-07-31 | 2025-07-31 | [8 empty] | 5 | PR |  | Past Compliance | -309
August | PDXE | PDX63 | Hanley Energy | FRB: Upgrade Cyber Sciences SER-3200 in Hanley BACOP to v2.23 | FRB |  |  | 42 |  | 2025-08-03 15:01 | 2025-06-09 | 2025-09-27 | Open |  | 2025-08-03 15:01 | 2025-08-03 15:01 | [8 empty] | 5 | FRB |  | Past Compliance | -305 | MCM OVERDUE
August | PDXW | PDX62 | Hanley Energy | BACOP 12M PM | FPM |  |  | 1 |  | 2025-08-07 | 2025-06-13 | 2025-10-01 | Completed |  | 2025-08-07 | 2025-08-07 | [8 empty] | 5 | FPM |  | Past Compliance | -302
August | PDXW | PDX64 | Hanley Energy | BACOP 12M PM | PR |  |  | 1 |  | 2025-08-07 | 2025-06-13 | 2025-10-01 | Completed |  | 2025-08-07 | 2025-08-07 | [8 empty] | 5 | PR |  | Past Compliance | -302
August | PDXW | PDX109 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 45 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXW | PDX110 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 22:52 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:52 | 2025-08-11 22:52 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX111 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXW | PDX112 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 23 |  | 2025-08-11 22:53 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:53 | 2025-08-11 22:53 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX130 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXE | PDX132 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 51 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXE | PDX133 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 55 |  | 2025-08-11 22:55 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:55 | 2025-08-11 22:55 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX171 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 16 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXE | PDX194 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXE | PDX195 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 20:59 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 20:59 | 2025-08-11 20:59 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX196 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 50 |  | 2025-08-11 22:58 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:58 | 2025-08-11 22:58 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX54 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 16 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXW | PDX56 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 17 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXE | PDX57 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 15 |  | 2025-08-11 19:59 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 19:59 | 2025-08-11 19:59 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX59 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 19 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXE | PDX60 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 17 |  | 2025-08-11 20:59 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 20:59 | 2025-08-11 20:59 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX62 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 33 |  | 2025-08-11 21:00 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 21:00 | 2025-08-11 21:00 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX64 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 42 |  | 2025-08-11 22:00 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:00 | 2025-08-11 22:00 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX65 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 42 |  | 2025-08-11 21:01 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 21:01 | 2025-08-11 21:01 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXW | PDX66 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 36 |  | 2025-08-11 20:00 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 20:00 | 2025-08-11 20:00 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX67 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 37 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXW | PDX68 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 51 |  | 2025-08-11 21:01 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 21:01 | 2025-08-11 21:01 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX69 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 51 |  | 2025-08-11 20:01 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 20:01 | 2025-08-11 20:01 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXE | PDX194 | Hanley Energy | BACOP 1.3B Stratix Switch Configuration Fault | CM |  |  | 1 |  | 2025-08-13 | 2025-06-19 | 2025-10-07 | Completed |  | 2025-08-13 | 2025-08-13 | [8 empty] | 5 | CM |  | Past Compliance | -296
August | PDXE | PDX133 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2025-08-18 | 2025-06-24 | 2025-10-12 | Completed |  | 2025-08-18 | 2025-08-18 | [8 empty] | 5 | SRVY |  | Past Compliance | -291
August | PDXE | PDX196 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 13 |  | 2025-08-26 22:47 | 2025-07-02 | 2025-10-20 | Completed |  | 2025-08-26 22:47 | 2025-08-26 22:47 | [8 empty] | 3 | SRVY |  | Past Compliance | -282
September | PDXE | PDX196 | Hanley Energy | FRB: Upgrade Cyber Sciences SER-3200 in IEM BACOP to v2.23 | FRB |  |  | 44 |  | 2025-09-01 | 2025-07-08 | 2025-10-26 | Completed |  | 2025-09-01 | 2025-09-01 | [8 empty] | 5 | FRB |  | Past Compliance | -277
September | PDXW | PDX109 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX110 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX111 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX112 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX130 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX131 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX132 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX194 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX195 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX50 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX53 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX54 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX56 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX57 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX59 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX60 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 2 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX62 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX63 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX64 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX65 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX66 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX67 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 5 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX68 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXE | PDX69 | Hanley Energy | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 3 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXW | PDX171 | Hanley Energy | FRB: Upgrade IEM BACOP to v4.1 | FRB |  |  | 50 |  | 2025-09-04 | 2025-07-11 | 2025-10-29 | Open |  | 2025-09-04 | 2025-09-04 | [8 empty] | 5 | FRB |  | Past Compliance | -274 | MCM OVERDUE
September | PDXW | PDX171 | Hanley Energy | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 8 |  | 2025-09-04 13:54 | 2025-07-11 | 2025-10-29 | Completed |  | 2025-09-04 13:54 | 2025-09-04 13:54 | [8 empty] | 5 | SRVY |  | Past Compliance | -273
October | PDXW | PDX111 | Hanley Energy | BACOP firmware update v4.1 to v4.2 | CM |  |  | 1 |  | 2025-10-09 | 2025-08-15 | 2025-12-03 | Completed |  | 2025-10-09 | 2025-10-09 | [8 empty] | 5 | CM |  | Past Compliance | -239
October | PDXW | PDX171 | Hanley Energy | FRB: Upgrade IEM BACOP to v4.1 | FRB |  |  | 17 |  | 2025-10-10 15:13 | 2025-08-16 | 2025-12-04 | Open | MCM-137734842 | 2025-10-10 15:13 | 2025-10-10 15:13 |  |  | Complete | Tier 2 | ewwillam | 2025-12-22 13:30 | 2025-12-23 23:55 | Successful | 5 | FRB |  | Past Compliance | -237 | MCM Complete
October | PDXW | PDX171 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 4 |  | 2025-10-10 | 2025-08-16 | 2025-12-04 | Completed | MCM-137734842 | 2025-10-10 | 2025-10-10 |  |  | Complete | Tier 2 | ewwillam | 2025-12-22 13:30 | 2025-12-23 23:55 | Successful | 3 | SRVY |  | Past Compliance | -238 | MCM Complete
October | PDXW | PDX66 | Hanley Energy | PDX66 BACOP 3A Troubleshoot and Repair | CM |  |  | 1 |  | 2025-10-16 | 2025-08-22 | 2025-12-10 | Completed |  | 2025-10-16 | 2025-10-16 | [8 empty] | 5 | CM |  | Past Compliance | -232
October | PDXE | PDX195 | Hanley Energy | PDX195 BACOP PLC FAULT | CM |  |  | 1 |  | 2025-10-17 | 2025-08-23 | 2025-12-11 | Completed |  | 2025-10-17 | 2025-10-17 | [8 empty] | 5 | CM |  | Past Compliance | -231
October | PDXW | PDX62 | Hanley Energy | BACOP 10B HMI Boot Failure | CM |  |  | 1 |  | 2025-10-27 | 2025-09-02 | 2025-12-21 | Completed |  | 2025-10-27 | 2025-10-27 | [8 empty] | 5 | CM |  | Past Compliance | -221
October | PDXE | PDX63 | Hanley Energy | 2B Update BACOP Panels to firmware v4.2 | CM |  |  | 20 |  | 2025-10-31 | 2025-09-06 | 2025-12-25 | Open | MCM-137515669 | 2025-10-31 | 2025-10-31 |  |  | Cancelled | Tier 2 | jomcdjj | 2025-12-29 08:00 | 2026-01-29 07:59 |  | 5 | CM |  | Past Compliance | -217 | MCM Cancelled — Resubmit
November | PDXE | PDX57 | Hanley Energy | BACOP 5B | PR |  |  | 2 |  | 2025-11-04 | 2025-09-10 | 2025-12-29 | Completed |  | 2025-11-04 | 2025-11-04 | [8 empty] | 5 | PR |  | Past Compliance | -213
November | PDXE | PDX130 | Hanley Energy | GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | CM |  |  | 2 |  | 2025-11-06 | 2025-09-12 | 2025-12-31 | Completed |  | 2025-11-06 | 2025-11-06 | [8 empty] | 5 | CM |  | Past Compliance | -211
November | PDXE | PDX69 | Hanley Energy | BACOP 2.4A Battery 1 Replacement | CM |  |  | 1 |  | 2025-11-06 | 2025-09-12 | 2025-12-31 | Cancelled | MCM-137996136 | 2025-11-06 | 2025-11-06 |  |  | Cancelled | Tier 2 | aguiaedg | 2025-12-15 08:00 | 2026-01-01 07:59 |  | 5 | CM |  | Past Compliance | -211 | MCM Cancelled — Resubmit
November | PDXW | PDX171 | Hanley Energy | PDX171 BACOP STRATIX SWITCH FIRMWARE UPDATE FROM v1751 to v1753 | CM |  |  | 1 |  | 2025-11-09 | 2025-09-15 | 2026-01-03 | Completed | MCM-137734842 | 2025-11-09 | 2025-11-09 |  |  | Complete | Tier 2 | ewwillam | 2025-12-22 13:30 | 2025-12-23 23:55 | Successful | 5 | CM |  | Past Compliance | -208 | MCM Complete
November | PDXW | PDX110 | Hanley Energy | BACOP V4.2 Software Upgrade | REG-FOLL |  |  | 1 |  | 2025-11-12 13:03 | 2025-09-18 | 2026-01-06 | Open |  | 2025-11-12 13:03 | 2025-11-12 13:03 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -204 | MCM OVERDUE
November | PDXW | PDX172 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2025-11-14 | 2025-09-20 | 2026-01-08 | Completed | MCM-138789313 | 2025-11-14 | 2025-11-14 |  |  | Complete | Tier 2 | jpsoren | 2026-02-08 08:00 | 2026-03-11 06:55 | Successful | 3 | SRVY |  | Past Compliance | -203 | MCM Complete
November | PDXW | PDX66 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 7 |  | 2025-11-24 | 2025-09-30 | 2026-01-18 | Open | MCM-136563989 | 2025-11-24 | 2025-11-24 |  |  | Complete | Tier 2 | camrenk | 2026-01-20 14:00 | 2026-02-07 07:30 | Successful | 5 | FRB |  | Past Compliance | -193 | MCM Complete
November | PDXW | PDX66 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2025-11-24 13:42 | 2025-09-30 | 2026-01-18 | Completed | MCM-136563989 | 2025-11-24 13:42 | 2025-11-24 13:42 |  |  | Complete | Tier 2 | camrenk | 2026-01-20 14:00 | 2026-02-07 07:30 | Successful | 3 | SRVY |  | Past Compliance | -192 | MCM Complete
November | PDXW | PDX68 | Hanley Energy | PDX68 BACOP V4.2 Software Upgrade | PR |  |  | 1 |  | 2025-11-24 13:59 | 2025-09-30 | 2026-01-18 | Open |  | 2025-11-24 13:59 | 2025-11-24 13:59 | [8 empty] | 5 | PR |  | Past Compliance | -192 | MCM OVERDUE
December | PDXW | PDX66 | Hanley Energy | FRB: Upgrade Cyber Sciences SER-3200 in Hanley BACOP to v2.23 | FRB |  |  | 29 |  | 2025-12-04 | 2025-10-10 | 2026-01-28 | Completed | MCM-136563989 | 2025-12-04 | 2025-12-04 |  |  | Complete | Tier 2 | camrenk | 2026-01-20 14:00 | 2026-02-07 07:30 | Successful | 5 | FRB |  | Past Compliance | -183 | MCM Complete
December | PDXE | PDX57 | Hanley Energy | BACOP 6B | PR |  |  | 1 |  | 2025-12-09 | 2025-10-15 | 2026-02-02 | Completed |  | 2025-12-09 | 2025-12-09 | [8 empty] | 5 | PR |  | Past Compliance | -178
December | PDXE | PDX133 | Hanley Energy | PDX133 BACOP Level 1 Settings Increase | CM |  |  | 1 |  | 2025-12-16 | 2025-10-22 | 2026-02-09 | Completed | MCM-140550708 | 2025-12-16 | 2025-12-16 |  |  | Complete | Tier 2 | coronahb | 2026-02-16 08:00 | 2026-03-16 07:00 | Successful | 5 | CM |  | Past Compliance | -171 | MCM Complete
December | PDXW | PDX172 | Hanley Energy | BACOP 1.1B Health Alarm Troubleshoot and Repair | CM |  |  | 1 |  | 2025-12-21 | 2025-10-27 | 2026-02-14 | Open | MCM-138789313 | 2025-12-21 | 2025-12-21 |  |  | Complete | Tier 2 | jpsoren | 2026-02-08 08:00 | 2026-03-11 06:55 | Successful | 5 | CM |  | Past Compliance | -166 | MCM Complete
December | PDXW | PDX66 | Hanley Energy | BACOP 12M PM | CM |  |  | 1 |  | 2025-12-22 | 2025-10-28 | 2026-02-15 | Completed | MCM-136563989 | 2025-12-22 | 2025-12-22 |  |  | Complete | Tier 2 | camrenk | 2026-01-20 14:00 | 2026-02-07 07:30 | Successful | 5 | CM |  | Past Compliance | -165 | MCM Complete
December | PDXW | PDX62 | Hanley Energy | PDX62 BACOP 12M PM | FPM |  |  | 2 |  | 2025-12-30 10:13 | 2025-11-05 | 2026-02-23 | Open | MCM-137280144 | 2025-12-30 10:13 | 2025-12-30 10:13 |  |  | Complete | Tier 2 | tzeise | 2026-03-02 18:30 | 2026-04-04 06:55 | Successful | 5 | FPM |  | Past Compliance | -156 | MCM Complete
December | PDXW | PDX64 | Hanley Energy | PDX64 BACOP 12M PM | FPM |  |  | 2 |  | 2025-12-30 10:22 | 2025-11-05 | 2026-02-23 | Open |  | 2025-12-30 10:22 | 2025-12-30 10:22 | [8 empty] | 5 | FPM |  | Past Compliance | -156 | MCM OVERDUE
January | PDXE | PDX133 | Hanley Energy | PDX133 BACOP Level 1 Settings Increase | CM |  |  | 5 |  | 2026-01-08 | 2025-11-14 | 2026-03-04 | Completed | MCM-140550708 | 2026-01-08 | 2026-01-08 |  |  | Complete | Tier 2 | coronahb | 2026-02-16 08:00 | 2026-03-16 07:00 | Successful | 5 | CM |  | Past Compliance | -148 | MCM Complete
January | PDXW | PDX56 | Hanley Energy | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 9 |  | 2026-01-15 14:15 | 2025-11-21 | 2026-03-11 | Open | MCM-140750949 | 2026-01-15 14:15 | 2026-01-15 14:15 |  |  | Cancelled | Tier 2 | cbazanay | 2026-01-16 08:00 | 2026-02-16 07:59 |  | 5 | FRB |  | Past Compliance | -140 | MCM Cancelled — Resubmit
January | PDXW | PDX56 | Hanley Energy | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 9 |  | 2026-01-15 | 2025-11-21 | 2026-03-11 | Completed | MCM-140750949 | 2026-01-15 | 2026-01-15 |  |  | Cancelled | Tier 2 | cbazanay | 2026-01-16 08:00 | 2026-02-16 07:59 |  | 3 | SRVY |  | Past Compliance | -141 | MCM Cancelled — Resubmit
January | PDXE | PDX130 | Hanley Energy | BACOP 1.5A Stratix Switch COMMS | CM |  |  | 1 |  | 2026-01-19 | 2025-11-25 | 2026-03-15 | Completed | MCM-144582000 | 2026-01-19 | 2026-01-19 |  |  | Complete | Tier 3 | shldsjas | 2026-02-16 14:00 | 2026-03-19 01:00 | Successful | 5 | CM |  | Past Compliance | -137 | MCM Complete
January | PDXW | PDX172 | Hanley Energy | BACOP 1.3A Meter Error | CM |  |  | 1 |  | 2026-01-27 | 2025-12-03 | 2026-03-23 | Completed | MCM-138789313 | 2026-01-27 | 2026-01-27 |  |  | Complete | Tier 2 | jpsoren | 2026-02-08 08:00 | 2026-03-11 06:55 | Successful | 5 | CM |  | Past Compliance | -129 | MCM Complete

## 90 Day Outlook
Site | Description | Metrics (WO/Building) | Upgrades Needed? | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM Scheduled Start Date | MCM Scheduled End Date | MCM/TT | Vendor Start Date | Vendor End Date | Site Confirmation | MCM Gap Status
PDX111 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-05-04 | 2026-03-10 | 2026-06-28 | MCM Scheduled | 2026-06-07 13:00 | 2026-07-08 06:59 | MCM-134903284 |  |  |  | MCM Scheduled
PDX112 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-05-10 | 2026-03-16 | 2026-07-04 | MCM Scheduled | 2026-06-08 13:00 | 2026-07-09 06:59 | MCM-145242196 |  |  |  | MCM Scheduled
PDX112 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-04 | 2026-04-10 | 2026-07-29 | MCM Scheduled | 2026-06-08 07:00 | 2026-07-09 06:59 | MCM-144338241 |  |  |  | MCM Scheduled
PDX111 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-11 | 2026-04-17 | 2026-08-05 | MCM Scheduled | 2026-06-07 13:00 | 2026-07-08 06:59 | MCM-136066518 |  |  |  | MCM Scheduled
PDX69 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-07-25 | 2026-05-31 | 2026-09-18 | MCM Scheduled | 2026-07-01 07:00 | 2026-07-31 06:55 | MCM-151521619 |  |  |  | MCM Scheduled
PDX57 | [GLOBAL] AMCOP 36M PM V1.0 | 13 | Yes | 2026-07-26 | 2026-06-01 | 2026-09-19 | MCM Needed (<60d) | [6 empty] | MCM Needed (<60d)
PDX99 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | Yes | 2026-08-01 | 2026-06-07 | 2026-09-25 | MCM Needed (<60d) | [6 empty] | MCM Needed (<60d)
PDX132 | [GLOBAL] AMCOP 36M PM V1.0 | 27 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)
PDX96 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | No | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)
PDX132 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM in Draft | 2026-07-27 13:00 | 2026-08-26 06:55 | MCM-147982640 |  |  |  | MCM in Draft
PDX54 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 2 | No | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM in Draft | 2026-07-01 07:00 | 2026-07-31 06:55 | MCM-151535397 |  |  |  | MCM in Draft
PDX57 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 12 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM Scheduled | 2026-06-15 13:00 | 2026-07-16 01:00 | MCM-150275221 |  |  |  | MCM Scheduled
PDX60 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 11 | Yes | 2026-08-15 | 2026-06-21 | 2026-10-09 | MCM Scheduled | 2026-06-15 13:00 | 2026-07-16 01:00 | MCM-150274397 |  |  |  | MCM Scheduled