## AMCOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
December | PDXC | PDX61 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 4 |  | 2021-12-17 | 2021-10-23 | 2022-02-10 | Completed |  | 2021-12-17 | 2021-12-17 | [8 empty] | 3 | PM |  | Past Compliance | -1631
September | PDXC | PDX90 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 21 |  | 2022-09-30 | 2022-08-06 | 2022-11-24 | Completed |  | 2022-09-30 | 2022-09-30 | [8 empty] | 3 | PM |  | Past Compliance | -1344
October | PDXC | PDX90 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2022-10-17 | 2022-08-23 | 2022-12-11 | Completed |  | 2022-10-17 | 2022-10-17 | [8 empty] | 3 | PM |  | Past Compliance | -1327
December | PDXC | PDX61 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2022-12-17 | 2022-10-23 | 2023-02-10 | Completed |  | 2022-12-17 | 2022-12-17 | [8 empty] | 3 | PM |  | Past Compliance | -1266
March | PDXC | PDX55 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 11 |  | 2023-03-16 | 2023-01-20 | 2023-05-10 | Completed |  | 2023-03-16 | 2023-03-16 | [8 empty] | 3 | PM |  | Past Compliance | -1177
August | PDXC | PDX97 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2023-08-01 | 2023-06-07 | 2023-09-25 | Completed |  | 2023-08-01 | 2023-08-01 | [8 empty] | 3 | PM |  | Past Compliance | -1039
September | PDXC | PDX58 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 6 |  | 2023-09-09 | 2023-07-16 | 2023-11-03 | Completed |  | 2023-09-09 | 2023-09-09 | [8 empty] | 3 | PM |  | Past Compliance | -1000
October | PDXC | PDX91 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 22 |  | 2023-10-15 | 2023-08-21 | 2023-12-09 | Completed |  | 2023-10-15 | 2023-10-15 | [8 empty] | 3 | PM |  | Past Compliance | -964
January | PDXC | PDX58 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 8 |  | 2024-01-28 | 2023-12-04 | 2024-03-23 | Completed |  | 2024-01-28 | 2024-01-28 | [8 empty] | 3 | PM |  | Past Compliance | -859
July | PDXC | PDX52 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 16 |  | 2024-07-01 | 2024-05-07 | 2024-08-25 | Completed |  | 2024-07-01 | 2024-07-01 | [8 empty] | 3 | PM |  | Past Compliance | -704
July | PDXC | PDX92 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2024-07-12 | 2024-05-18 | 2024-09-05 | Completed |  | 2024-07-12 | 2024-07-12 | [8 empty] | 3 | PM |  | Past Compliance | -693
December | PDXC | PDX61 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 11 |  | 2024-12-17 | 2024-10-23 | 2025-02-10 | Completed |  | 2024-12-17 | 2024-12-17 | [8 empty] | 3 | PM |  | Past Compliance | -535
June | PDXC | PDX93 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 27 |  | 2025-06-20 | 2025-04-26 | 2025-08-14 | Completed |  | 2025-06-20 | 2025-06-20 | [8 empty] | 3 | PM |  | Past Compliance | -350
September | PDXC | PDX90 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 21 |  | 2025-09-30 | 2025-08-06 | 2025-11-24 | Completed |  | 2025-09-30 | 2025-09-30 | [8 empty] | 3 | PM |  | Past Compliance | -248
October | PDXC | PDX90 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2025-10-17 | 2025-08-23 | 2025-12-11 | Completed |  | 2025-10-17 | 2025-10-17 | [8 empty] | 3 | PM |  | Past Compliance | -231
December | PDXC | PDX180 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-12-10 | 2025-10-16 | 2026-02-03 | Completed | MCM-132879050 | 2025-12-10 | 2025-12-10 |  |  | Complete | Tier 2 | samsine | 2025-12-22 08:00 | 2025-12-23 22:00 | Successful | 3 | PM |  | Past Compliance | -177 | MCM Complete
December | PDXC | PDX61 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-12-17 | 2025-10-23 | 2026-02-10 | Completed | MCM-135965018 | 2025-12-17 | 2025-12-17 |  |  | Complete | Tier 2 | shephawk | 2025-12-15 08:00 | 2026-01-10 03:00 | Successful | 3 | PM |  | Past Compliance | -170 | MCM Complete
February | PDXC | PDX61 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-02-21 | 2025-12-28 | 2026-04-17 | Completed | MCM-138853859 | 2026-02-21 | 2026-02-21 |  |  | Complete | Tier 2 | xcastoma | 2026-03-09 13:00 | 2026-04-09 06:55 | Successful | 3 | PM |  | Past Compliance | -104 | MCM Complete
March | PDXC | PDX55 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 11 |  | 2026-03-16 | 2026-01-20 | 2026-05-10 | Completed | MCM-130416811 | 2026-03-16 | 2026-03-16 |  |  | Scheduled | Tier 2 | combine | 2026-05-13 07:00 | 2026-06-13 06:59 |  | 3 | PM |  | Past Compliance | -81
August | PDXC | PDX97 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-08-01 | 2026-06-07 | 2026-09-25 | Open |  | 2026-08-01 | 2026-08-01 | [8 empty] | 3 | PM |  | Outside Compliance | 57 | MCM Needed (<60d)
September | PDXC | PDX58 | IEM | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 5 |  | 2026-09-09 | 2026-07-16 | 2026-11-03 | Open |  | 2026-09-09 | 2026-09-09 | [8 empty] | 3 | PM |  | Outside Compliance | 96 | MCM Not Yet Required

## AMCOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXC | PDX61 | IEM | Amcop Battery Replacement | CM |  |  | 1 |  | 2024-04-22 | 2024-02-27 | 2024-06-16 | Completed |  | 2024-04-22 | 2024-04-22 | [8 empty] | 5 | CM |  | Past Compliance | -774
April | PDXC | PDX178 | IEM | FSB: Identify AMCOPs running software V4.1 for network setting update R1 | SRVY |  |  | 18 |  | 2024-04-23 | 2024-02-28 | 2024-06-17 | Completed |  | 2024-04-23 | 2024-04-23 | [8 empty] | 3 | SRVY |  | Past Compliance | -773
April | PDXC | PDX4 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXC | PDX52 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 16 |  | 2024-04-26 20:16 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 20:16 | 2024-04-26 20:16 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXC | PDX58 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 13 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXC | PDX606 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXC | PDX61 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 14 |  | 2024-04-26 20:18 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 20:18 | 2024-04-26 20:18 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXC | PDX90 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXC | PDX91 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 22 |  | 2024-04-26 19:34 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:34 | 2024-04-26 19:34 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXC | PDX92 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:35 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:35 | 2024-04-26 19:35 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXC | PDX93 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:35 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:35 | 2024-04-26 19:35 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXC | PDX97 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
May | PDXC | PDX178 | IEM | FSB: Update AMCOP v4.1 HMI network port setting R1 | FSB |  |  | 17 |  | 2024-05-02 17:40 | 2024-03-08 | 2024-06-26 | Completed |  | 2024-05-02 17:40 | 2024-05-02 17:40 | [8 empty] | 3 | FSB |  | Past Compliance | -763
May | PDXC | PDX179 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 11 |  | 2024-05-15 | 2024-03-21 | 2024-07-09 | Completed |  | 2024-05-15 | 2024-05-15 | [8 empty] | 3 | SRVY |  | Past Compliance | -751
May | PDXC | PDX4 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX52 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 16 |  | 2024-05-16 06:36 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:36 | 2024-05-16 06:36 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX58 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 13 |  | 2024-05-16 06:55 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 06:55 | 2024-05-16 06:55 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX606 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX61 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 14 |  | 2024-05-16 08:25 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 08:25 | 2024-05-16 08:25 | [8 empty] | 3 | FSB |  | Past Compliance | -749
May | PDXC | PDX90 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX91 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 22 |  | 2024-05-16 07:02 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 07:02 | 2024-05-16 07:02 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX92 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX93 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXC | PDX97 | IEM | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
June | PDXC | PDX179 | IEM | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 13 |  | 2024-06-03 | 2024-04-09 | 2024-07-28 | Completed |  | 2024-06-03 | 2024-06-03 | [8 empty] | 3 | FSB |  | Past Compliance | -732
July | PDXC | PDX52 | IEM | 2A AMCOP and MCBU Troubleshooting | CM |  |  | 1 |  | 2024-07-16 | 2024-05-22 | 2024-09-09 | Completed |  | 2024-07-16 | 2024-07-16 | [8 empty] | 5 | CM |  | Past Compliance | -689
July | PDXC | PDX178 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:03 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:03 | 2024-07-23 16:03 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX4 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 16:04 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:04 | 2024-07-23 16:04 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX52 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 16 |  | 2024-07-23 16:06 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:06 | 2024-07-23 16:06 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX55 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 11 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXC | PDX58 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 13 |  | 2024-07-23 16:07 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:07 | 2024-07-23 16:07 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX606 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXC | PDX61 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 14 |  | 2024-07-23 16:08 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:08 | 2024-07-23 16:08 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX90 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 16:14 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:14 | 2024-07-23 16:14 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX91 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 22 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXC | PDX92 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 17:02 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 17:02 | 2024-07-23 17:02 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX93 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:15 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 16:15 | 2024-07-23 16:15 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXC | PDX97 | IEM | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
August | PDXC | PDX179 | IEM | FRB: Update AMCOP to V4.0 | FRB |  |  | 17 |  | 2024-08-03 | 2024-06-09 | 2024-09-27 | Completed |  | 2024-08-03 | 2024-08-03 | [8 empty] | 5 | FRB |  | Past Compliance | -671
August | PDXC | PDX93 | IEM | AMCOP 1.3A Auto Failure and MCBG Basler Relay Fault | CM |  |  | 1 |  | 2024-08-31 | 2024-07-07 | 2024-10-25 | Completed |  | 2024-08-31 | 2024-08-31 | [8 empty] | 5 | CM |  | Past Compliance | -643
September | PDXC | PDX179 | IEM | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 24 |  | 2024-09-05 11:41 | 2024-07-12 | 2024-10-30 | Completed |  | 2024-09-05 11:41 | 2024-09-05 11:41 | [8 empty] | 3 | FSB |  | Past Compliance | -637
October | PDXC | PDX179 | IEM | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 11 |  | 2024-10-01 06:56 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 06:56 | 2024-10-01 06:56 | [8 empty] | 3 | FSB |  | Past Compliance | -612
October | PDXC | PDX52 | IEM | 2A AMCOP Auto Fail | CM |  |  | 1 |  | 2024-10-23 | 2024-08-29 | 2024-12-17 | Completed |  | 2024-10-23 | 2024-10-23 | [8 empty] | 5 | CM |  | Past Compliance | -590
October | PDXC | PDX180 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 11 |  | 2024-10-25 | 2024-08-31 | 2024-12-19 | Completed |  | 2024-10-25 | 2024-10-25 | [8 empty] | 3 | SRVY |  | Past Compliance | -588
October | PDXC | PDX90 | IEM | 9B Failed to start from AMCOP | CM |  |  | 1 |  | 2024-10-30 | 2024-09-05 | 2024-12-24 | Completed |  | 2024-10-30 | 2024-10-30 | [8 empty] | 5 | CM |  | Past Compliance | -583
November | PDXC | PDX52 | IEM | AMCOP 5C Spare PLC Retrofit | PR |  |  | 2 |  | 2024-11-07 | 2024-09-13 | 2025-01-01 | Completed |  | 2024-11-07 | 2024-11-07 | [8 empty] | 5 | PR |  | Past Compliance | -575
November | PDXC | PDX179 | IEM | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 155 |  | 2024-11-15 15:53 | 2024-09-21 | 2025-01-09 | Completed |  | 2024-11-15 15:53 | 2024-11-15 15:53 | [8 empty] | 3 | FSB |  | Past Compliance | -566
November | PDXC | PDX178 | IEM | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 10 |  | 2024-11-22 20:11 | 2024-09-28 | 2025-01-16 | Completed |  | 2024-11-22 20:11 | 2024-11-22 20:11 | [8 empty] | 3 | FSB |  | Past Compliance | -559
December | PDXC | PDX180 | IEM | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 14 |  | 2024-12-02 12:09 | 2024-10-08 | 2025-01-26 | Completed |  | 2024-12-02 12:09 | 2024-12-02 12:09 | [8 empty] | 3 | FSB |  | Past Compliance | -549
December | PDXC | PDX179 | IEM | AMCOP Troubleshooting and Repair | CM |  |  | 1 |  | 2024-12-09 | 2024-10-15 | 2025-02-02 | Completed |  | 2024-12-09 | 2024-12-09 | [8 empty] | 3 | CM |  | Past Compliance | -543
December | PDXC | PDX52 | IEM | AMCOP 5A Fuse Holder Troubleshooting | CM |  |  | 1 |  | 2024-12-18 | 2024-10-24 | 2025-02-11 | Completed |  | 2024-12-18 | 2024-12-18 | [8 empty] | 5 | CM |  | Past Compliance | -534
January | PDXC | PDX52 | IEM | UPS 7A-1 AMCOP Signal Relay Replacement | CM |  |  | 1 |  | 2025-01-15 | 2024-11-21 | 2025-03-11 | Completed |  | 2025-01-15 | 2025-01-15 | [8 empty] | 5 | CM |  | Past Compliance | -506
January | PDXC | PDX180 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 27 |  | 2025-01-17 | 2024-11-23 | 2025-03-13 | Completed |  | 2025-01-17 | 2025-01-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -504
January | PDXC | PDX179 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:23 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:23 | 2025-01-22 12:23 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX4 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 12:26 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:26 | 2025-01-22 12:26 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX52 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 16 |  | 2025-01-22 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 | 2025-01-22 | [8 empty] | 5 | FRB |  | Past Compliance | -499
January | PDXC | PDX55 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 11 |  | 2025-01-22 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 | 2025-01-22 | [8 empty] | 5 | FRB |  | Past Compliance | -499
January | PDXC | PDX58 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 13 |  | 2025-01-22 12:29 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:29 | 2025-01-22 12:29 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX606 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:30 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:30 | 2025-01-22 12:30 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX61 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 14 |  | 2025-01-22 12:30 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:30 | 2025-01-22 12:30 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX92 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:39 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:39 | 2025-01-22 12:39 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX93 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:40 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:40 | 2025-01-22 12:40 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX97 | IEM | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:40 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:40 | 2025-01-22 12:40 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXC | PDX178 | IEM | FSB: Update AMCOP v4.1 HMI network port setting R1 | FSB |  |  | 35 |  | 2025-01-27 | 2024-12-03 | 2025-03-23 | Completed |  | 2025-01-27 | 2025-01-27 | [8 empty] | 3 | FSB |  | Past Compliance | -494
January | PDXC | PDX58 | IEM | AMCOP 36M Review | FPM |  |  | 1 |  | 2025-01-30 | 2024-12-06 | 2025-03-26 | Completed |  | 2025-01-30 | 2025-01-30 | [8 empty] | 5 | FPM |  | Past Compliance | -491
February | PDXC | PDX180 | IEM | FDN: OPTDC AMCOP Utility Source Loss Timer Adjustment | FSB |  |  | 17 |  | 2025-02-04 08:35 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 08:35 | 2025-02-04 08:35 | [8 empty] | 5 | FSB |  | Past Compliance | -485
February | PDXC | PDX181 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 60 |  | 2025-02-04 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 | 2025-02-04 | [8 empty] | 3 | SRVY |  | Past Compliance | -486
March | PDXC | PDX4 | IEM | Amcop Timer Correction | CM |  |  | 2 |  | 2025-03-11 | 2025-01-15 | 2025-05-05 | Completed |  | 2025-03-11 | 2025-03-11 | [8 empty] | 5 | CM |  | Past Compliance | -451
March | PDXC | PDX179 | IEM | PDX179: SER-3200-PTP REPLACEMENT FOR AMCOP 2.4A | CM |  |  | 1 |  | 2025-03-19 | 2025-01-23 | 2025-05-13 | Completed |  | 2025-03-19 | 2025-03-19 | [8 empty] | 5 | CM |  | Past Compliance | -443
April | PDXC | PDX180 | IEM | FSB: Identify AMCOPs running software V4.1 for network setting update R1 | SRVY |  |  | 12 |  | 2025-04-02 | 2025-02-06 | 2025-05-27 | Completed |  | 2025-04-02 | 2025-04-02 | [8 empty] | 3 | SRVY |  | Past Compliance | -429
April | PDXC | PDX181 | IEM | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 49 |  | 2025-04-24 | 2025-02-28 | 2025-06-18 | Completed |  | 2025-04-24 | 2025-04-24 | [8 empty] | 3 | FSB |  | Past Compliance | -407
June | PDXC | PDX181 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 75 |  | 2025-06-04 | 2025-04-10 | 2025-07-29 | Completed |  | 2025-06-04 | 2025-06-04 | [8 empty] | 3 | SRVY |  | Past Compliance | -366
June | PDXC | PDX61 | IEM | PDX61 AMCOP 5B PLC REPLACING 2 ALARM WIRES | CM |  |  | 1 |  | 2025-06-04 | 2025-04-10 | 2025-07-29 | Completed |  | 2025-06-04 | 2025-06-04 | [8 empty] | 5 | CM |  | Past Compliance | -366
June | PDXC | PDX178 | IEM | PDX180 AMCOP START-UP | FPM |  |  | 1 |  | 2025-06-23 | 2025-04-29 | 2025-08-17 | Completed |  | 2025-06-23 | 2025-06-23 | [8 empty] | 5 | FPM |  | Past Compliance | -347
July | PDXC | PDX181 | IEM | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 58 |  | 2025-07-01 13:51 | 2025-05-07 | 2025-08-25 | Completed |  | 2025-07-01 13:51 | 2025-07-01 13:51 | [8 empty] | 3 | FSB |  | Past Compliance | -338
July | PDXC | PDX4 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 08:07 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:07 | 2025-07-11 08:07 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXC | PDX52 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 16 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX55 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 11 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX58 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 13 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX606 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX90 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 08:21 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:21 | 2025-07-11 08:21 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXC | PDX91 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 22 |  | 2025-07-11 08:21 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:21 | 2025-07-11 08:21 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXC | PDX92 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 08:21 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:21 | 2025-07-11 08:21 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXC | PDX93 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX97 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXC | PDX55 | IEM | AMCOP 4B SER & PLC | CM |  |  | 1 |  | 2025-07-14 | 2025-05-20 | 2025-09-07 | Completed |  | 2025-07-14 | 2025-07-14 | [8 empty] | 5 | CM |  | Past Compliance | -326
July | PDXC | PDX178 | IEM | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 37 |  | 2025-07-21 10:20 | 2025-05-27 | 2025-09-14 | Completed |  | 2025-07-21 10:20 | 2025-07-21 10:20 | [8 empty] | 5 | FRB |  | Past Compliance | -318
July | PDXC | PDX179 | IEM | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 36 |  | 2025-07-21 | 2025-05-27 | 2025-09-14 | Completed |  | 2025-07-21 | 2025-07-21 | [8 empty] | 5 | FRB |  | Past Compliance | -319
July | PDXC | PDX180 | IEM | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 37 |  | 2025-07-21 10:20 | 2025-05-27 | 2025-09-14 | Open |  | 2025-07-21 10:20 | 2025-07-21 10:20 | [8 empty] | 5 | FRB |  | Past Compliance | -318 | MCM OVERDUE
July | PDXC | PDX93 | IEM | AMCOP 1.4B UPS Troubleshot/Repair | CM |  |  | 1 |  | 2025-07-28 | 2025-06-03 | 2025-09-21 | Completed |  | 2025-07-28 | 2025-07-28 | [8 empty] | 5 | CM |  | Past Compliance | -312
August | PDXC | PDX180 | IEM | AMCOP 1.2B Troubleshoot | CM |  |  | 2 |  | 2025-08-07 | 2025-06-13 | 2025-10-01 | Completed |  | 2025-08-07 | 2025-08-07 | [8 empty] | 5 | CM |  | Past Compliance | -302
August | PDXC | PDX180 | IEM | FSB: Identify sites for AMCOP-CUPS interconnect removal | SRVY |  |  | 52 |  | 2025-08-07 | 2025-06-13 | 2025-10-01 | Completed |  | 2025-08-07 | 2025-08-07 | [8 empty] | 3 | SRVY |  | Past Compliance | -302
August | PDXC | PDX55 | IEM | AMCOP 3A Beacon Light Replacement | CM |  |  | 3 |  | 2025-08-09 | 2025-06-15 | 2025-10-03 | Completed |  | 2025-08-09 | 2025-08-09 | [8 empty] | 5 | CM |  | Past Compliance | -300
August | PDXC | PDX4 | IEM | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 18 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXC | PDX52 | IEM | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 16 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXC | PDX606 | IEM | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXC | PDX97 | IEM | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXC | PDX91 | IEM | PDX91 AMCOP 8B BEACON LIGHT DIAG | CM |  |  | 1 |  | 2025-08-28 | 2025-07-04 | 2025-10-22 | Completed |  | 2025-08-28 | 2025-08-28 | [8 empty] | 5 | CM |  | Past Compliance | -281
August | PDXC | PDX52 | IEM | Global Action Item[PDX52][AMCOP SER (PLC) BCD Wiring and IP Validation | PR |  |  | 1 |  | 2025-08-29 | 2025-07-05 | 2025-10-23 | Completed |  | 2025-08-29 | 2025-08-29 | [8 empty] | 5 | PR |  | Past Compliance | -280
September | PDXC | PDX93 | IEM | AMCOP 1.4B troubleshoot/repair | CM |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 5 | CM |  | Past Compliance | -275
September | PDXC | PDX180 | IEM | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 27 |  | 2025-09-30 | 2025-08-06 | 2025-11-24 | Completed | MCM-132879050 | 2025-09-30 | 2025-09-30 |  |  | Complete | Tier 2 | samsine | 2025-12-22 08:00 | 2025-12-23 22:00 | Successful | 5 | PR |  | Past Compliance | -248 | MCM Complete
October | PDXC | PDX178 | IEM | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 26 |  | 2025-10-01 | 2025-08-07 | 2025-11-25 | Completed | MCM-135168761 | 2025-10-01 | 2025-10-01 |  |  | Complete | Tier 2 | zmguer | 2025-12-08 14:00 | 2025-12-20 02:00 | Successful | 5 | PR |  | Past Compliance | -247 | MCM Complete
October | PDXC | PDX179 | IEM | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 27 |  | 2025-10-02 | 2025-08-08 | 2025-11-26 | Completed | MCM-135421715 | 2025-10-02 | 2025-10-02 |  |  | Cancelled | Tier 2 | musjaff | 2025-12-08 14:00 | 2025-12-13 02:00 |  | 5 | PR |  | Past Compliance | -246 | MCM Cancelled — Resubmit
October | PDXC | PDX181 | IEM | AMCOP SER(BCD) PLC/IP Wiring Validation | PR |  |  | 27 |  | 2025-10-02 | 2025-08-08 | 2025-11-26 | Completed |  | 2025-10-02 | 2025-10-02 | [8 empty] | 5 | PR |  | Past Compliance | -246
October | PDXC | PDX52 | IEM | AMCOP 6B Troubleshoot and Repair | CM |  |  | 1 |  | 2025-10-30 | 2025-09-05 | 2025-12-24 | Completed | MCM-139598394 | 2025-10-30 | 2025-10-30 |  |  | Complete | Tier 2 | hegmason | 2025-12-17 08:00 | 2025-12-24 07:00 | Successful | 5 | CM |  | Past Compliance | -218 | MCM Complete
November | PDXC | PDX52 | IEM | AMCOP 6B Troubleshoot and Repair | CM |  |  | 1 |  | 2025-11-03 | 2025-09-09 | 2025-12-28 | Completed | MCM-139598394 | 2025-11-03 | 2025-11-03 |  |  | Complete | Tier 2 | hegmason | 2025-12-17 08:00 | 2025-12-24 07:00 | Successful | 5 | CM |  | Past Compliance | -214 | MCM Complete
November | PDXC | PDX181 | IEM | AMCOP 2.6B HMI Descrepencies | CM |  |  | 1 |  | 2025-11-07 | 2025-09-13 | 2026-01-01 | Open |  | 2025-11-07 | 2025-11-07 | [8 empty] | 5 | CM |  | Past Compliance | -210 | MCM OVERDUE
November | PDXC | PDX58 | IEM | PDX058 AMCOP SER/Fault Code Points Update | CM |  |  | 1 |  | 2025-11-20 | 2025-09-26 | 2026-01-14 | Completed |  | 2025-11-20 | 2025-11-20 | [8 empty] | 5 | CM |  | Past Compliance | -197
November | PDXC | PDX61 | IEM | PDX061 AMCOP SER/Fault Code Points Update | CM |  |  | 1 |  | 2025-11-20 | 2025-09-26 | 2026-01-14 | Completed | MCM-135965018 | 2025-11-20 | 2025-11-20 |  |  | Complete | Tier 2 | shephawk | 2025-12-15 08:00 | 2026-01-10 03:00 | Successful | 5 | CM |  | Past Compliance | -197 | MCM Complete
December | PDXC | PDX58 | IEM | PDX58 AMCOP V6 Upgrades | PR |  |  | 14 |  | 2025-12-08 | 2025-10-14 | 2026-02-01 | Completed |  | 2025-12-08 | 2025-12-08 | [8 empty] | 5 | PR |  | Past Compliance | -179
December | PDXC | PDX90 | IEM | AMCOP Battery Replacements | MEC |  |  | 11 |  | 2025-12-10 15:50 | 2025-10-16 | 2026-02-03 | Completed | MCM-132412450 | 2025-12-10 15:50 | 2025-12-10 15:50 |  |  | Complete | Tier 2 | mrneal | 2026-02-04 14:00 | 2026-03-06 02:00 | Successful | 5 | MEC |  | Past Compliance | -176 | MCM Complete
December | PDXC | PDX4 | IEM | AMCOP 18A Troubleshoot | BRKD |  |  | 1 |  | 2025-12-17 | 2025-10-23 | 2026-02-10 | Completed | MCM-140610481 | 2025-12-17 | 2025-12-17 |  |  | Complete | Tier 3 | adamitcd | 2025-12-18 16:00 | 2025-12-19 07:59 | Successful | 5 | BRKD |  | Past Compliance | -170 | MCM Complete
December | PDXC | PDX58 | IEM | PDX58 AMCOP 4A SER replacement | CM |  |  | 1 |  | 2025-12-17 | 2025-10-23 | 2026-02-10 | Completed | MCM-138830411 | 2025-12-17 | 2025-12-17 |  |  | Complete | Tier 2 | xcastoma | 2026-03-09 13:00 | 2026-04-09 06:55 | Successful | 5 | CM |  | Past Compliance | -170 | MCM Complete
December | PDXC | PDX179 | IEM | PDX179 AMCOP-1.3A SER 1 AMCOP DC-UPS Battery Not Healthy transitioned to Active | CM |  |  | 2 |  | 2025-12-18 | 2025-10-24 | 2026-02-11 | Completed | MCM-140813849 | 2025-12-18 | 2025-12-18 |  |  | Complete | Tier 3 | musjaff | 2026-01-12 16:30 | 2026-01-17 02:00 | Successful | 5 | CM |  | Past Compliance | -169 | MCM Complete
December | PDXC | PDX93 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | CM |  |  | 28 |  | 2025-12-22 | 2025-10-28 | 2026-02-15 | Completed |  | 2025-12-22 | 2025-12-22 | [8 empty] | 5 | CM |  | Past Compliance | -165
December | PDXC | PDX178 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-135118343 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | zmguer | 2025-12-22 14:00 | 2026-02-28 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX179 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-140813849 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 3 | musjaff | 2026-01-12 16:30 | 2026-01-17 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX180 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132879050 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | samsine | 2025-12-22 08:00 | 2025-12-23 22:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX181 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed |  | 2025-12-23 | 2025-12-23 | [8 empty] | 5 | FSB |  | Past Compliance | -164
December | PDXC | PDX4 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 19 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-140610481 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 3 | adamitcd | 2025-12-18 16:00 | 2025-12-19 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX52 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 17 |  | 2025-12-23 14:42 | 2025-10-29 | 2026-02-16 | Open | MCM-139598394 | 2025-12-23 14:42 | 2025-12-23 14:42 |  |  | Complete | Tier 2 | hegmason | 2025-12-17 08:00 | 2025-12-24 07:00 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXC | PDX55 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 12 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-140271378 | 2025-12-23 | 2025-12-23 |  |  | Cancelled | Tier 3 | morewant | 2026-01-21 08:00 | 2026-02-20 08:00 |  | 5 | FSB |  | Past Compliance | -164 | MCM Cancelled — Resubmit
December | PDXC | PDX606 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132543422 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | adamitcd | 2026-01-05 08:00 | 2026-02-05 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX61 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 15 |  | 2025-12-23 14:44 | 2025-10-29 | 2026-02-16 | Completed | MCM-135965018 | 2025-12-23 14:44 | 2025-12-23 14:44 |  |  | Complete | Tier 2 | shephawk | 2025-12-15 08:00 | 2026-01-10 03:00 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXC | PDX90 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132412450 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | mrneal | 2026-02-04 14:00 | 2026-03-06 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX91 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 23 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-133269831 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | vanscole | 2026-01-12 15:00 | 2026-01-31 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX92 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-133131092 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | studylan | 2026-02-02 08:00 | 2026-03-03 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXC | PDX97 | IEM | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132540079 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | adamitcd | 2026-01-05 08:00 | 2026-02-05 07:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
January | PDXC | PDX606 | IEM | PDX606 AMCOP/V6 Upgrade | PR |  |  | 1 |  | 2026-01-13 | 2025-11-19 | 2026-03-09 | Cancelled | MCM-132543422 | 2026-01-13 | 2026-01-13 |  |  | Complete | Tier 2 | adamitcd | 2026-01-05 08:00 | 2026-02-05 07:59 | Successful | 3 | PR |  | Past Compliance | -143 | MCM Complete
January | PDXC | PDX52 | IEM | AMCOP Camlock Wire Reconfiguration | CM |  |  | 1 |  | 2026-01-27 | 2025-12-03 | 2026-03-23 | Completed | MCM-143285957 | 2026-01-27 | 2026-01-27 |  |  | Complete | Tier 2 | ajtimpy | 2026-01-29 14:00 | 2026-01-30 02:00 | Successful - Off Script | 5 | CM |  | Past Compliance | -129 | MCM Complete
January | PDXC | PDX90 | IEM | [PDX90] AMCOP SER PLC Wiring Validation | FPM |  |  | 23 |  | 2026-01-27 | 2025-12-03 | 2026-03-23 | Completed | MCM-132412450 | 2026-01-27 | 2026-01-27 |  |  | Complete | Tier 2 | mrneal | 2026-02-04 14:00 | 2026-03-06 02:00 | Successful | 5 | FPM |  | Past Compliance | -129 | MCM Complete
February | PDXC | PDX90 | IEM | FSB: Perform firmware and hardware upgrades to AMCOP | FPM |  |  | 1 |  | 2026-02-04 | 2025-12-11 | 2026-03-31 | Completed | MCM-132412450 | 2026-02-04 | 2026-02-04 |  |  | Complete | Tier 2 | mrneal | 2026-02-04 14:00 | 2026-03-06 02:00 | Successful | 5 | FPM |  | Past Compliance | -121 | MCM Complete

## BACOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
October | PDXC | PDX91 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 14 |  | 2023-10-01 | 2023-08-07 | 2023-11-25 | Completed |  | 2023-10-01 | 2023-10-01 | [8 empty] | 4 | PM |  | Past Compliance | -978
March | PDXC | PDX92 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2024-03-01 | 2024-01-06 | 2024-04-25 | Completed |  | 2024-03-01 | 2024-03-01 | [8 empty] | 4 | PM |  | Past Compliance | -826
March | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2024-03-21 | 2024-01-26 | 2024-05-15 | Completed |  | 2024-03-21 | 2024-03-21 | [8 empty] | 4 | PM |  | Past Compliance | -806
May | PDXC | PDX58 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2024-05-02 | 2024-03-08 | 2024-06-26 | Completed |  | 2024-05-02 | 2024-05-02 | [8 empty] | 4 | PM |  | Past Compliance | -764
June | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2024-06-01 | 2024-04-07 | 2024-07-26 | Completed |  | 2024-06-01 | 2024-06-01 | [8 empty] | 4 | PM |  | Past Compliance | -734
June | PDXC | PDX58 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2024-06-29 | 2024-05-05 | 2024-08-23 | Completed |  | 2024-06-29 | 2024-06-29 | [8 empty] | 4 | PM |  | Past Compliance | -706
September | PDXC | PDX58 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2024-09-07 | 2024-07-14 | 2024-11-01 | Completed |  | 2024-09-07 | 2024-09-07 | [8 empty] | 4 | PM |  | Past Compliance | -636
June | PDXC | PDX55 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2025-06-02 | 2025-04-08 | 2025-07-27 | Completed |  | 2025-06-02 | 2025-06-02 | [8 empty] | 4 | PM |  | Past Compliance | -368
June | PDXC | PDX93 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2025-06-20 | 2025-04-26 | 2025-08-14 | Completed |  | 2025-06-20 | 2025-06-20 | [8 empty] | 4 | PM |  | Past Compliance | -350
December | PDXC | PDX180 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2025-12-10 | 2025-10-16 | 2026-02-03 | Completed | MCM-139726947 | 2025-12-10 | 2025-12-10 |  |  | Complete | Tier 3 | ernlealf | 2025-12-09 08:00 | 2026-01-09 07:59 | Successful | 4 | PM |  | Past Compliance | -177 | MCM Complete
January | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2026-01-20 | 2025-11-26 | 2026-03-16 | Completed | MCM-143270588 | 2026-01-20 | 2026-01-20 |  |  | Complete | Tier 3 | corahale | 2026-02-16 14:00 | 2026-03-14 06:55 | Successful | 4 | PM |  | Past Compliance | -136 | MCM Complete
October | PDXC | PDX55 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2026-10-01 | 2026-08-07 | 2026-11-25 | Open |  | 2026-10-01 | 2026-10-01 | [8 empty] | 4 | PM |  | Outside Compliance | 118 | MCM Not Yet Required
February | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2027-02-22 | 2026-12-29 | 2027-04-18 | Open |  | 2027-02-22 | 2027-02-22 | [8 empty] | 4 | PM |  | Outside Compliance | 262 | MCM Not Yet Required
March | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2027-03-21 | 2027-01-25 | 2027-05-15 | Open |  | 2027-03-21 | 2027-03-21 | [8 empty] | 4 | PM |  | Outside Compliance | 289 | MCM Not Yet Required
June | PDXC | PDX61 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2027-06-01 | 2027-04-07 | 2027-07-26 | Open |  | 2027-06-01 | 2027-06-01 | [8 empty] | 4 | PM |  | Outside Compliance | 361 | MCM Not Yet Required
June | PDXC | PDX55 | IEM | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2028-06-02 | 2028-04-08 | 2028-07-27 | Open |  | 2028-06-02 | 2028-06-02 | [8 empty] | 4 | PM |  | Outside Compliance | 728 | MCM Not Yet Required

## BACOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXC | PDX55 | IEM | FRB: Upgrade Hanley BACOP to v4.1 | FRB |  |  | 19 |  | 2024-04-05 | 2024-02-10 | 2024-05-30 | Completed |  | 2024-04-05 | 2024-04-05 | [8 empty] | 5 | FRB |  | Past Compliance | -791
April | PDXC | PDX55 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 8 |  | 2024-04-05 | 2024-02-10 | 2024-05-30 | Completed |  | 2024-04-05 | 2024-04-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -791
April | PDXC | PDX178 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2024-04-23 | 2024-02-28 | 2024-06-17 | Completed |  | 2024-04-23 | 2024-04-23 | [8 empty] | 5 | SRVY |  | Past Compliance | -773
May | PDXC | PDX93 | IEM | BACOP 12m SOP | FPM |  |  | 10 |  | 2024-05-03 | 2024-03-09 | 2024-06-27 | Completed |  | 2024-05-03 | 2024-05-03 | [8 empty] | 5 | FPM |  | Past Compliance | -763
May | PDXC | PDX55 | IEM | BACOP 12M PM SOP | PR |  |  | 1 |  | 2024-05-05 | 2024-03-11 | 2024-06-29 | Completed |  | 2024-05-05 | 2024-05-05 | [8 empty] | 5 | PR |  | Past Compliance | -761
May | PDXC | PDX179 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2024-05-15 | 2024-03-21 | 2024-07-09 | Completed |  | 2024-05-15 | 2024-05-15 | [8 empty] | 5 | SRVY |  | Past Compliance | -751
May | PDXC | PDX55 | IEM | FRB: Upgrade FUJI SMBE BACOP to v4.1 | FRB |  |  | 12 |  | 2024-05-15 | 2024-03-21 | 2024-07-09 | Completed |  | 2024-05-15 | 2024-05-15 | [8 empty] | 5 | FRB |  | Past Compliance | -751
May | PDXC | PDX52 | IEM | BACOP Branch Circuit Install HUPP | PR |  |  | 6 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 5 | PR |  | Past Compliance | -750
May | PDXC | PDX92 | IEM | PDX92 BACOP 2.3A HMI Replacment | CM |  |  | 2 |  | 2024-05-17 | 2024-03-23 | 2024-07-11 | Completed |  | 2024-05-17 | 2024-05-17 | [8 empty] | 5 | CM |  | Past Compliance | -749
June | PDXC | PDX179 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2024-06-11 | 2024-04-17 | 2024-08-05 | Completed |  | 2024-06-11 | 2024-06-11 | [8 empty] | 5 | SRVY |  | Past Compliance | -724
June | PDXC | PDX178 | IEM | FRB: Identify BACOPs with Janitza UMG 604-PRO meters not separately in EAM | SRVY |  |  | 8 |  | 2024-06-17 | 2024-04-23 | 2024-08-11 | Completed |  | 2024-06-17 | 2024-06-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -718
June | PDXC | PDX178 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-06-17 | 2024-04-23 | 2024-08-11 | Completed |  | 2024-06-17 | 2024-06-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -718
July | PDXC | PDX55 | IEM | BACOP 4A Battery Replacment | CM |  |  | 2 |  | 2024-07-15 | 2024-05-21 | 2024-09-08 | Completed |  | 2024-07-15 | 2024-07-15 | [8 empty] | 5 | CM |  | Past Compliance | -690
July | PDXC | PDX179 | IEM | FRB: Upgrade Cyber Sciences SER-3200 in IEM BACOP to v2.23 | FRB |  |  | 15 |  | 2024-07-16 | 2024-05-22 | 2024-09-09 | Completed |  | 2024-07-16 | 2024-07-16 | [8 empty] | 5 | FRB |  | Past Compliance | -689
July | PDXC | PDX90 | IEM | PDX91 BACOP Shunt Tripped TOB Installation | CM |  |  | 1 |  | 2024-07-29 | 2024-06-04 | 2024-09-22 | Completed |  | 2024-07-29 | 2024-07-29 | [8 empty] | 5 | CM |  | Past Compliance | -676
July | PDXC | PDX91 | IEM | PDX91 BACOP Shunt Tripped TOB Installation 4A2 | CM |  |  | 2 |  | 2024-07-30 | 2024-06-05 | 2024-09-23 | Completed |  | 2024-07-30 | 2024-07-30 | [8 empty] | 5 | CM |  | Past Compliance | -675
August | PDXC | PDX92 | IEM | bacop shunt trip | CM |  |  | 1 |  | 2024-08-01 | 2024-06-07 | 2024-09-25 | Completed |  | 2024-08-01 | 2024-08-01 | [8 empty] | 5 | CM |  | Past Compliance | -673
August | PDXC | PDX178 | IEM | FRB: Identify BACOPs with Janitza UMG 604-PRO meters not separately in EAM | SRVY |  |  | 22 |  | 2024-08-03 | 2024-06-09 | 2024-09-27 | Completed |  | 2024-08-03 | 2024-08-03 | [8 empty] | 3 | SRVY |  | Past Compliance | -671
August | PDXC | PDX91 | IEM | PDX91 BACOP Shunt Tripped TOB Installation 5B1 | CM |  |  | 2 |  | 2024-08-08 | 2024-06-14 | 2024-10-02 | Completed |  | 2024-08-08 | 2024-08-08 | [8 empty] | 5 | CM |  | Past Compliance | -666
August | PDXC | PDX178 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 11 |  | 2024-08-09 | 2024-06-15 | 2024-10-03 | Completed |  | 2024-08-09 | 2024-08-09 | [8 empty] | 5 | SRVY |  | Past Compliance | -665
August | PDXC | PDX179 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 9 |  | 2024-08-09 | 2024-06-15 | 2024-10-03 | Completed |  | 2024-08-09 | 2024-08-09 | [8 empty] | 5 | SRVY |  | Past Compliance | -665
September | PDXC | PDX90 | IEM | FRB: Upgrade Cyber Sciences SER-3200 in Hanley BACOP to v2.23 | FRB |  |  | 7 |  | 2024-09-05 | 2024-07-12 | 2024-10-30 | Completed |  | 2024-09-05 | 2024-09-05 | [8 empty] | 5 | FRB |  | Past Compliance | -638
September | PDXC | PDX90 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2024-09-05 | 2024-07-12 | 2024-10-30 | Completed |  | 2024-09-05 | 2024-09-05 | [8 empty] | 3 | SRVY |  | Past Compliance | -638
September | PDXC | PDX179 | IEM | Vendor Troubleshoot Stratix Switch Fault in BACOP 2.1B | CM |  |  | 4 |  | 2024-09-06 | 2024-07-13 | 2024-10-31 | Completed |  | 2024-09-06 | 2024-09-06 | [8 empty] | 5 | CM |  | Past Compliance | -637
October | PDXC | PDX93 | IEM | Bacop 2.1A | CM |  |  | 1 |  | 2024-10-09 | 2024-08-15 | 2024-12-03 | Completed |  | 2024-10-09 | 2024-10-09 | [8 empty] | 5 | CM |  | Past Compliance | -604
October | PDXC | PDX179 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2024-10-10 | 2024-08-16 | 2024-12-04 | Completed |  | 2024-10-10 | 2024-10-10 | [8 empty] | 5 | SRVY |  | Past Compliance | -603
October | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-10-25 | 2024-08-31 | 2024-12-19 | Completed |  | 2024-10-25 | 2024-10-25 | [8 empty] | 3 | SRVY |  | Past Compliance | -588
November | PDXC | PDX180 | IEM | FRB: Upgrade Cyber Sciences SER-3200 in Hanley BACOP to v2.23 | FRB |  |  | 27 |  | 2024-11-01 09:26 | 2024-09-07 | 2024-12-26 | Completed |  | 2024-11-01 09:26 | 2024-11-01 09:26 | [8 empty] | 5 | FRB |  | Past Compliance | -580
November | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-11-06 | 2024-09-12 | 2024-12-31 | Completed |  | 2024-11-06 | 2024-11-06 | [8 empty] | 3 | SRVY |  | Past Compliance | -576
November | PDXC | PDX179 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2024-11-20 | 2024-09-26 | 2025-01-14 | Completed |  | 2024-11-20 | 2024-11-20 | [8 empty] | 3 | SRVY |  | Past Compliance | -562
December | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-12-11 | 2024-10-17 | 2025-02-04 | Completed |  | 2024-12-11 | 2024-12-11 | [8 empty] | 3 | SRVY |  | Past Compliance | -541
December | PDXC | PDX92 | IEM | 2.2B Bacop DIM Communication Restricted | CM |  |  | 1 |  | 2024-12-28 | 2024-11-03 | 2025-02-21 | Completed |  | 2024-12-28 | 2024-12-28 | [8 empty] | 5 | CM |  | Past Compliance | -524
January | PDXC | PDX92 | IEM | BACOP 1.6B Communication Fault | CM |  |  | 1 |  | 2025-01-03 | 2024-11-09 | 2025-02-27 | Completed |  | 2025-01-03 | 2025-01-03 | [8 empty] | 5 | CM |  | Past Compliance | -518
January | PDXC | PDX93 | IEM | Bacop 2.6B troubleshoot/repair | CM |  |  | 2 |  | 2025-01-10 | 2024-11-16 | 2025-03-06 | Completed |  | 2025-01-10 | 2025-01-10 | [8 empty] | 5 | CM |  | Past Compliance | -511
January | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-01-17 | 2024-11-23 | 2025-03-13 | Completed |  | 2025-01-17 | 2025-01-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -504
January | PDXC | PDX90 | IEM | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 28 |  | 2025-01-23 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 | 2025-01-23 | [8 empty] | 5 | FSB |  | Past Compliance | -498
January | PDXC | PDX91 | IEM | FSB: Update BACOP Level 1 Pre-Caution/Caution settings at JITWMW sites | FSB |  |  | 36 |  | 2025-01-23 12:08 | 2024-11-29 | 2025-03-19 | Completed |  | 2025-01-23 12:08 | 2025-01-23 12:08 | [8 empty] | 5 | FSB |  | Past Compliance | -497
February | PDXC | PDX181 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 7 |  | 2025-02-04 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 | 2025-02-04 | [8 empty] | 5 | SRVY |  | Past Compliance | -486
February | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-02-17 | 2024-12-24 | 2025-04-13 | Completed |  | 2025-02-17 | 2025-02-17 | [8 empty] | 3 | SRVY |  | Past Compliance | -473
February | PDXC | PDX92 | IEM | DLR Fault 1.6B BACOP | CM |  |  | 1 |  | 2025-02-28 | 2025-01-04 | 2025-04-24 | Completed |  | 2025-02-28 | 2025-02-28 | [8 empty] | 5 | CM |  | Past Compliance | -462
March | PDXC | PDX58 | IEM | BACOP Shunt Trip Initial Response Policy | PR |  |  | 1 |  | 2025-03-15 | 2025-01-19 | 2025-05-09 | Completed |  | 2025-03-15 | 2025-03-15 | [8 empty] | 5 | PR |  | Past Compliance | -447
March | PDXC | PDX93 | IEM | Bacop 1.2A troubleshot | CM |  |  | 1 |  | 2025-03-29 | 2025-02-02 | 2025-05-23 | Completed |  | 2025-03-29 | 2025-03-29 | [8 empty] | 5 | CM |  | Past Compliance | -433
April | PDXC | PDX180 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-04-02 | 2025-02-06 | 2025-05-27 | Completed |  | 2025-04-02 | 2025-04-02 | [8 empty] | 3 | SRVY |  | Past Compliance | -429
April | PDXC | PDX181 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 7 |  | 2025-04-24 | 2025-02-28 | 2025-06-18 | Completed |  | 2025-04-24 | 2025-04-24 | [8 empty] | 3 | SRVY |  | Past Compliance | -407
May | PDXC | PDX91 | IEM | BACOP 4A Janitza Meter and CT's T-1 | CM |  |  | 1 |  | 2025-05-19 | 2025-03-25 | 2025-07-13 | Completed |  | 2025-05-19 | 2025-05-19 | [8 empty] | 5 | CM |  | Past Compliance | -382
June | PDXC | PDX181 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 9 |  | 2025-06-04 | 2025-04-10 | 2025-07-29 | Completed |  | 2025-06-04 | 2025-06-04 | [8 empty] | 5 | SRVY |  | Past Compliance | -366
June | PDXC | PDX180 | IEM | Troubleshoot of BACOP 2.1B | CM |  |  | 3 |  | 2025-06-06 | 2025-04-12 | 2025-07-31 | Completed |  | 2025-06-06 | 2025-06-06 | [8 empty] | 4 | CM |  | Past Compliance | -364
June | PDXC | PDX93 | IEM | BACOP 1.2A Troubleshooting/Repair | CM |  |  | 1 |  | 2025-06-07 | 2025-04-13 | 2025-08-01 | Open |  | 2025-06-07 | 2025-06-07 | [8 empty] | 5 | CM |  | Past Compliance | -363 | MCM OVERDUE
June | PDXC | PDX178 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX179 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 11:03 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:03 | 2025-06-13 11:03 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXC | PDX180 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX55 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 10 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX58 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 9 |  | 2025-06-13 11:26 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:26 | 2025-06-13 11:26 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXC | PDX61 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 8 |  | 2025-06-13 11:30 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 11:30 | 2025-06-13 11:30 | [8 empty] | 3 | SRVY |  | Past Compliance | -356
June | PDXC | PDX90 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 7 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX91 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 15 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX92 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXC | PDX93 | IEM | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
July | PDXC | PDX181 | IEM | Does this IEM BACOP contain a Cyber Sciences SER-3200 family SER? | SRVY |  |  | 5 |  | 2025-07-03 | 2025-05-09 | 2025-08-27 | Completed |  | 2025-07-03 | 2025-07-03 | [8 empty] | 5 | SRVY |  | Past Compliance | -337
July | PDXC | PDX61 | IEM | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 6 |  | 2025-07-18 | 2025-05-24 | 2025-09-11 | Completed |  | 2025-07-18 | 2025-07-18 | [8 empty] | 3 | SRVY |  | Past Compliance | -322
July | PDXC | PDX61 | IEM | FRB: Upgrade Cyber Sciences SER-3200 in Hanley BACOP to v2.23 | FRB |  |  | 20 |  | 2025-07-22 | 2025-05-28 | 2025-09-15 | Open |  | 2025-07-22 | 2025-07-22 | [8 empty] | 5 | FRB |  | Past Compliance | -318 | MCM OVERDUE
August | PDXC | PDX178 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 51 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXC | PDX179 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 24 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXC | PDX181 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 25 |  | 2025-08-11 22:57 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 22:57 | 2025-08-11 22:57 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXC | PDX55 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 22 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXC | PDX58 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 21 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXC | PDX61 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 26 |  | 2025-08-11 23:37 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 23:37 | 2025-08-11 23:37 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXC | PDX90 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 28 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXC | PDX91 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 36 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXC | PDX92 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 43 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXC | PDX93 | IEM | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 6 |  | 2025-08-11 23:38 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 23:38 | 2025-08-11 23:38 | [8 empty] | 5 | FRB |  | Past Compliance | -297
August | PDXC | PDX178 | IEM | Trouble shoot and correct BACOP 2.1 with vendor | CM |  |  | 1 |  | 2025-08-27 | 2025-07-03 | 2025-10-21 | Completed |  | 2025-08-27 | 2025-08-27 | [8 empty] | 5 | CM |  | Past Compliance | -282
September | PDXC | PDX178 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX179 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX180 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX181 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX55 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX58 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX61 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX90 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX91 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX92 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX93 | IEM | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXC | PDX58 | IEM | Bacop 2a powercycle of bob4 | CM |  |  | 2 |  | 2025-09-08 | 2025-07-15 | 2025-11-02 | Completed |  | 2025-09-08 | 2025-09-08 | [8 empty] | 5 | CM |  | Past Compliance | -270
October | PDXC | PDX61 | IEM | BACOP 2A Troubleshoot and Repair | CM |  |  | 1 |  | 2025-10-06 | 2025-08-12 | 2025-11-30 | Completed | MCM-132952741 | 2025-10-06 | 2025-10-06 |  |  | Complete | Tier 2 | grstef | 2025-12-15 14:00 | 2026-01-10 02:00 | Successful | 4 | CM |  | Past Compliance | -242 | MCM Complete
October | PDXC | PDX180 | IEM | BACOP 1.2B HMI to PLC Connection Failure | CM |  |  | 1 |  | 2025-10-13 | 2025-08-19 | 2025-12-07 | Completed | MCM-139726947 | 2025-10-13 | 2025-10-13 |  |  | Complete | Tier 3 | ernlealf | 2025-12-09 08:00 | 2026-01-09 07:59 | Successful | 5 | CM |  | Past Compliance | -235 | MCM Complete
October | PDXC | PDX93 | IEM | BACOP 2.3B Troubleshooting/repair | CM |  |  | 1 |  | 2025-10-20 | 2025-08-26 | 2025-12-14 | Completed |  | 2025-10-20 | 2025-10-20 | [8 empty] | 5 | CM |  | Past Compliance | -228
November | PDXC | PDX93 | IEM | PDX93 BACOP 2.1A Busway Totals not Matching Main Meter, Shunt Trips Inhibited | CM |  |  | 1 |  | 2025-11-03 | 2025-09-09 | 2025-12-28 | Completed |  | 2025-11-03 | 2025-11-03 | [8 empty] | 5 | CM |  | Past Compliance | -214
November | PDXC | PDX181 | IEM | PDX 181 Bacop V4.2 Firmware Update | CM |  |  | 1 |  | 2025-11-10 | 2025-09-16 | 2026-01-04 | Completed | MCM-141065396 | 2025-11-10 | 2025-11-10 |  |  | Complete | Tier 3 | aaolaniy | 2026-01-05 08:00 | 2026-02-04 07:55 | Successful | 5 | CM |  | Past Compliance | -207 | MCM Complete
January | PDXC | PDX92 | IEM | BACOP 1.1B Troubleshooting/repair | CM |  |  | 3 |  | 2026-01-28 | 2025-12-04 | 2026-03-24 | Completed | MCM-143351588 | 2026-01-28 | 2026-01-28 |  |  | Complete | Tier 2 | stayroa | 2026-02-26 14:00 | 2026-03-26 01:00 | Successful | 5 | CM |  | Past Compliance | -128 | MCM Complete

## 90 Day Outlook
Site | Description | Metrics (WO/Building) | Upgrades Needed? | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM Scheduled Start Date | MCM Scheduled End Date | MCM/TT | Vendor Start Date | Vendor End Date | Site Confirmation | MCM Gap Status
PDX97 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | No | 2026-08-01 | 2026-06-07 | 2026-09-25 | MCM Needed (<60d) | [6 empty] | MCM Needed (<60d)
PDX58 | [GLOBAL] AMCOP 36M PM V1.0 | 5 | No | 2026-09-09 | 2026-07-16 | 2026-11-03 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)
PDX55 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 1 | Yes | 2026-10-01 | 2026-08-07 | 2026-11-25 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)