## AMCOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
May | PDXS | PDX80 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 4 |  | 2022-05-05 | 2022-03-11 | 2022-06-29 | Completed |  | 2022-05-05 | 2022-05-05 | [8 empty] | 3 | PM |  | Past Compliance | -1492
July | PDXS | PDX80 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 18 |  | 2023-07-30 | 2023-06-05 | 2023-09-23 | Completed |  | 2023-07-30 | 2023-07-30 | [8 empty] | 3 | PM |  | Past Compliance | -1041
August | PDXS | PDX98 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2023-08-01 | 2023-06-07 | 2023-09-25 | Completed |  | 2023-08-01 | 2023-08-01 | [8 empty] | 3 | PM |  | Past Compliance | -1039
January | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2024-01-17 | 2023-11-23 | 2024-03-12 | Cancelled |  | 2024-01-17 | 2024-01-17 | [8 empty] | 3 | PM |  | Past Compliance | -870
June | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 9 |  | 2024-06-14 | 2024-04-20 | 2024-08-08 | Completed |  | 2024-06-14 | 2024-06-14 | [8 empty] | 3 | PM |  | Past Compliance | -721
January | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 4 |  | 2025-01-11 | 2024-11-17 | 2025-03-07 | Completed |  | 2025-01-11 | 2025-01-11 | [8 empty] | 3 | PM |  | Past Compliance | -510
May | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-05-10 | 2025-03-16 | 2025-07-04 | Completed |  | 2025-05-10 | 2025-05-10 | [8 empty] | 3 | PM |  | Past Compliance | -391
June | PDXS | PDX138 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 3 |  | 2025-06-20 | 2025-04-26 | 2025-08-14 | Cancelled |  | 2025-06-20 | 2025-06-20 | [8 empty] | 3 | PM |  | Past Compliance | -350
July | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Completed |  | 2025-07-11 | 2025-07-11 | [8 empty] | 3 | PM |  | Past Compliance | -329
August | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-08-08 | 2025-06-14 | 2025-10-02 | Completed |  | 2025-08-08 | 2025-08-08 | [8 empty] | 3 | PM |  | Past Compliance | -301
October | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 17 |  | 2025-10-03 | 2025-08-09 | 2025-11-27 | Completed | MCM-132741396 | 2025-10-03 | 2025-10-03 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 3 | PM |  | Past Compliance | -245 | MCM Complete
December | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-12-12 | 2025-10-18 | 2026-02-05 | Completed | MCM-132741396 | 2025-12-12 | 2025-12-12 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 3 | PM |  | Past Compliance | -175 | MCM Complete
December | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2025-12-27 | 2025-11-02 | 2026-02-20 | Completed | MCM-132486241 | 2025-12-27 | 2025-12-27 |  |  | Complete | Tier 2 | arerafat | 2026-02-09 14:00 | 2026-03-12 06:59 | Successful | 3 | PM |  | Past Compliance | -160 | MCM Complete
June | PDXS | PDX140 | Interstates | [GLOBAL] AMCOP MK2 72M PM | PPM | G.CNTRL.AMCOP2 | 72 | 21 |  | 2026-06-01 | 2025-12-03 | 2026-11-28 | Cancelled | MCM-147851160 | 2026-06-01 | 2026-06-01 |  |  | Scheduled | Tier 3 | jesuogo | 2026-06-02 04:00 | 2026-06-16 06:55 |  | 4 | PM |  | Within Compliance | -4
January | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2026-01-30 | 2025-12-06 | 2026-03-26 | Completed | MCM-132741396 | 2026-01-30 | 2026-01-30 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 3 | PM |  | Past Compliance | -126 | MCM Complete
March | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 6 |  | 2026-03-24 | 2026-01-28 | 2026-05-18 | Completed | MCM-146713404 | 2026-03-24 | 2026-03-24 |  |  | Scheduled | Tier 2 | rollispa | 2026-06-08 07:00 | 2026-07-09 06:59 |  | 3 | PM |  | Past Compliance | -73
April | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2026-04-24 | 2026-02-28 | 2026-06-18 | Cancelled | MCM-146713404 | 2026-04-24 | 2026-04-24 |  |  | Scheduled | Tier 2 | rollispa | 2026-06-08 07:00 | 2026-07-09 06:59 |  | 3 | PM |  | Within Compliance | -42
May | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 6 |  | 2026-05-15 | 2026-03-21 | 2026-07-09 | Open | MCM-150801576 | 2026-05-15 | 2026-05-15 |  |  | Pending Approval | Tier 2 | coombsja | 2026-06-18 07:00 | 2026-08-12 06:55 |  | 3 | PM |  | Within Compliance | -21 | MCM Pending Approval
May | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2026-05-31 | 2026-04-06 | 2026-07-25 | Cancelled | MCM-146713404 | 2026-05-31 | 2026-05-31 |  |  | Scheduled | Tier 2 | rollispa | 2026-06-08 07:00 | 2026-07-09 06:59 |  | 3 | PM |  | Within Compliance | -5
June | PDXS | PDX82 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2026-06-23 | 2026-04-29 | 2026-08-17 | Cancelled | MCM-146713404 | 2026-06-23 | 2026-06-23 |  |  | Scheduled | Tier 2 | rollispa | 2026-06-08 07:00 | 2026-07-09 06:59 |  | 3 | PM |  | Within Compliance | 18
July | PDXS | PDX80 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 20 |  | 2026-07-30 | 2026-06-05 | 2026-09-23 | Open | MCM-151427924 | 2026-07-30 | 2026-07-30 |  |  | Pending Approval | Tier 2 | jpiel | 2026-06-17 07:00 | 2026-07-18 06:55 |  | 3 | PM |  | Outside Compliance | 55 | MCM Pending Approval
August | PDXS | PDX98 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-08-01 | 2026-06-07 | 2026-09-25 | Open | MCM-151429971 | 2026-08-01 | 2026-08-01 |  |  | Pending Approval | Tier 2 | jpiel | 2026-06-17 07:00 | 2026-07-18 06:55 |  | 3 | PM |  | Outside Compliance | 57 | MCM Pending Approval
August | PDXS | PDX83 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 9 |  | 2026-08-07 | 2026-06-13 | 2026-10-01 | Open |  | 2026-08-07 | 2026-08-07 | [8 empty] | 3 | PM |  | Outside Compliance | 63 | MCM Needed (<90d)
September | PDXS | PDX83 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 1 |  | 2026-09-18 | 2026-07-25 | 2026-11-12 | Open |  | 2026-09-18 | 2026-09-18 | [8 empty] | 3 | PM |  | Outside Compliance | 105 | MCM Not Yet Required
January | PDXS | PDX83 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2027-01-22 | 2026-11-28 | 2027-03-18 | Open |  | 2027-01-22 | 2027-01-22 | [8 empty] | 3 | PM |  | Outside Compliance | 231 | MCM Not Yet Required
January | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 4 |  | 2028-01-11 | 2027-11-17 | 2028-03-06 | Open |  | 2028-01-11 | 2028-01-11 | [8 empty] | 3 | PM |  | Outside Compliance | 585 | MCM Not Yet Required
May | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2028-05-10 | 2028-03-16 | 2028-07-04 | Open |  | 2028-05-10 | 2028-05-10 | [8 empty] | 3 | PM |  | Outside Compliance | 705 | MCM Not Yet Required
July | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2028-07-11 | 2028-05-17 | 2028-09-04 | Open |  | 2028-07-11 | 2028-07-11 | [8 empty] | 3 | PM |  | Outside Compliance | 767 | MCM Not Yet Required
August | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | PPM | G.AMCOP.36M | 36M | 2 |  | 2028-08-08 | 2028-06-14 | 2028-10-02 | Open |  | 2028-08-08 | 2028-08-08 | [8 empty] | 3 | PM |  | Outside Compliance | 795 | MCM Not Yet Required

## AMCOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXS | PDX607 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXS | PDX80 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 18 |  | 2024-04-26 19:32 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:32 | 2024-04-26 19:32 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXS | PDX81 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXS | PDX82 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 19:33 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 19:33 | 2024-04-26 19:33 | [8 empty] | 3 | FSB |  | Past Compliance | -769
April | PDXS | PDX83 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 27 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
April | PDXS | PDX98 | Interstates | FSB: AMCOP Generator Crank Fail Timer Setting Change | FSB |  |  | 1 |  | 2024-04-26 | 2024-03-02 | 2024-06-20 | Completed |  | 2024-04-26 | 2024-04-26 | [8 empty] | 3 | FSB |  | Past Compliance | -770
May | PDXS | PDX82 | Interstates | AMCOP 2.3B Beacon Light Troubleshoot and Repair | CM |  |  | 1 |  | 2024-05-03 | 2024-03-09 | 2024-06-27 | Completed |  | 2024-05-03 | 2024-05-03 | [8 empty] | 5 | CM |  | Past Compliance | -763
May | PDXS | PDX83 | Interstates | AMCOP UPS Battery Wiring Replacement 1.1B | CM |  |  | 1 |  | 2024-05-08 | 2024-03-14 | 2024-07-02 | Completed |  | 2024-05-08 | 2024-05-08 | [8 empty] | 5 | CM |  | Past Compliance | -758
May | PDXS | PDX607 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXS | PDX80 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 18 |  | 2024-05-16 07:00 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 07:00 | 2024-05-16 07:00 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXS | PDX81 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXS | PDX82 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXS | PDX83 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 27 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
May | PDXS | PDX98 | Interstates | FSB: Update AMCOP settings to align with revised Q4 2023 changes (rev 3) | FSB |  |  | 1 |  | 2024-05-16 | 2024-03-22 | 2024-07-10 | Completed |  | 2024-05-16 | 2024-05-16 | [8 empty] | 3 | FSB |  | Past Compliance | -750
June | PDXS | PDX82 | Interstates | AMCOP 2.3B Beacon Light Troubleshoot and Repair | CM |  |  | 2 |  | 2024-06-03 | 2024-04-09 | 2024-07-28 | Completed |  | 2024-06-03 | 2024-06-03 | [8 empty] | 5 | CM |  | Past Compliance | -732
June | PDXS | PDX83 | Interstates | AMCOP UPS Battery Wiring Replacement 2.1B | CM |  |  | 2 |  | 2024-06-12 | 2024-04-18 | 2024-08-06 | Completed |  | 2024-06-12 | 2024-06-12 | [8 empty] | 5 | CM |  | Past Compliance | -723
July | PDXS | PDX138 | Interstates | AMCOP 1.2A and AMCOP 1.2B Conduit Rework | CM |  |  | 1 |  | 2024-07-16 | 2024-05-22 | 2024-09-09 | Completed |  | 2024-07-16 | 2024-07-16 | [8 empty] | 5 | CM |  | Past Compliance | -689
July | PDXS | PDX138 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 7 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXS | PDX607 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 18:08 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 18:08 | 2024-07-23 18:08 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXS | PDX80 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 18 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXS | PDX81 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:12 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:12 | 2024-07-23 16:12 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXS | PDX82 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
July | PDXS | PDX83 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 27 |  | 2024-07-23 16:13 | 2024-05-29 | 2024-09-16 | Cancelled |  | 2024-07-23 16:13 | 2024-07-23 16:13 | [8 empty] | 4 | FSB |  | Past Compliance | -681
July | PDXS | PDX98 | Interstates | FSB: AMCOP enclosure sealant application | FSB |  |  | 1 |  | 2024-07-23 | 2024-05-29 | 2024-09-16 | Completed |  | 2024-07-23 | 2024-07-23 | [8 empty] | 4 | FSB |  | Past Compliance | -682
August | PDXS | PDX138 | Interstates | FRB: Update AMCOP to V4.0 | FRB |  |  | 20 |  | 2024-08-03 | 2024-06-09 | 2024-09-27 | Completed |  | 2024-08-03 | 2024-08-03 | [8 empty] | 5 | FRB |  | Past Compliance | -671
August | PDXS | PDX82 | Interstates | AMCOP 2.3A Battery Alarm Troubleshooting | CM |  |  | 4 |  | 2024-08-15 | 2024-06-21 | 2024-10-09 | Completed |  | 2024-08-15 | 2024-08-15 | [8 empty] | 5 | CM |  | Past Compliance | -659
September | PDXS | PDX138 | Interstates | FSB: Inspect for and remove AMCOP-CUPS interconnect wiring at OPTDC sites | FSB |  |  | 19 |  | 2024-09-03 | 2024-07-10 | 2024-10-28 | Completed |  | 2024-09-03 | 2024-09-03 | [8 empty] | 3 | FSB |  | Past Compliance | -640
September | PDXS | PDX83 | Interstates | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 16 |  | 2024-09-18 | 2024-07-25 | 2024-11-12 | Completed |  | 2024-09-18 | 2024-09-18 | [8 empty] | 3 | FSB |  | Past Compliance | -625
September | PDXS | PDX83 | Interstates | AMCOP Battery Power Supply Setting Change | CM |  |  | 5 |  | 2024-09-20 | 2024-07-27 | 2024-11-14 | Completed |  | 2024-09-20 | 2024-09-20 | [8 empty] | 5 | CM |  | Past Compliance | -623
October | PDXS | PDX83 | Interstates | FSB: MEDS UMG 512-PRO AMCOP Polarity Correction | FSB |  |  | 10 |  | 2024-10-01 | 2024-08-07 | 2024-11-25 | Completed |  | 2024-10-01 | 2024-10-01 | [8 empty] | 3 | FSB |  | Past Compliance | -612
November | PDXS | PDX607 | Interstates | PDX607 AMCOP Settings Update | CM |  |  | 1 |  | 2024-11-23 | 2024-09-29 | 2025-01-17 | Completed |  | 2024-11-23 | 2024-11-23 | [8 empty] | 5 | CM |  | Past Compliance | -559
November | PDXS | PDX81 | Interstates | Amcop Settings Update 1.1C | CM |  |  | 1 |  | 2024-11-25 | 2024-10-01 | 2025-01-19 | Completed |  | 2024-11-25 | 2024-11-25 | [8 empty] | 5 | CM |  | Past Compliance | -557
December | PDXS | PDX138 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 17 |  | 2024-12-03 | 2024-10-09 | 2025-01-27 | Completed |  | 2024-12-03 | 2024-12-03 | [8 empty] | 3 | FSB |  | Past Compliance | -549
December | PDXS | PDX83 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 1 |  | 2024-12-16 | 2024-10-22 | 2025-02-09 | Completed |  | 2024-12-16 | 2024-12-16 | [8 empty] | 3 | FSB |  | Past Compliance | -536
December | PDXS | PDX82 | Interstates | AMCOP 1.4A watchdog alarm | CM |  |  | 1 |  | 2024-12-27 | 2024-11-02 | 2025-02-20 | Completed |  | 2024-12-27 | 2024-12-27 | [8 empty] | 5 | CM |  | Past Compliance | -525
January | PDXS | PDX81 | Interstates | AMCOP 1.2A HMI Fault | CM |  |  | 2 |  | 2025-01-09 | 2024-11-15 | 2025-03-05 | Completed |  | 2025-01-09 | 2025-01-09 | [8 empty] | 5 | CM |  | Past Compliance | -512
January | PDXS | PDX138 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 54 |  | 2025-01-11 09:30 | 2024-11-17 | 2025-03-07 | Completed |  | 2025-01-11 09:30 | 2025-01-11 09:30 | [8 empty] | 3 | FSB |  | Past Compliance | -509
January | PDXS | PDX607 | Interstates | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:30 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:30 | 2025-01-22 12:30 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXS | PDX80 | Interstates | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 18 |  | 2025-01-22 12:35 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:35 | 2025-01-22 12:35 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXS | PDX82 | Interstates | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:37 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:37 | 2025-01-22 12:37 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXS | PDX83 | Interstates | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 27 |  | 2025-01-22 12:37 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:37 | 2025-01-22 12:37 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXS | PDX98 | Interstates | FRB: Deploy firmware and hardware changes to AMCOP | FRB |  |  | 1 |  | 2025-01-22 12:40 | 2024-11-28 | 2025-03-18 | Cancelled |  | 2025-01-22 12:40 | 2025-01-22 12:40 | [8 empty] | 5 | FRB |  | Past Compliance | -498
January | PDXS | PDX81 | Interstates | PDX81 AMCOP Firmware Update | CM |  |  | 27 |  | 2025-01-27 | 2024-12-03 | 2025-03-23 | Completed |  | 2025-01-27 | 2025-01-27 | [8 empty] | 5 | CM |  | Past Compliance | -494
February | PDXS | PDX138 | Interstates | PDX138 AMCOP 2.1C AUTO FAIL | CM |  |  | 3 |  | 2025-02-04 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 | 2025-02-04 | [8 empty] | 5 | CM |  | Past Compliance | -486
February | PDXS | PDX81 | Interstates | AMCOP 2.5A Deadbus | CM |  |  | 1 |  | 2025-02-04 | 2024-12-11 | 2025-03-31 | Completed |  | 2025-02-04 | 2025-02-04 | [8 empty] | 5 | CM |  | Past Compliance | -486
February | PDXS | PDX138 | Interstates | AMCOP V5.0 Upgrade | CM |  |  | 23 |  | 2025-02-10 | 2024-12-17 | 2025-04-06 | Completed |  | 2025-02-10 | 2025-02-10 | [8 empty] | 5 | CM |  | Past Compliance | -480
February | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 44 |  | 2025-02-10 17:02 | 2024-12-17 | 2025-04-06 | Completed |  | 2025-02-10 17:02 | 2025-02-10 17:02 | [8 empty] | 3 | FSB |  | Past Compliance | -479
March | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 24 |  | 2025-03-04 09:56 | 2025-01-08 | 2025-04-28 | Completed |  | 2025-03-04 09:56 | 2025-03-04 09:56 | [8 empty] | 3 | FSB |  | Past Compliance | -457
March | PDXS | PDX80 | Interstates | Ingest pallet of AMCOP spares into inventory | FPM |  |  | 1 |  | 2025-03-29 | 2025-02-02 | 2025-05-23 | Completed |  | 2025-03-29 | 2025-03-29 | [8 empty] | 5 | FPM |  | Past Compliance | -433
March | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | FPM |  | 36 | 1 |  | 2025-03-31 | 2025-02-04 | 2025-05-25 | Completed |  | 2025-03-31 | 2025-03-31 | [8 empty] | 3 | FPM |  | Past Compliance | -431
April | PDXS | PDX138 | Interstates | AMCOP settings change for Rack less BBUs | CM |  |  | 2 |  | 2025-04-01 | 2025-02-05 | 2025-05-26 | Completed |  | 2025-04-01 | 2025-04-01 | [8 empty] | 5 | CM |  | Past Compliance | -430
April | PDXS | PDX80 | Interstates | PDX80 CST/PDX80 AMCOP 5B Watch dog alarm | CM |  |  | 2 |  | 2025-04-05 | 2025-02-09 | 2025-05-30 | Completed |  | 2025-04-05 | 2025-04-05 | [8 empty] | 5 | CM |  | Past Compliance | -426
April | PDXS | PDX138 | Interstates | AMCOP 5.0 Firmware Update | CM |  |  | 1 |  | 2025-04-12 | 2025-02-16 | 2025-06-06 | Cancelled |  | 2025-04-12 | 2025-04-12 | [8 empty] | 5 | CM |  | Past Compliance | -419
April | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 23 |  | 2025-04-28 11:59 | 2025-03-04 | 2025-06-22 | Completed |  | 2025-04-28 11:59 | 2025-04-28 11:59 | [8 empty] | 3 | FSB |  | Past Compliance | -402
May | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 24 |  | 2025-05-06 09:55 | 2025-03-12 | 2025-06-30 | Completed |  | 2025-05-06 09:55 | 2025-05-06 09:55 | [8 empty] | 3 | FSB |  | Past Compliance | -394
May | PDXS | PDX138 | Interstates | FSB: Update AMCOP Settings for BBU-Less OPTDC Lineups | FSB |  |  | 27 |  | 2025-05-12 09:06 | 2025-03-18 | 2025-07-06 | Completed |  | 2025-05-12 09:06 | 2025-05-12 09:06 | [8 empty] | 2 | FSB |  | Past Compliance | -388
June | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 12 |  | 2025-06-11 10:56 | 2025-04-17 | 2025-08-05 | Completed |  | 2025-06-11 10:56 | 2025-06-11 10:56 | [8 empty] | 3 | FSB |  | Past Compliance | -358
June | PDXS | PDX140 | Interstates | Amcop V6 TImer Updates | CM |  |  | 1 |  | 2025-06-30 | 2025-05-06 | 2025-08-24 | Completed |  | 2025-06-30 | 2025-06-30 | [8 empty] | 5 | CM |  | Past Compliance | -340
July | PDXS | PDX140 | Interstates | PDX140/AMCOP MK2 Software Update | CM |  |  | 1 |  | 2025-07-02 | 2025-05-08 | 2025-08-26 | Completed |  | 2025-07-02 | 2025-07-02 | [8 empty] | 5 | CM |  | Past Compliance | -338
July | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 21 |  | 2025-07-08 15:09 | 2025-05-14 | 2025-09-01 | Completed |  | 2025-07-08 15:09 | 2025-07-08 15:09 | [8 empty] | 3 | FSB |  | Past Compliance | -331
July | PDXS | PDX607 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXS | PDX80 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 18 |  | 2025-07-11 08:17 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:17 | 2025-07-11 08:17 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXS | PDX81 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 08:18 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:18 | 2025-07-11 08:18 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXS | PDX82 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 08:19 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 08:19 | 2025-07-11 08:19 | [8 empty] | 5 | FSB |  | Past Compliance | -328
July | PDXS | PDX83 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 27 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXS | PDX98 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | FSB |  |  | 1 |  | 2025-07-11 | 2025-05-17 | 2025-09-04 | Cancelled |  | 2025-07-11 | 2025-07-11 | [8 empty] | 5 | FSB |  | Past Compliance | -329
July | PDXS | PDX139 | Interstates | AMCOP Log Download | FPM |  |  | 1 |  | 2025-07-16 | 2025-05-22 | 2025-09-09 | Completed |  | 2025-07-16 | 2025-07-16 | [8 empty] | 5 | FPM |  | Past Compliance | -324
July | PDXS | PDX138 | Interstates | FRB: Upgrade CAT EMCP firmware to prevent loss of communication with AMCOP | FRB |  |  | 32 |  | 2025-07-21 11:16 | 2025-05-27 | 2025-09-14 | Completed |  | 2025-07-21 11:16 | 2025-07-21 11:16 | [8 empty] | 5 | FRB |  | Past Compliance | -318
July | PDXS | PDX140 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 4 |  | 2025-07-24 | 2025-05-30 | 2025-09-17 | Completed |  | 2025-07-24 | 2025-07-24 | [8 empty] | 3 | FSB |  | Past Compliance | -316
July | PDXS | PDX81 | Interstates | [GLOBAL] AMCOP 36M PM V1.0 | FPM |  |  | 5 |  | 2025-07-30 | 2025-06-05 | 2025-09-23 | Completed |  | 2025-07-30 | 2025-07-30 | [8 empty] | 3 | FPM |  | Past Compliance | -310
August | PDXS | PDX607 | Interstates | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXS | PDX98 | Interstates | FDN: No 2 second delay on AMCOP during Auto Fail Condition | FSB |  |  | 1 |  | 2025-08-14 | 2025-06-20 | 2025-10-08 | Completed |  | 2025-08-14 | 2025-08-14 | [8 empty] | 4 | FSB |  | Past Compliance | -295
August | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 2 |  | 2025-08-15 07:34 | 2025-06-21 | 2025-10-09 | Completed |  | 2025-08-15 07:34 | 2025-08-15 07:34 | [8 empty] | 3 | FSB |  | Past Compliance | -294
August | PDXS | PDX98 | Interstates | PDX98 AMCOP SER Wiring Validation | CM |  |  | 1 |  | 2025-08-25 | 2025-07-01 | 2025-10-19 | Completed |  | 2025-08-25 | 2025-08-25 | [8 empty] | 5 | CM |  | Past Compliance | -284
September | PDXS | PDX139 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 39 |  | 2025-09-05 08:14 | 2025-07-12 | 2025-10-30 | Completed |  | 2025-09-05 08:14 | 2025-09-05 08:14 | [8 empty] | 3 | FSB |  | Past Compliance | -272
September | PDXS | PDX81 | Interstates | AMCOP SER(BCD) PLC/IP Wiring Validation | CM |  |  | 1 |  | 2025-09-12 | 2025-07-19 | 2025-11-06 | Completed | MCM-138907258 | 2025-09-12 | 2025-09-12 |  |  | Cancelled | Tier 2 | alyszrea | 2025-12-08 13:00 | 2026-01-08 07:59 |  | 5 | CM |  | Past Compliance | -266 | MCM Cancelled — Resubmit
September | PDXS | PDX140 | Interstates | FSB: Increase settings on AMCOP Mk2 systems | FSB |  |  | 5 |  | 2025-09-16 | 2025-07-23 | 2025-11-10 | Completed |  | 2025-09-16 | 2025-09-16 | [8 empty] | 3 | FSB |  | Past Compliance | -262
September | PDXS | PDX138 | Interstates | AMCOP 1.3 Battery Troubleshoot/Repair | CM |  |  | 1 |  | 2025-09-21 | 2025-07-28 | 2025-11-15 | Completed |  | 2025-09-21 | 2025-09-21 | [8 empty] | 5 | CM |  | Past Compliance | -257
October | PDXS | PDX82 | Interstates | AMCOP SER wiring and IP validation | CM |  |  | 3 |  | 2025-10-10 | 2025-08-16 | 2025-12-04 | Completed | MCM-132741396 | 2025-10-10 | 2025-10-10 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 5 | CM |  | Past Compliance | -238 | MCM Complete
October | PDXS | PDX140 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 12 |  | 2025-10-14 09:16 | 2025-08-20 | 2025-12-08 | Completed | MCM-129577140 | 2025-10-14 09:16 | 2025-10-14 09:16 |  |  | Complete | Tier 2 | rbamos | 2025-12-23 14:00 | 2026-01-23 07:59 | Successful - Off Script | 3 | FSB |  | Past Compliance | -233 | MCM Complete
October | PDXS | PDX80 | Interstates | AMCOP 3B battery replacment | BRKD |  |  | 1 |  | 2025-10-31 | 2025-09-06 | 2025-12-25 | Completed | MCM-132792426 | 2025-10-31 | 2025-10-31 |  |  | Complete | Tier 2 | arerafat | 2026-01-28 14:00 | 2026-03-08 02:00 | Unsuccessful | 4 | BRKD |  | Past Compliance | -217 | MCM Complete
November | PDXS | PDX82 | Interstates | amcop 2.2A batt alarm | CM |  |  | 1 |  | 2025-11-04 | 2025-09-10 | 2025-12-29 | Completed | MCM-132741396 | 2025-11-04 | 2025-11-04 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 5 | CM |  | Past Compliance | -213 | MCM Complete
December | PDXS | PDX140 | Interstates | FSB: Increase settings on AMCOP Mk2 systems | FSB |  |  | 8 |  | 2025-12-15 | 2025-10-21 | 2026-02-08 | Completed | MCM-129577140 | 2025-12-15 | 2025-12-15 |  |  | Complete | Tier 2 | rbamos | 2025-12-23 14:00 | 2026-01-23 07:59 | Successful - Off Script | 3 | FSB |  | Past Compliance | -172 | MCM Complete
December | PDXS | PDX138 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-129557685 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | kasculbi | 2026-01-13 14:00 | 2026-02-13 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX607 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132794481 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | arerafat | 2026-01-05 14:00 | 2026-02-04 02:00 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX80 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 19 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132792426 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | arerafat | 2026-01-28 14:00 | 2026-03-08 02:00 | Unsuccessful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX81 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132486241 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | arerafat | 2026-02-09 14:00 | 2026-03-12 06:59 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX82 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 28 |  | 2025-12-23 14:49 | 2025-10-29 | 2026-02-16 | Completed | MCM-132741396 | 2025-12-23 14:49 | 2025-12-23 14:49 |  |  | Complete | Tier 2 | arerafat | 2025-12-29 08:00 | 2026-02-21 07:55 | Successful | 5 | FSB |  | Past Compliance | -163 | MCM Complete
December | PDXS | PDX83 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 29 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132412717 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | arerafat | 2026-02-02 08:00 | 2026-03-01 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX98 | Interstates | FSB: Perform AMCOP V6 upgrades | FSB |  |  | 2 |  | 2025-12-23 | 2025-10-29 | 2026-02-16 | Completed | MCM-132793696 | 2025-12-23 | 2025-12-23 |  |  | Complete | Tier 2 | arerafat | 2026-01-21 08:00 | 2026-02-01 07:55 | Successful | 5 | FSB |  | Past Compliance | -164 | MCM Complete
December | PDXS | PDX138 | Interstates | Correct AMCOP 1.1A Utility Source Loss Time Delay | CM |  |  | 1 |  | 2025-12-31 | 2025-11-06 | 2026-02-24 | Completed | MCM-129557685 | 2025-12-31 | 2025-12-31 |  |  | Complete | Tier 2 | kasculbi | 2026-01-13 14:00 | 2026-02-13 07:55 | Successful | 5 | CM |  | Past Compliance | -156 | MCM Complete
January | PDXS | PDX98 | Interstates | FSB: Perform firmware and hardware upgrades to AMCOP | PR |  |  | 1 |  | 2026-01-05 | 2025-11-11 | 2026-03-01 | Completed | MCM-132793696 | 2026-01-05 | 2026-01-05 |  |  | Complete | Tier 2 | arerafat | 2026-01-21 08:00 | 2026-02-01 07:55 | Successful | 5 | PR |  | Past Compliance | -151 | MCM Complete
January | PDXS | PDX83 | Interstates | AMCOP 1.2A Watchdog Alarm | BRKD |  |  | 1 |  | 2026-01-08 | 2025-11-14 | 2026-03-04 | Completed | MCM-132412717 | 2026-01-08 | 2026-01-08 |  |  | Complete | Tier 2 | arerafat | 2026-02-02 08:00 | 2026-03-01 07:55 | Successful | 5 | BRKD |  | Past Compliance | -148 | MCM Complete
January | PDXS | PDX140 | Interstates | FSB: Increase settings on AMCOP Mk2 systems | FSB |  |  | 27 |  | 2026-01-10 01:14 | 2025-11-16 | 2026-03-06 | Completed | MCM-140621972 | 2026-01-10 01:14 | 2026-01-10 01:14 |  |  | Complete | Tier 2 | bamxbam | 2026-01-14 08:00 | 2026-02-14 07:59 | Successful | 3 | FSB |  | Past Compliance | -146 | MCM Complete
January | PDXS | PDX80 | Interstates | AMCOP 7C alarms | CM |  |  | 13 |  | 2026-01-22 | 2025-11-28 | 2026-03-18 | Completed | MCM-132792426 | 2026-01-22 | 2026-01-22 |  |  | Complete | Tier 2 | arerafat | 2026-01-28 14:00 | 2026-03-08 02:00 | Unsuccessful | 5 | CM |  | Past Compliance | -134 | MCM Complete
January | PDXS | PDX139 | Interstates | FSB: Upgrade AMCOP Mk2 HMI from v10 to v11 | FSB |  |  | 27 |  | 2026-01-23 | 2025-11-29 | 2026-03-19 | Completed | MCM-139750713 | 2026-01-23 | 2026-01-23 |  |  | Complete | Tier 2 | auprice | 2026-02-11 08:00 | 2026-03-14 06:59 | Successful | 4 | FSB |  | Past Compliance | -133 | MCM Complete
February | PDXS | PDX245 | Interstates | FDN: Post FDN AMCOP Autofail Alarms for ABB Breakers | FSB |  |  | 9 |  | 2026-02-02 | 2025-12-09 | 2026-03-29 | Completed | MCM-145503464 | 2026-02-02 | 2026-02-02 |  |  | Cancelled | Tier 2 | alejpm | 2026-03-20 07:00 | 2026-04-16 06:55 |  | 3 | FSB |  | Past Compliance | -123 | MCM Cancelled — Resubmit

## BACOP Outlook
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
February | PDXS | PDX80 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2024-02-10 | 2023-12-17 | 2024-04-05 | Completed |  | 2024-02-10 | 2024-02-10 | [8 empty] | 4 | PM |  | Past Compliance | -846
May | PDXS | PDX81 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 18 |  | 2024-05-10 | 2024-03-16 | 2024-07-04 | Completed |  | 2024-05-10 | 2024-05-10 | [8 empty] | 4 | PM |  | Past Compliance | -756
November | PDXS | PDX80 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 1 |  | 2024-11-19 | 2024-09-25 | 2025-01-13 | Completed |  | 2024-11-19 | 2024-11-19 | [8 empty] | 4 | PM |  | Past Compliance | -563
October | PDXS | PDX82 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 10 |  | 2025-10-03 | 2025-08-09 | 2025-11-27 | Completed |  | 2025-10-03 | 2025-10-03 | [8 empty] | 4 | PM |  | Past Compliance | -245
December | PDXS | PDX82 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 6 |  | 2025-12-12 | 2025-10-18 | 2026-02-05 | Completed |  | 2025-12-12 | 2025-12-12 | [8 empty] | 4 | PM |  | Past Compliance | -175
March | PDXS | PDX80 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 16 |  | 2026-03-13 | 2026-01-17 | 2026-05-07 | On Hold | MCM-143631288 | 2026-03-13 | 2026-03-13 |  |  | Complete | Tier 2 | kenmccot | 2026-04-27 07:00 | 2026-05-28 06:55 | Successful - Off Script | 4 | PM |  | Past Compliance | -84 | MCM Complete
March | PDXS | PDX82 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 2 |  | 2026-03-13 | 2026-01-17 | 2026-05-07 | Completed | MCM-136370733 | 2026-03-13 | 2026-03-13 |  |  | Scheduled | Tier 2 | mqueener | 2026-05-18 07:00 | 2026-06-18 06:59 |  | 4 | PM |  | Past Compliance | -84
May | PDXS | PDX82 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-05-24 | 2026-03-30 | 2026-07-18 | Open | MCM-136370733 | 2026-05-24 | 2026-05-24 |  |  | Scheduled | Tier 2 | mqueener | 2026-05-18 07:00 | 2026-06-18 06:59 |  | 4 | PM |  | Within Compliance | -12 | MCM Scheduled
June | PDXS | PDX81 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-06-10 | 2026-04-16 | 2026-08-04 | Open | MCM-138742066 | 2026-06-10 | 2026-06-10 |  |  | Scheduled | Tier 2 | coombsja | 2026-05-04 07:00 | 2026-06-04 06:59 |  | 4 | PM |  | Within Compliance | 5 | MCM Scheduled
July | PDXS | PDX83 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | PPM | G.CNTRL.BACOP.36M | 36M | 24 |  | 2026-07-01 | 2026-05-07 | 2026-08-25 | Open | MCM-141405665 | 2026-07-01 | 2026-07-01 |  |  | Scheduled | Tier 3 | ravjuan | 2026-05-25 13:00 | 2026-06-25 06:59 |  | 4 | PM |  | Within Compliance | 26 | MCM Scheduled

## BACOP Upgrades
Month | Cluster | Site | Vendor | Description | EAM Category | EAM PM | FREQ | Metrics (WO/Building) | Days Required | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM/TT | Scheduled Start Date | Scheduled End Date | PO | Maintenance Cost | MCM Status | MCM Tier | MCM Tech | MCM Sched Start | MCM Sched End | MCM Closure | Priority | Job Type | Overall Status | Compliance Status | Days Until Due | MCM Gap Status
April | PDXS | PDX83 | Interstates | 1.5 Bacop health status alarm | CM |  |  | 1 |  | 2024-04-04 | 2024-02-09 | 2024-05-29 | Completed |  | 2024-04-04 | 2024-04-04 | [8 empty] | 5 | CM |  | Past Compliance | -792
April | PDXS | PDX82 | Interstates | BACOP 1.5B points unavailable | CM |  |  | 1 |  | 2024-04-18 | 2024-02-23 | 2024-06-12 | Completed |  | 2024-04-18 | 2024-04-18 | [8 empty] | 5 | CM |  | Past Compliance | -778
April | PDXS | PDX81 | Interstates | BACOP 2.1A PDC-6 Meter Error Alarm | CM |  |  | 1 |  | 2024-04-28 | 2024-03-04 | 2024-06-22 | Completed |  | 2024-04-28 | 2024-04-28 | [8 empty] | 5 | CM |  | Past Compliance | -768
June | PDXS | PDX80 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2024-06-04 | 2024-04-10 | 2024-07-29 | Completed |  | 2024-06-04 | 2024-06-04 | [8 empty] | 3 | SRVY |  | Past Compliance | -731
June | PDXS | PDX80 | Interstates | FRB: Identify Hanley BACOPs with Cyber Sciences SER-3200 SERs | SRVY |  |  | 3 |  | 2024-06-04 | 2024-04-10 | 2024-07-29 | Completed |  | 2024-06-04 | 2024-06-04 | [8 empty] | 5 | SRVY |  | Past Compliance | -731
July | PDXS | PDX83 | Interstates | Bacop 2.6A Metering | CM |  |  | 3 |  | 2024-07-01 | 2024-05-07 | 2024-08-25 | Completed |  | 2024-07-01 | 2024-07-01 | [8 empty] | 5 | CM |  | Past Compliance | -704
July | PDXS | PDX81 | Interstates | Follow up required for the [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | FPM |  |  | 1 |  | 2024-07-03 | 2024-05-09 | 2024-08-27 | Completed |  | 2024-07-03 | 2024-07-03 | [8 empty] | 4 | FPM |  | Past Compliance | -702
July | PDXS | PDX80 | Interstates | [PDX80] BACOP 7B Dim disconnecting | BRKD |  |  | 2 |  | 2024-07-05 | 2024-05-11 | 2024-08-29 | Completed |  | 2024-07-05 | 2024-07-05 | [8 empty] | 5 | BRKD |  | Past Compliance | -700
July | PDXS | PDX82 | Interstates | BACOP 1.5B in alarm | BRKD |  |  | 1 |  | 2024-07-15 | 2024-05-21 | 2024-09-08 | Completed |  | 2024-07-15 | 2024-07-15 | [8 empty] | 5 | BRKD |  | Past Compliance | -690
August | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 9 |  | 2024-08-10 | 2024-06-16 | 2024-10-04 | Completed |  | 2024-08-10 | 2024-08-10 | [8 empty] | 3 | SRVY |  | Past Compliance | -664
September | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 4 |  | 2024-09-09 | 2024-07-16 | 2024-11-03 | Completed |  | 2024-09-09 | 2024-09-09 | [8 empty] | 3 | SRVY |  | Past Compliance | -634
October | PDXS | PDX138 | Interstates | FRB: Identify Hanley BACOPs with Cyber Sciences SER-3200 SERs | SRVY |  |  | 9 |  | 2024-10-10 | 2024-08-16 | 2024-12-04 | Completed |  | 2024-10-10 | 2024-10-10 | [8 empty] | 5 | SRVY |  | Past Compliance | -603
October | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 6 |  | 2024-10-10 | 2024-08-16 | 2024-12-04 | Completed |  | 2024-10-10 | 2024-10-10 | [8 empty] | 3 | SRVY |  | Past Compliance | -603
November | PDXS | PDX82 | Interstates | 1.5B BACOP troubleshooting | CM |  |  | 2 |  | 2024-11-01 | 2024-09-07 | 2024-12-26 | Completed |  | 2024-11-01 | 2024-11-01 | [8 empty] | 5 | CM |  | Past Compliance | -581
November | PDXS | PDX83 | Interstates | BACOP Firmware Upgrade | FPM |  |  | 130 |  | 2024-11-04 | 2024-09-10 | 2024-12-29 | Completed |  | 2024-11-04 | 2024-11-04 | [8 empty] | 5 | FPM |  | Past Compliance | -578
November | PDXS | PDX138 | Interstates | FRB: Identify Hanley BACOPs with Cyber Sciences SER-3200 SERs | SRVY |  |  | 116 |  | 2024-11-13 | 2024-09-19 | 2025-01-07 | Completed |  | 2024-11-13 | 2024-11-13 | [8 empty] | 5 | SRVY |  | Past Compliance | -569
November | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2024-11-13 | 2024-09-19 | 2025-01-07 | Completed |  | 2024-11-13 | 2024-11-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -569
December | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 3 |  | 2024-12-12 | 2024-10-18 | 2025-02-05 | Completed |  | 2024-12-12 | 2024-12-12 | [8 empty] | 3 | SRVY |  | Past Compliance | -540
December | PDXS | PDX83 | Interstates | Rows 48 & 50 BACOP Metering | PR |  |  | 3 |  | 2024-12-18 | 2024-10-24 | 2025-02-11 | Completed |  | 2024-12-18 | 2024-12-18 | [8 empty] | 5 | PR |  | Past Compliance | -534
December | PDXS | PDX81 | Interstates | PDX81 BACOP Health alarms | CM |  |  | 4 |  | 2024-12-30 | 2024-11-05 | 2025-02-23 | Completed |  | 2024-12-30 | 2024-12-30 | [8 empty] | 5 | CM |  | Past Compliance | -522
January | PDXS | PDX138 | Interstates | FDN: Identify BACOP panels running v3 for proactive reboot | SRVY |  |  | 5 |  | 2025-01-15 | 2024-11-21 | 2025-03-11 | Completed |  | 2025-01-15 | 2025-01-15 | [8 empty] | 3 | SRVY |  | Past Compliance | -506
January | PDXS | PDX82 | Interstates | BACOP health alarm | REG-FOLL |  |  | 1 |  | 2025-01-19 | 2024-11-25 | 2025-03-15 | Completed |  | 2025-01-19 | 2025-01-19 | [8 empty] | 5 | REG-FOLL |  | Past Compliance | -502
February | PDXS | PDX82 | Interstates | BACOP 1.5B DC UPS alarm | CM |  |  | 1 |  | 2025-02-14 | 2024-12-21 | 2025-04-10 | Completed |  | 2025-02-14 | 2025-02-14 | [8 empty] | 5 | CM |  | Past Compliance | -476
May | PDXS | PDX83 | Interstates | Bacop 2.5 A | PR |  |  | 2 |  | 2025-05-01 | 2025-03-07 | 2025-06-25 | Completed |  | 2025-05-01 | 2025-05-01 | [8 empty] | 5 | PR |  | Past Compliance | -400
May | PDXS | PDX80 | Interstates | BACOP_9A_SER - Health in Alarm State. | CM |  |  | 1 |  | 2025-05-02 | 2025-03-08 | 2025-06-26 | Completed |  | 2025-05-02 | 2025-05-02 | [8 empty] | 5 | CM |  | Past Compliance | -399
May | PDXS | PDX82 | Interstates | BACOP 1.5B Battery replacement | CM |  |  | 1 |  | 2025-05-05 | 2025-03-11 | 2025-06-29 | Completed |  | 2025-05-05 | 2025-05-05 | [8 empty] | 5 | CM |  | Past Compliance | -396
May | PDXS | PDX81 | Interstates | BACOP 2.1A Troubleshooting | CM |  |  | 2 |  | 2025-05-17 | 2025-03-23 | 2025-07-11 | Completed |  | 2025-05-17 | 2025-05-17 | [8 empty] | 5 | CM |  | Past Compliance | -384
June | PDXS | PDX82 | Interstates | bacop 1.5B PDC comms | CM |  |  | 1 |  | 2025-06-03 | 2025-04-09 | 2025-07-28 | Completed |  | 2025-06-03 | 2025-06-03 | [8 empty] | 5 | CM |  | Past Compliance | -367
June | PDXS | PDX80 | Interstates | BACOP 3B | CM |  |  | 1 |  | 2025-06-09 | 2025-04-15 | 2025-08-03 | Completed |  | 2025-06-09 | 2025-06-09 | [8 empty] | 5 | CM |  | Past Compliance | -361
June | PDXS | PDX138 | Interstates | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXS | PDX80 | Interstates | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 6 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXS | PDX81 | Interstates | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXS | PDX82 | Interstates | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 25 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXS | PDX83 | Interstates | FSB: Identify BACOPs supporting homogenous TRN2P rack lineups | SRVY |  |  | 26 |  | 2025-06-13 | 2025-04-19 | 2025-08-07 | Completed |  | 2025-06-13 | 2025-06-13 | [8 empty] | 3 | SRVY |  | Past Compliance | -357
June | PDXS | PDX81 | Interstates | [GLOBAL] BACKSTOPPING CONTROL PANEL 12M PM V1.0 | FPM |  | 12 | 2 |  | 2025-06-08 | 2025-05-02 | 2025-07-15 | Completed |  | 2025-06-08 | 2025-06-08 | [8 empty] | 4 | FPM |  | Past Compliance | -362
July | PDXS | PDX82 | Interstates | BACOP 1.3A MCBU/MCBG comms loss | CM |  |  | 1 |  | 2025-07-25 | 2025-05-31 | 2025-09-18 | Completed |  | 2025-07-25 | 2025-07-25 | [8 empty] | 5 | CM |  | Past Compliance | -315
August | PDXS | PDX138 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 25 |  | 2025-08-11 20:57 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 20:57 | 2025-08-11 20:57 | [8 empty] | 5 | FRB |  | Past Compliance | -297
August | PDXS | PDX80 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 23 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Completed |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298
August | PDXS | PDX81 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 46 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXS | PDX82 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 10 |  | 2025-08-11 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 | 2025-08-11 | [8 empty] | 5 | FRB |  | Past Compliance | -298 | MCM OVERDUE
August | PDXS | PDX83 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 20 |  | 2025-08-11 23:00 | 2025-06-17 | 2025-10-05 | Open |  | 2025-08-11 23:00 | 2025-08-11 23:00 | [8 empty] | 5 | FRB |  | Past Compliance | -297 | MCM OVERDUE
August | PDXS | PDX82 | Interstates | BACOP 1.2A Stratix Switch Port Configuration Alarm | CM |  |  | 1 |  | 2025-08-30 | 2025-07-06 | 2025-10-24 | Completed |  | 2025-08-30 | 2025-08-30 | [8 empty] | 5 | CM |  | Past Compliance | -279
September | PDXS | PDX138 | Interstates | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXS | PDX80 | Interstates | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXS | PDX81 | Interstates | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXS | PDX82 | Interstates | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXS | PDX83 | Interstates | FDN: Notification -BACOP Armor Block Failure Remediation | FSB |  |  | 1 |  | 2025-09-03 | 2025-07-10 | 2025-10-28 | Completed |  | 2025-09-03 | 2025-09-03 | [8 empty] | 4 | FSB |  | Past Compliance | -275
September | PDXS | PDX80 | Interstates | BACOP 3B MCBB meter failure | CM |  |  | 1 |  | 2025-09-05 | 2025-07-12 | 2025-10-30 | Completed |  | 2025-09-05 | 2025-09-05 | [8 empty] | 5 | CM |  | Past Compliance | -273
September | PDXS | PDX82 | Interstates | BACOP comms testing | CM |  |  | 1 |  | 2025-09-12 | 2025-07-19 | 2025-11-06 | Completed |  | 2025-09-12 | 2025-09-12 | [8 empty] | 5 | CM |  | Past Compliance | -266
September | PDXS | PDX83 | Interstates | Bacop 1.4B BOB not connected | CM |  |  | 1 |  | 2025-09-18 | 2025-07-25 | 2025-11-12 | Completed |  | 2025-09-18 | 2025-09-18 | [8 empty] | 5 | CM |  | Past Compliance | -260
December | PDXS | PDX82 | Interstates | BACOP 2.2A Unhealthy | CM |  |  | 1 |  | 2025-12-14 | 2025-10-20 | 2026-02-07 | Completed |  | 2025-12-14 | 2025-12-14 | [8 empty] | 5 | CM |  | Past Compliance | -173
January | PDXS | PDX80 | Interstates | FRB: Update BACOP Panels to firmware v4.2 | FRB |  |  | 14 |  | 2026-01-26 | 2025-12-02 | 2026-03-22 | Open | MCM-140619180 | 2026-01-26 | 2026-01-26 |  |  | Complete | Tier 3 | qtedavid | 2026-01-05 08:00 | 2026-02-05 07:59 | Successful | 5 | FRB |  | Past Compliance | -130 | MCM Complete

## 90 Day Outlook
Site | Description | Metrics (WO/Building) | Upgrades Needed? | PM Due Date | Compliance Start Date | Compliance End Date | Status | MCM Scheduled Start Date | MCM Scheduled End Date | MCM/TT | Vendor Start Date | Vendor End Date | Site Confirmation | MCM Gap Status
PDX80 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 16 | Yes | 2026-03-13 | 2026-01-17 | 2026-05-07 | Complete | 2026-04-27 07:00 | 2026-05-28 06:55 | MCM-143631288 |  |  |  | MCM Complete
PDX81 | [GLOBAL] AMCOP 36M PM V1.0 | 6 | Yes | 2026-05-15 | 2026-03-21 | 2026-07-09 | MCM in Draft | 2026-06-18 07:00 | 2026-08-12 06:55 | MCM-150801576 |  |  |  | MCM Pending Approval
PDX82 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-05-24 | 2026-03-30 | 2026-07-18 | MCM Scheduled | 2026-05-18 07:00 | 2026-06-18 06:59 | MCM-136370733 |  |  |  | MCM Scheduled
PDX81 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-06-10 | 2026-04-16 | 2026-08-04 | MCM Scheduled | 2026-05-04 07:00 | 2026-06-04 06:59 | MCM-138742066 |  |  |  | MCM Scheduled
PDX83 | [GLOBAL] BACKSTOPPING CONTROL PANEL 36M PM V1.0 | 24 | Yes | 2026-07-01 | 2026-05-07 | 2026-08-25 | MCM Scheduled | 2026-05-25 13:00 | 2026-06-25 06:59 | MCM-141405665 |  |  |  | MCM Scheduled
PDX80 | [GLOBAL] AMCOP 36M PM V1.0 | 20 | Yes | 2026-07-30 | 2026-06-05 | 2026-09-23 | MCM in Draft | 2026-06-17 07:00 | 2026-07-18 06:55 | MCM-151427924 |  |  |  | MCM Pending Approval
PDX98 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | No | 2026-08-01 | 2026-06-07 | 2026-09-25 | MCM in Draft | 2026-06-17 07:00 | 2026-07-18 06:55 | MCM-151429971 |  |  |  | MCM Pending Approval
PDX83 | [GLOBAL] AMCOP 36M PM V1.0 | 9 | Yes | 2026-08-07 | 2026-06-13 | 2026-10-01 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)
PDX83 | [GLOBAL] AMCOP 36M PM V1.0 | 1 | Yes | 2026-09-18 | 2026-07-25 | 2026-11-12 | MCM Needed (<90d) | [6 empty] | MCM Needed (<90d)